## Bridges in order bridge #
DCK ¦ 2010 Bridge Inspection Review and Rating ¦ Issued December 10th, 2010
Issues highlighted in red need attention for safety concerns
| Structure # | Road Name | Project-Branch # | Station (km) | Creek Name | Old load rating (Tonnes) | New load rating (Tonnes) | Reviewing Engineer | Notes | INSPECT IN 2011? | Snooper Truck inspection in 2011? (Y/N) | RESPONSIBILITY (OPS / BCTS)
1 | CK-2005 | Anderson River | 8074-01 | 2.7 | Gilt Creek | 41 | 41 | Greg Dohm P.Eng | Continue with current load rating
2 | CK-2007 | Anderson Seven | 8074-07 | 0.1 | Anderson River | 40 | 5 | Greg Dohm P.Eng | Downrate to 5 tonnes. Please post. Recommend replacing rotting log stringers.
3 | CK-2009 | Blue Mnt One | 5913-01 | 6 | Not known |  |  |  | NOT INSPECTED
4 | CK-2013 | Blue Mtn Five | 5913-05 | 1.5 | Not known |  |  |  | NOT INSPECTED
5 | CK-2014 | Cantelon Creek | 8124-01 | 8.2 | Cantelon Creek | 5 | zero | Greg Dohm P.Eng | Close bridge - please remove or replace bridge or barricade. |  |  | BCTS
6 | CK-2015 | Cantelon Creek | 8124-01 | 9 | Not known | 5 | 2 | Greg Dohm P.Eng | Downrate to 2 tonnes. Please post. Replace deck ties and plank deck if continued recreational access is required. Also would need to replace sills and potentially cribs prior to industrial hauling. |  |  | BCTS
7 | CK-2016 | Cantelon Creek | 8124-01 | 9.1 | Not known | 5 | zero | Greg Dohm P.Eng | Close bridge - please remove or replace bridge or barricade. |  |  | BCTS
8 | CK-2017 | Cantelon North | 8124-03 | 0.7 | Cantelon Creek (north fork) |  |  |  | NOT INSPECTED |  |  | BCTS
9 | CK-2019 | Cayoose Creek | 8110-01 | 0.1 | Skagit River | 62 | 62 | Greg Dohm P.Eng | Continue with current BCL-625 load rating
10 | CK-2022 | Chehalis | 8241-01 | 15.2 | Statlu Creek | 90 | 90 | Greg Dohm P.Eng | Provide additional riprap protection at left abutment to prevent further scour behind cast-in-place footing, where approaches are supported by side log cribs.
11 | CK-2027 | Chehalis | 8241-01 | 31.7 | Skwellepil Creek | 90 | 90 | Greg Dohm P.Eng | Bailey Bridge
12 | CK-2028 | Chehalis | 8241-01 | 39.81 | West Eagle Creek | NA | NA | Greg Dohm P.Eng | NOT INSPECTED - unable to land; only 1 stringer remaining. Do NOT reinspect.
13 | CK-2029 | Chehalis | 8241-01 | 39.9 | Statlu Lake Creek | NA | NA | Greg Dohm P.Eng | NOT INSPECTED - unable to land; deck is almost gone. Do NOT reinspect.
14 | CK-2034 | Chehalis-Statlu | 8241-02 | 9.7 | Not Known | NA | NA | Greg Dohm P.Eng | NOT INSPECTED - unable to land; structure looks badly plugged with gravel. Do NOT reinspect.
15 | CK-2036 | Chehalis-Southstatlu | 8241-03 | 0.2 | Statlu Creek | 136 | 136 | Greg Dohm P.Eng | Recommend repairs to curb rails and monitoring scouring at abutment noted.
16 | CK-2039 | Chehalis-Southstatlu | 8241-03 | 9.5 | Dickson Creek |  |  |  | NOT INSPECTED
17 | CK-2047 | Chehalis-Mystery | 8241-11 | 11.9 | Mystery Creek | 54 | 30 | Greg Dohm P.Eng | Downrate to 30 tonne until deck joints and grout pockets are inspected properly. Inspection requires that gravel be swept/shovelled off for visual inspection of deck joints and pockets.
18 | CK-2048 | Chilliwack River | 5127-01 | 1 | Side Creek |  |  |  | NOT INSPECTED |  |  | BCTS
19 | CK-2049 | Chilliwack River | 5127-01 | 1.5 | Side Creek |  |  |  | NOT INSPECTED |  |  | BCTS
20 | CK-2054 | Liumchen Creek | 5127-02 | 0.9 | Little Tamihi Creek |  |  |  | NOT INSPECTED
21 | CK-2055 | Liumchen Creek | 5127-02 | 2.5 | Deer Creek |  |  |  | NOT INSPECTED
21 | CK-2056 | Liumchen West | 5127-03 | 8.5 | Liumchen Creek |  |  |  | NOT INSPECTED
22 | CK-2057 | Liumchen West | 5127-03 | 9 | Slug Creek |  |  |  | NOT INSPECTED
23 | CK-2058 | Liumchen West | 5127-03 | 9.5 | East Liumchen Creek |  |  |  | NOT INSPECTED
24 | CK-2059 | Liumchen West | 5127-03 | 12.8 | Liumchen Creek |  |  |  | NOT INSPECTED
25 | CK-2060 | Liumchen West | 5127-03 | 13.1 | Not Known |  |  |  | NOT INSPECTED
26 | CK-2061 | Little Tamihi West | 5127-04 | 0.7 | Liumchen Creek |  |  |  | NOT INSPECTED
27 | CK-2062 | Little Tamihi West | 5127-04 | 13 | Not Known |  |  |  | NOT INSPECTED
28 | CK-2064 | Chilliwack-Tamihi Cr | 5127-06 | 6.3 | Tamihi Creek | 68 | 68 | Greg Dohm P.Eng | Brushing needed and other repairs as noted.
29 | CK-2065 | Chilliwack-Tamihi Cr | 5127-06 | 8.3 | Fumerol Creek | 0 | 0 | Greg Dohm P.Eng | Close bridge by barricades or remove
30 | CK-2066 | Chilliwack-Tamihi Cr | 5127-06 | 10.3 | Stapley Creek | 68 | 62 | Greg Dohm P.Eng | Inspector did not drill for rot, however assessed as fair condition. Stringer diameters from file indicate load rating for BCL-625 or 62 tonnes is reasonable provided stringer rot is minimal. Reinspect next year but require drilling for rot depths on accessible stringers. Bridge is very old and should be replaced asap.
31 | CK-2068 | Slesse Creek | 5127-07 | 6.1 | Slesse Creek | 54 | 54 | Greg Dohm P.Eng | L60 or 54 tonne load rating. Please post.
32 | CK-2069 | Slesse-Borden | 5127-08 | 0.7 | Side Creek |  |  |  | NOT INSPECTED
32 | CK-2073 | Chipmunk Creek | 5127-12 | 1.5 | Chipmunk Creek | 68 | 68 | Greg Dohm P.Eng | Damaged curb rail needs repair.
33 | CK-2074 | Chipmunk Creek | 5127-12 | 8.3 | Chipmunk Creek | 54 | 54 | Greg Dohm P.Eng | Rail car bridge. L60 or 54 tonne load rating. Please post.
34 | CK-2075 | Foley Creek | 5127-13 | 2.1 | Foley Creek | 54 | 54 | Greg Dohm P.Eng | Please ensure this load rating posting gets corrected asap to show 54 tonnes and not 154 tonnes (ie. looks like someone marked-up the sign.)
35 | CK-2076 | Foley Creek | 5127-13 | 4.4 | Foley Creek | 54 | 54 | Greg Dohm P.Eng | Repair rotten planks on running deck. Continue with current load rating. |  |  | BCTS
36 | CK-2077 | Airplane Creek | 5127-14 | 0.1 | Foley Creek | 54 | 54 | Greg Dohm P.Eng | Concrete slab girders have gravel on deck, so inpsector was unable to inspect the shear connectors. Please clean deck and provide photos of shear connectors to Region, Thanks.
36 | CK-2084 | Chilliwack South | 5127-26 | 0 | Back channel | 54 | 54 | Greg Dohm P.Eng |  |  |  | BCTS
37 | CK-2085 | Chilliwack South | 5127-26 | 0.1 | Chilliwack River | 91 | 91 | Greg Dohm P.Eng | Repair rotten deck planks. Continue with current load rating of L100 or 91 tonnes. Please post. |  |  | BCTS
38 | CK-2086 | Chwk-South | 5127.26 | 4.2 |  | 68 | 68 | Greg Dohm P.Eng | Continue with L75 or 68 tonne load rating. Please post. Remove old stringer structure to ensure portable bridge bears correctly on end sills. |  |  | BCTS
39 | CK-2102 | Florence-Rocky | 8648.02 | 0.925 |  | 54 | 54 | Greg Dohm P.Eng |  |  |  | BCTS
40 | CK-2103 | Blue Mtn Five | 5913-05 | 1.5 | Not Known |  |  |  | NOT INSPECTED
41 | CK-2106 | Harrison East | 5748-01 | 15.4 | Bear Creek | 68 |  | Greg Dohm P.Eng | Continue with current load rating. Please send as-built drawings to Region so we can update CBR and the file. Thanks.
42 | CK-2108 | Harrison East | 5748-01 | 30.7 | Not Known | 136 | 136 | Greg Dohm P.Eng | New slab girder bridge.
43 | CK-2116 | Harrison East | 5748-01 | 64.4 | Big Silver Creek | 0 | 0 | Greg Dohm P.Eng | Close bridge by barricades or remove bridge.
44 | CK-2118 | Cogburn Creek | 5748-02 | 8 | Hut Creek | 0 | 0 | Greg Dohm P.Eng | Bridge washed out. Girders still in dry creek.
45 | CK-2119 | Cogburn Creek | 5748-02 | 4.8 | North Cogburn Creek | 41 | 0 | Greg Dohm P.Eng | Unable to land at bridge to inspect. Close bridge by barricades or remove bridge.
46 | CK-2120 | Bear Creek | 5748-03 | 7 | Not Known | unknown | 41 | Greg Dohm P.Eng | Downrate to 41 tonnes or L45. Please post.
47 | CK-2123 | Shovel Creek | 5748-06 | 7.6 | Pick Creek |  |  |  | NOT INSPECTED
48 | CK-2126 | Lookout Peak | 5748-07 | 0.1 | Bear Creek | unknown | unknown | Greg Dohm P.Eng | Portable bridge over spanning log stringer bridge. Design rating of portable not noted in inspection or on file. Please provide portable bridge design rating to Region. Thanks.
49 | CK-2140 | Harrison West | 6314-01 | 46.5 | Davidson Creek | 54 | 41 | Greg Dohm P.Eng | Immediate works are to replace broken curb rails and monitor ties from underside over winter to ensure they are not cracking or showing other signs of failure. In order to keep this industrial load rating, the wooden deck will need to be replaced next summer (including ties).
50 | CK-2144 | Harrison West | 6314-01 | 56.3 | Bremner Creek | 68 | 62 | Greg Dohm P.Eng | Re-post at 62 tonnes.
51 | CK-2146 | Harrison West | 6314-01 | 64.4 | Coon Creek | 91 | 91 | Greg Dohm P.Eng | Not posted.
52 | CK-2147 | Harrison West | 6314-01 | 66.9 | Tretheway Creek | 91 | 91 | Greg Dohm P.Eng | Not posted.
53 | CK-2148 | Simms Creek | 6314-07 | 8.6 | Simms Creek |  |  |  | NOT INSPECTED
54 | CK-2149 | Walian Creek | 6314-08 | 7.2 | Walian Creek | 0 | 0 | Greg Dohm P.Eng | Log stringer bridge. Close bridge by barricades or remove bridge.
54 | CK-2158 | Lorenzetta Hunter | 6086-01 | 9.8 | Hunter Creek | 68 | 68 | Greg Dohm P.Eng |  |  |  | BCTS
55 | CK-2159 | Lorenzetta Hunter | 6086-01 | 9.8 | Hunter Creek |  |  |  | NOT INSPECTED |  |  | BCTS
56 | CK-2160 | Lorenzetta Hunter | 6086-01 | 12 | Lorenzetta Creek |  |  |  | NOT INSPECTED |  |  | BCTS
57 | CK-2161 | Hunter East | 6086-02 | 1.3 | Side Creek | 62 | 62 | Greg Dohm P.Eng | Portable bridge TCH0501. L165 superstructure. Bearing support is only partial Portable bridge TCH0501. L165 superstructure. Bearing support is only partial at one end and is poor. Sill plate is rotting at other end. Riprap needs work. Bridge needs to be reinstalled asap. Continued current rating is provided for short term only to enable continued industrial traffic until re-installation is completed. |  |  | BCTS
58 | CK-2162 | Lost Creek | 8466-01 | 0.8 | Not Known | 150 | 150 | Greg Dohm P.Eng | Continue with current load rating.
59 | CK-2163 | Lost Creek | 8466-01 | 1.1 | Not Known | 136 | 136 | Greg Dohm P.Eng | Csp culvert
60 | CK-2164 | Lost Creek | 8466-01 | 1.4 | Not Known | 68 | 68 | Greg Dohm P.Eng | Csp culvert
61 | CK-2165 | Lost Creek | 8466-01 | 2.2 | Murdo Creek | 68 | 68 | Greg Dohm P.Eng
62 | CK-2166 | Lost Creek | 8466-01 | 5 | Weatherhead Creek | 55 | 55 | Greg Dohm P.Eng
63 | CK-2167 | Lost Creek | 8466-01 | 8.4 | Lost Creek | 68 | 68 | Greg Dohm P.Eng | Structure TCH0401 |  |  | BCTS
64 | CK-2168 | Lost Creek | 8466-01 | 8.3 | Twin Lakes Creek | 68 | 68 | Greg Dohm P.Eng |  |  |  | BCTS
65 | CK-2169 | Lost Creek | 8466-01 | 14.14 | Boulder Creek | 54 | 54 | Greg Dohm P.Eng | Recommended that curbs be repaired/replaced |  |  | BCTS
66 | CK-2170 | Lost Creek | 8466-01 | 16.6 | Teripocki Creek | 54 | 54 | Greg Dohm P.Eng | Recommended that curbs be repaired/replaced |  |  | BCTS
67 | CK-2171 | Lost Creek | 8466-01 | 17.305 | Kenyon Creek | 54 | 54 | Greg Dohm P.Eng |  |  |  | BCTS
68 | CK-2172 | Lost Creek | 8466-01 | 18.8 | Kenyon Creek | 54 | 20 | Greg Dohm P.Eng | Stringer rot observed. Based on previous as-built information for stringer sizes downrate to 20 tonnes. Please post. |  |  | BCTS
67 | CK-2173? | Lost Creek | 8466-01 | 18.9 | Side Creek | unknown | 20 | Greg Dohm P.Eng | CBR says this bridge is gone...however, still exists. Downrate to 20 tonnes. Please post. |  |  | BCTS
68 | CK-2174 | Lost-Murdo | 8466-02 | 0.7 | Side Creek | 5 | 5 | Greg Dohm P.Eng | Please post load rating sign at 5 tonnes |  |  | BCTS
69 | CK-2175 | Lost-Murdo | 8466-02 | 1.2 | Not Known | 5 | 5 | Greg Dohm P.Eng |  |  |  | BCTS
70 | CK-2177 | Lost-South | 8466-04 | 4.9 | Side Creek | 0 | 0 | Greg Dohm P.Eng | Close bridge by barricades or remove bridge.
71 | CK-2178 | Terepocki | 8466-06 | 2.4 | Salsbury Creek | 10 | 5 | Greg Dohm P.Eng | Downrate to 5 tonnes. Please post. Recommend planning to replace deck. |  |  | BCTS
71 | CK-2179 | Terepocki | 8466-06 | 5.2 | Salsbury Creek | [6 empty] | BCTS
72 | CK-2180 | Terepocki | 8466-06 | 5.5 | Not Known | 10 | 0 | Greg Dohm P.Eng | Close bridge by barricades or remove bridge.
73 | CK-2183 | Lost-North | 8466-07 | 3.1 | side creek | 10 | 0 | Greg Dohm P.Eng | Close bridge by barricades or remove bridge.
74 | CK-2186 | Mount Kettley | 8466-10 | 0.2 | Not Known | 68 | 68 | Greg Dohm P.Eng | Recommended that curbs be repaired/replaced |  |  | BCTS
75 | CK-2188 | Lost Blacklock Ck | 8466.11 | 0.45 |  | 68 | 68 | Greg Dohm P.Eng | Recommended that curbs be repaired/replaced |  |  | BCTS
76 | CK-2189 | Lost Blacklock Ck | 8466.11 | 1.98 | Side Creek | 68 | 68 | Greg Dohm P.Eng |  |  |  | BCTS
77 | CK-2190 | Lost Blacklock Ck | 8466.11 | 2.15 | Side Creek | 68 | 68 | Greg Dohm P.Eng |  |  |  | BCTS
78 | CK-2191 | Lost Blacklock Ck | 8466.11 | 2.47 | Side Creek | 68 | 68 | Greg Dohm P.Eng |  |  |  | BCTS
78 | CK-2196 | Nahatlatch | 6996-01 | 0.8 | Nahatlatch River | 68 | 68 | Greg Dohm P.Eng
78 | CK-2200 | Nehatlatch-Kookipi | 6996.02 | 0.08 | Nahatlatch River | 54 | 54 | Greg Dohm P.Eng |  |  |  | BCTS
79 | CK-2201 | Nehatlatch-Kookipi | 6996.02 | 3.18 | Kookipi Creek | 54 | 54 | Greg Dohm P.Eng | Repair damaged and rotting curbs |  |  | BCTS
80 | CK-2202 | Nehatlatch-Kookipi | 6996.02 | 15.86 |  | 91 | 91 | Greg Dohm P.Eng |  |  |  | BCTS
81 | CK-2203 | Kookipi Three | 6996-03 | 2.4 | Not Known |  |  |  | NOT INSPECTED |  |  | BCTS
82 | CK-2204 | North Ainslie Creek | 8019-01 | 10.8 | Goulah Creek | 41 | 41 | Greg Dohm P.Eng | Log stringer bridge. Continue with current load rating. Please post.
83 | CK-2214 | Peers Ck | 8126.01 | 0.263 |  | 54 | 54 | Greg Dohm P.Eng |  |  |  | BCTS
84 | CK-2217 | Pitt River | 8394-01 | 2.2 | Side Creek | unknown | 54 | Greg Dohm P.Eng | Please send as-built drawing for portable superstructure for load rating. Current rating not to exceed 54 tonnes or L60 until further superstructure information is provided.
85 | CK-2218 | Pitt River | 8394-01 | 8 | Fish Hatchery Creek | unknown | unknown | Greg Dohm P.Eng | Please send as-built drawings for load rating.
86 | CK-2219 | Pitt River | 8394-01 | 9.8 | Corbold Creek | unknown | unknown | Greg Dohm P.Eng | Please send as-built drawings for load rating.
87 | CK-2222 | Pitt River | 8394-01 | 18.2 | Side Creek | unknown | 62 | Greg Dohm P.Eng | BCL-625 or 62 tonnes load rating, please post.
88 | CK-2223 | Pitt River | 8394-01 | 20.2 | Side Creek | unknown | 62 | Greg Dohm P.Eng | WBC - remove from CBR
89 | CK-2224 | Pitt River | 8394-01 | 23 | Shale Creek | 91 | 91 | Greg Dohm P.Eng | Replace broken and rotten planking
90 | CK-2225 | Pitt River | 8394-01 | 24.6 | Blue Creek | unknown | 0 | Greg Dohm P.Eng | Close bridge by barricades or remove bridge. In CBR there is some sort of mix-up on this bridge number.
91 | CK-2226 | Pitt-Boise | 8394-02 | 0.3 | Pitt River | 91 | 91 | Greg Dohm P.Eng | Replace broken and rotten planking
92 | CK-2227 | Pitt-Boise | 8394-02 | 2 | Side Creek | 62 | 62 | Greg Dohm P.Eng | Repair sink hole in gravel deck. Align traffic clear of rotting outside stringer. BCL-625 or 62 tonnes. Please post.
93 | CK-2228 | Pitt-Boise | 8394-02 | 3.2 | Side Creek | 62 | 62 | Greg Dohm P.Eng | BCL-625 or 62 tonnes load rating, please post.
94 | CK-2229 | Pitt-Boise | 8394-02 | 4.7 | Side Creek | Unknown | 20 | Greg Dohm P.Eng | Remove from CBR as this is only 5m long. (stringers look like their rotting; plan to replace).
95 | CK-2230 | Pitt-Boise | 8394-02 | 7.6 | Boise Creek | 100 | 62 | Greg Dohm P.Eng | Downrate to 62 tonnes or BCL-625 until rotten running planks are replaced. Please post.
96 | CK-2233 | Pitt-Steve | 8394-04 | 0.7 | Steve Creek | 109 | 109 | Greg Dohm P.Eng | Post at 109 tonnes or L120 design vehicle.
97 | CK-2234 | Ruby Creek | 8125-01 | 17 | West Fork Ruby Creek | 54 | unknown | Greg Dohm P.Eng | NOT INSPECTED - could not land.
98 | CK-2234 | Ruby Ck | 8125.03 | 13.52 |  | na | na | Greg Dohm P.Eng | NOT INSPECTED - could not land. - duplicate of above. |  |  | BCTS
99 | CK-2235 | Scuzzy Creek | 8127-01 | 6.6 | Scuzzy Creek | Unknown | 62 | Greg Dohm P.Eng | NEED TO COME BACK TO THIS ONE!!! Significant tension cracks opening up adjacent to the lock-block foundation. Need as-built drawings to confirm lock-blocks extend to stream elevation. Monitor tension cracks monthly will bridge open. Limit bridge rating to BCL-625 or 62 tonnes.
100 | CK-2240 | Spuzzum Ck | 8128.01 | 5.025 |  | 54 | 54 | Greg Dohm P.Eng |  |  |  | BCTS
101 | CK-2241 | Spuzzum Creek | 8128-01 | 25.4 | not known | 54 | 54 | Greg Dohm P.Eng |  |  |  | BCTS
102 | CK-2243 | Spuzzum-Urquhart | 8128-02 | 6.6 | not known |  |  |  | NOT INSPECTED - could not land.
103 | CK-2244 | Spuzzum-Urquhart | 8128-02 | 11.5 | Urquhart Creek |  |  |  | NOT INSPECTED - could not land.
104 | CK-2247 | Spuzzum Six | 8128-06 | 0.4 | South Fork Urquhart Creek |  |  |  | NOT INSPECTED - could not land.
105 | CK-2248 | Spuzzum Ck | 8128.07 | 0.2 |  |  |  |  | NOT INSPECTED |  |  | BCTS
106 | CK-2249 | Spuzzum Seven | 8128-07 | 5.4 | Side Creek | 54 | 0 | Greg Dohm P.Eng | Bridge condemned due to rotten ties. Close bridge by barricades until deck replaced or remove bridge. |  |  | BCTS
107 | CK-2250 | Spuzzum Seven | 8128-07 | 5.9 | Side Creek | Unknown | 0 | Greg Dohm P.Eng | Bridge condemned due to rotten ties. Close bridge by barricades until deck replaced or remove bridge. |  |  | BCTS
108 | CK-2252 | Spuzzum Ten | 8128-10 | 4 | Southwest Fork |  |  |  | NOT INSPECTED - could not land.
109 | CK-2253 | Squeah | 6092-01 | 3.2 | not known | 5 | 5 | Greg Dohm P.Eng | Rivetted rail car. Poor decking, cribbing and curbing. Plan to replace entire bridge soon.
110 | CK-2254 | Squeah | 6092-01 | 6.6 | not known | 5 | 5 | Greg Dohm P.Eng | Welded rail car. Deck is in poor condition and underside of railcar is unable to be inspected due to overspan.
111 | CK-2255 | Squeah | 6092-01 | 8.6 | not known | 5 | 5 | Greg Dohm P.Eng | 5 tonne rating. Please post. Plan to replace entire bridge due to fruiting bodies and extensive rot.
112 | CK-2256 | Squeah | 6092-01 | 11.8 | Kieikum Creek | 5 | 5 | Greg Dohm P.Eng | Load rated for 5 tonnes. Please post. Plan to replace entire bridge due to extensive rot.
113 | CK-2260 | Stave River | 8013-01 | 4.1 | Roaring Creek |  |  |  | NOT INSPECTED
114 | CK-2261 | Stave River | 8013-01 | 8.5 | Winslow Creek | 68 | 54 | Greg Dohm P.Eng | Post at 54 tonnes or L60 design vehicle. Plan to replace deck on long span within 2011 for continued industrial traffic. Repair broken planks asap.
115 | CK-2264 | Stave River | 8013-01 | 13 | Side Creek | 18 | 10 | Greg Dohm P.Eng | Downrate to 10 tonnes. Please post. Recommend replacing bridge.
116 | CK-2271 | Stave River | 8013-01 | 26.2 | Stave River | 68 | 68 | Greg Dohm P.Eng
117 | CK-2272 | Stave River | 8013-01 | 26.7 | Side Creek |  |  |  | NOT INSPECTED
118 | CK-2273 | Stave River | 8013-01 | 30.9 | not known | 68 | 68 | Greg Dohm P.Eng
119 | CK-2274 | Stave River | 8013-01 | 31.6 | Side Creek | Unknown | 62 | Greg Dohm P.Eng | Replace 2 rotten outside stringers or place guide logsto keep wheel path clear of these stringers. There seems to be some mixup on this crossingID, as the previous inspection indicated this was a CSP culvert.
120 | CK-2275 | Stave River | 8013-01 | 32.8 | Side Creek | 68 | 68 | Greg Dohm P.Eng |  |  |  | BCTS
121 | CK-2277 | Winslow Creek | 8013-02 | 0.9 | Beaver Dam Creek | 68 | 68 | Greg Dohm P.Eng |  |  |  | BCTS
122 | CK-2278 | Winslow Creek | 8013-02 | 0.9 | Beaver Dam Creek | 68 | 68 | Greg Dohm P.Eng | Repair fill slope failure asap. Also attend to adding riprap to exposed post on pads. |  |  | BCTS
123 | CK-2282 | Sumallo Six | 7510-06 | 0.2 | Side Creek |  |  |  | NOT INSPECTED - blocked access
124 | CK-2286 | Tsileuh Creek | 7978-01 | 17.7 | South Fork Tsileuh Creek | Unknown |  | Greg Dohm P.Eng | Barricaded due to rock slide - not accessible except by motor bike. Do not inspect until road is re-opened in the future. Not load rated.
125 | CK-2287 | Silverhope | 8148-01 | 0.6 | Silverhope Creek (structure # 13) | 68 | 68 | Greg Dohm P.Eng | Load rating to be L75 or 68 tonnes upon regrouting base plates at bridge abutment supports.
126 | CK-2288 | Uztlius Creek | 7972-01 | 6.4 | not known | Unknown | NA | Greg Dohm P.Eng | Recommend replacing this structure due various stages of stringer rot. No rating provided as this is not a bridge.
127 | CK-2289 | Uztlius Creek | 7972-01 | 8.7 | not known | 68 | 68 | Greg Dohm P.Eng
128 | CK-2290 | Uztlius Creek | 7972-01 | 16.7 | not known | 68 | 68 | Greg Dohm P.Eng
129 | CK-2291 | Uztlius Creek | 7972-01 | 17.7 | not known | 68 | 68 | Greg Dohm P.Eng
130 | CK-2292 | Uztlius Creek | 7972-01 | 18.5 | Utzlius Creek | 68 | 68 | Greg Dohm P.Eng
131 | CK-2293 | Uztlius Creek | 7972-01 | 19 | Uztlius Creek | 68 | 68 | Greg Dohm P.Eng
132 | CK-2294 | Uztlius Creek | 7972-01 | 20.5 | Uztlius Creek | 68 | 68 | Greg Dohm P.Eng | Replace broken deck running planks and recommend replacing curb rails.
133 | CK-2295 | Uztlius Creek | 7972-01 | 21.9 | Uztlius Creek | 68 | 68 | Greg Dohm P.Eng | Recommend replacing curb rails
134 | CK-2297 | Uztlius Creek | 7972-01 | 25.9 | not known | Unknown | 20 | Greg Dohm P.Eng | Remove from CBR as this is less than 6m long. (stringers rotting; plan to replace).
135 | CK-2298 | Uztlius Creek | 7972-01 | 27.5 | Uztlius Creek | 68 | 68 | Greg Dohm P.Eng
136 | CK-2299 | Uztlius Creek | 7972-01 | 28.1 | Uztlius Creek | 68 | 68 | Greg Dohm P.Eng | Replace broken and rotten running deck planking
137 | CK-2300 | Uztlius Creek | 7972-01 | 30.8 | not known | 68 | 68 | Greg Dohm P.Eng | Repair curb rail immediately. Plan to replace deck within two years to maintain load rating.
138 | CK-2301 | Uztlius Creek | 7972-01 | 32.7 | not known | 68 | 68 | Greg Dohm P.Eng
139 | CK-2302 | Uztlius Creek | 7972-01 | 35.4 | not known | Unknown | 0 | Greg Dohm P.Eng | Rotten wood box culvert. Recommend barricading, removing or replacing immediately. Remove from CBR.
140 | CK-2304 | Uztlius Creek | 7972-01 | 6.6 | East Anderson Creek | Unknown | 0 | Greg Dohm P.Eng | Bridge condemned. Close bridge by permanent barricades or remove bridge.
141 | CK-2305 | Uztlius-E Anderson | 7972-02 | 11.7 | East Anderson Creek | 68 | 68 | Greg Dohm P.Eng
142 | CK-2306 | Uztlius Creek | 7972-01 | 12.6 | not known | 40 | 54 | Greg Dohm P.Eng | Additional fill was added since last inspection. Scour under right crib must be monitored regularly especially after storm events to ensure sill log continues to be adequately supported.
143 | CK-2307 | Uztlius-E Anderson | 7972-02 | 12.8 | East Anderson Creek | 68 | 68 | Greg Dohm P.Eng
144 | CK-2315 | Stave-Winslow | 8013.02 | 4.178 |  | 5 | 2 | Greg Dohm P.Eng | Downrate to 2 tonnes. Please post or barricade bridge. |  |  | BCTS
145 | CK-2319 | Garnet Creek | 7558-01 | 10.1 | Side Creek |  |  |  | NOT INSPECTED
146 | CK-2321 | Blue Mtn Two | 5913-02 | 2.2 | Martyn Creek 2 | 1 | 0 | Greg Dohm P.Eng | Bridge condemned. Remove bridge or barricade road completely.
147 | CK-2323 | Harrison West | 6314-01 | 61 | Not Known |  |  |  | NOT INSPECTED - bridge out
148 | CK-2327 | Stave River | 8013-01 | 0 | Side Creek |  |  |  | NOT INSPECTED
149 | CK-2328 | Jones Lake | 8149-01 | 12.7 | Flat Creek |  |  |  | NOT INSPECTED
150 | CK-2329 | Lost-South | 8466-04 | 1.2 | Not Known | 136 | 136 | Greg Dohm P.Eng | Current load rating to continue. |  |  | BCTS
151 | CK-2330 | Lost Blacklock Ck | 8466-11 | 1.37 |  | 68 | 68 | Greg Dohm P.Eng |  |  |  | BCTS
152 | CK-2331 | Stave River | 8013-01 | 5.1 | Camp Creek |  |  |  | NOT INSPECTED
153 | CK-2332 | Stave River | 8013-01 | 1.4 | Side Creek |  |  |  | NOT INSPECTED
154 | CK-2333 | Stave River | 8013-01 | 3 | Side Creek |  |  |  | NOT INSPECTED
155 | CK-2334 | Stave River | 8013-01 | 4.4 | Side Creek |  |  |  | NOT INSPECTED
156 | CK-2335 | Stave River | 8013-01 | 7.2 | Side Creek | 68 | 68 | Greg Dohm P.Eng
157 | CK-2336 | Stave River | 8013-01 | 7.2 | Side Creek | 68 | 68 | Greg Dohm P.Eng
158 | CK-2338 | Stave River | 8013-01 | 12.2 | not known | NA | NA | Greg Dohm P.Eng | CBR shows this as a CSP culvert - not a wood box culvert which is what was inspected. Reinspect next year looking for CSP culvert or else figure out discrepancy.
159 | CK-2339 | Stave River | 8013-01 | 13.6 | Side Creek | 68 | 68 | Greg Dohm P.Eng
160 | CK-2343 | Stave River | 8013-01 | 28.1 | Side Creek | 68 | 68 | Greg Dohm P.Eng
161 | CK-2345 | Winslow Creek | 8013-02 | 2.4 | Bradley Creek | 68 | 68 | Greg Dohm P.Eng |  |  |  | BCTS
162 | CK-2346 | Pitt-Boise | 8394-02 | 0.9 | not known | Unknown | 5 | Greg Dohm P.Eng | Downrate to 5 tonnes. Please post. Recommend bridge replacement.
163 | CK-2348 | Cogburn Creek | 5748-02 | 4.8 | (No Creek Present) | 136 | 136 | Greg Dohm P.Eng
164 | CK-2349 | Stave River | 8013-01 | 5.2 | Side Creek | 68 | 68 | Greg Dohm P.Eng
165 | CK-2350 | Stave River | 8013-01 | 6.7 | Side Creek |  |  |  | NOT INSPECTED
166 | CK-2351 | Uztlius-Stoyoma East | 7972-05 | 3.5 | Stoyoma Creek | 68 | 68 | Greg Dohm P.Eng |  |  |  | BCTS
167 | CK-2353 | Stave-Winslow | 8013.02 | 1.84 | Side Creek | 68 | 68 | Greg Dohm P.Eng |  |  |  | BCTS
168 | CK-2354 | Harrison East | 5748-01 | 16.8 | Side Creek | 91 | 91 | Greg Dohm P.Eng
169 | CK-2357 | Cantelon Ten | 8124-10 | 0.1 | Cantelon Creek | 54 | 2 | Greg Dohm P.Eng | Downrate to 2 tonne until ties replaced. Please post. |  |  | BCTS
170 | CK-2358 | Lost Creek | 8466-01 | 3.1 | not known | 54 | 54 | Greg Dohm P.Eng | One CSP culvert inlet is 90% plugged. The other 10% plugged. Needs to be cleaned.
171 | CK-2363 | Spuzzum Ck | 8128.01 | 24.65 | Side Creek | 68 | 68 | Greg Dohm P.Eng |  |  |  | BCTS
172 | CK-2365 | Lost Creek | 8466-01 | 1.1 | Side Creek |  |  |  | BRIDGE REMOVED NOV. 19 2010. NEED TO REMOVE FROM CBR (per Jim Neuman's email).
173 | CK-2369 | Spuzzum Ck | 8128.21 | 2.304 | Side Creek | 68 | 68 | Greg Dohm P.Eng | Damaged curb rail |  |  | BCTS
174 | CK-2370 | Karen Creek | 8240.01 | 1.882 | Karen Creek | 68 | 68 | Greg Dohm P.Eng |  |  |  | BCTS
175 | CK-2371 | Karen Creek | 8240-01 | 2.26 | Not Known | 68 | 68 | Greg Dohm P.Eng | Damaged curb rail |  |  | BCTS
175 | CK-2372 | Sowerby Creek | 8112-01 | 1.6 | Sowerby Creek | 68 | 68 | Greg Dohm P.Eng | There seems to be some mixup on this crossingID, as the previous CBR inspection indicated this was a concrete bridge and now this inspection indicates it is a CSP culvert.
176 | CK-2373 | Simms Creek | 6314-07 | 3.79 | Side Creek | 136 | 136 | Greg Dohm P.Eng | Remove from CBR because this is not a major culvert and road is restricted to 4WD access only
177 | CK-2378 | Stave River | 8013-01 | 8.8 | Winslow Side Channel |  |  |  | NOT INSPECTED
178 | CK-2379 | Chehalis | 8241-01 | 0 | Chehalis River |  |  |  | NOT INSPECTED
179 | CK-2380 | Chehalis-Fleetwood | 8241-08 | 12 | Upper Maisal Creek | Unknown | Unknown | Greg Dohm P.Eng | Please send as-built drawings to Region for load rating.
180 | CK-2382 | Chehalis-Statlu | 8241-02 | 24.6 | Side Creek |  |  |  | NOT INSPECTED
181 | CK-2386 | Centre Creek | 5127-17 | 5.1 | Centre Creek | 41 | 5 | Greg Dohm P.Eng | ATV access only. Post at 5 tonnes. |  |  | BCTS
182 | CK-2387 | Chilliwack River | 5127-01 | 6.7 | Paleface Creek Side Channel | 62 | 62 | Greg Dohm P.Eng |  |  |  | BCTS
183 | CK-2394 | Cogburn Creek | 5748-02 | 0.2 | Big Silver Creek |  |  |  | NOT INSPECTED
184 | CK-2395 | Harrison East | 5748-01 | 0.3 | Big Silver River |  |  |  | NOT INSPECTED
185 | CK-2400 | Nesakwatch Creek | 5127-16 | 1.07 | not known |  |  |  | NOT INSPECTED |  |  | BCTS
186 | CK-2401 | Nesakwatch Lake | 5127-24 | 1.64 | not known |  |  |  | NOT INSPECTED |  |  | BCTS
187 | CK-2406 | Pitt River | 8394-01 | 18.5 | not known | 62 | 62 | Greg Dohm P.Eng | Load rate for BCL-625 or 62 tonnes.
188 | CK-2416 | Squeah | 6092-01 | 13 | Kleikum Creek |  |  |  | NOT INSPECTED
189 | CK-2419 | Stave River | 8013-01 | 17 | Side Creek | Unknown | 62 | Greg Dohm P.Eng | This is a WBC. Debris restricting flow at outlet. Remove from CBR.
190 | CK-2420 | Stave River | 8013-01 | 17.5 | not known | Unknown | Unknown | Greg Dohm P.Eng | This is a WBC. It appears one stringer is broken. Debris restricting flow at outlet creating washout hazard. Recommend repairing asap.Remove from CBR.
191 | CK-2423 | Stave Lake | 8013 | 29.5 |  |  |  |  | NOT INSPECTED
192 | CK-2440 | Stave River | 8013-01 | 31.8 | Side Creek | Unknown | 62 | Greg Dohm P.Eng | Please send as-built drawings to Region for load rating. Load rating restricted to BCL-625 until as-built drawings reviewed.
193 | CK-2441 | Dewdney West | 10452-01 | 1.5 | Fifteen Mile Creek |  |  |  | NOT INSPECTED
194 | CK-2467 | Silverhope | 8148-01 | 8.4 | Unknown |  |  |  | NOT INSPECTED

## ck
CK2005
CK2007
CK2014
CK2015
CK2016
CK2019
CK2022
CK2027
CK2028
CK2029
CK2034
CK2036
CK2047
CK2064
CK2065
CK2066
CK2068
CK2073
CK2074
CK2075
CK2076
CK2077
CK2084
CK2085
CK2086
CK2102
CK2106
CK2108
CK2116
CK2118
CK2119
CK2120
CK2126
CK2140
CK2144
CK2146
CK2147
CK2149
CK2158
CK2161
CK2162
CK2163
CK2164
CK2165
CK2166
CK2167
CK2168
CK2169
CK2170
CK2171
CK2172
CK2173
CK2174
CK2175
CK2177
CK2178
CK2180
CK2183
CK2186
CK2188
CK2189
CK2190
CK2191
CK2196
CK2200
CK2201
CK2202
CK2204
CK2214
CK2217
CK2218
CK2219
CK2222
CK2223
CK2224
CK2225
CK2226
CK2227
CK2228
CK2229
CK2230
CK2233
CK2234
CK2235
CK2240
CK2241
CK2243
CK2244
CK2247
CK2249
CK2250
CK2252
CK2253
CK2254
CK2255
CK2256
CK2261
CK2264
CK2271
CK2273
CK2274
CK2275
CK2277
CK2278
CK2282
CK2286
CK2287
CK2288
CK2289
CK2290
CK2291
CK2292
CK2293
CK2294
CK2295
CK2297
CK2298
CK2299
CK2300
CK2301
CK2302
CK2304
CK2305
CK2306
CK2307
CK2315
CK2321
CK2328
CK2329
CK2330
CK2335
CK2336
CK2338
CK2339
CK2343
CK2345
CK2346
CK2348
CK2349
CK2351
CK2353
CK2354
CK2357
CK2358
CK2363
CK2369
CK2371
CK2372
CK2373
CK2380
CK2386
CK2387
CK2406
CK2419
CK2420
CK2440

## Sheet2
No | Type | Project | Length | Road name | km | Crossing name
CK-2005 | MC | 8074-01 | 2.8 | ANDERSON RIVER | 2.7 | Gilt Creek
CK-2007 | T | 8074-07 | 27.4 | ANDERSON SEVEN | 0.1 | Anderson River
CK-2009 | T | 5913-01 | 3.5 | BLUE MNT ONE | 6 | Not known
CK-2013 | T | 5913-05 | 999 | BLUE MTN FIVE | 1.5 | Not known
CK-2014 | T | 8124-01 | 12.3 | CANTELON CREEK | 8.2 | Cantelon Creek | BCTS
CK-2015 | T | 8124-01 | 8 | CANTELON CREEK | 9 | Not known | BCTS
CK-2016 | P | 8124-01 | 9 | CANTELON CREEK | 9.1 | Not known | BCTS
CK-2017 | T | 8124-03 | 11 | CANTELON NORTH | 0.7 | Cantelon Creek (north fork) | BCTS
CK-2019 | P | 8110-01 | 27.5 | CAYOOSE CREEK | 0.1 | Skagit River
CK-2022 | T | 8241-01 | 37 | CHEHALIS | 15.2 | Statlu Creek
CK-2027 | T | 8241-01 | 27.6 | CHEHALIS | 31.7 | Skwellepil Creek
CK-2028 | T | 8241-01 | 12.8 | CHEHALIS | 39.81 | West Eagle Creek
CK-2029 | T | 8241-01 | 99 | CHEHALIS | 39.9 | Statlu Lake Creek
CK-2034 | T | 8241-02 | 9999 | CHEHALIS-STATLU | 9.7 | Not Known
CK-2036 | T | 8241-03 | 1989 | CHEHALIS-SOUTHSTATLU |  | Statlu Creek
CK-2039 | T | 8241-03 | 9999 | CHEHALIS-SOUTHSTATLU | 9.5 | Dickson Creek
CK-2047 | P | 8241-11 | 19.9 | CHEHALIS-MYSTERY | 11.9 | Mystery Creek
CK-2048 | MC | 5127-01 | 14.5 | CHILLIWACK RIVER | 1 | Side Creek | BCTS
CK-2049 | MC | 5127-01 | 14.7 | CHILLIWACK RIVER | 1.5 | Side Creek | BCTS
CK-2054 | T | 5127-02 | 12.2 | LIUMCHEN CREEK | 0.9 | Little Tamihi Creek
CK-2055 | T | 5127-02 | 12.2 | LIUMCHEN CREEK | 2.5 | Deer Creek
CK-2056 | T | 5127-03 | 17.9 | LIUMCHEN WEST | 8.5 | Liumchen Creek
CK-2057 | T | 5127-03 | 12.2 | LIUMCHEN WEST | 9 | Slug Creek
CK-2058 | T | 5127-03 | 16.8 | LIUMCHEN WEST | 9.5 | East Liumchen Creek
CK-2059 | P | 5127-03 | 24.3 | LIUMCHEN WEST | 12.8 | Liumchen Creek
CK-2060 | T | 5127-03 | 999.9 | LIUMCHEN WEST | 13.1 | Not Known
CK-2061 | P | 5127-04 | 26 | LITTLE TAMIHI WEST | 0.7 | Liumchen Creek
CK-2062 | T | 5127-04 | 7.8 | LITTLE TAMIHI WEST | 13 | Not Known
CK-2064 | P | 5127-06 | 26.8 | CHILLIWACK-TAMIHI CR | 6.3 | Tamihi Creek
CK-2065 | T | 5127-06 | 15.4 | CHILLIWACK-TAMIHI CR | 8.3 | Fumerol Creek
CK-2066 | T | 5127-06 | 7.6 | CHILLIWACK-TAMIHI CR | 10.3 | Stapley Creek
CK-2068 | P | 5127-07 | 33.5 | SLESSE CREEK | 6.1 | Slesse Creek
CK-2069 | T | 5127-08 | 11.5 | SLESSE-BORDEN | 0.7 | Side Creek
CK-2073 | P | 5127-12 | 999 | CHIPMUNK CREEK | 1.5 | Chipmunk Creek
CK-2074 | T | 5127-12 | 16.2 | CHIPMUNK CREEK | 8.3 | Chipmunk Creek
CK-2075 | P | 5127-13 | 24 | FOLEY CREEK | 2.1 | Foley Creek
CK-2076 | T | 5127-13 | 23.8 | FOLEY CREEK | 4.4 | Foley Creek | BCTS
CK-2077 | P | 5127-14 | 22 | AIRPLANE CREEK | 0.1 | Foley Creek
CK-2084 | P | 5127-26 | 14.6 | CHILLIWACK SOUTH | 0 | Back channel | BCTS
CK-2085 | P | 5127-26 | 34.4 | CHILLIWACK SOUTH | 0.1 | Chilliwack River | BCTS
CK-2086 |  | 5127.26 |  | Chwk-South | 4.2 |  | BCTS
CK-2102 |  | 8648.02 |  | Florence-Rocky | 0.925 |  | BCTS
CK-2103 | T | 5913-05 |  | BLUE MTN FIVE | 1.5 | Not Known
CK-2106 | P | 5748-01 | 20 | HARRISON EAST | 15.4 | Bear Creek
CK-2108 | T | 5748-01 | 9 | HARRISON EAST | 30.7 | Not Known
CK-2116 | T | 5748-01 | 16 | HARRISON EAST | 64.4 | Big Silver Creek
CK-2118 | P | 5748-02 | 21.3 | COGBURN CREEK | 8 | Hut Creek
CK-2119 | P | 5748-02 | 16 | COGBURN CREEK | 4.8 | North Cogburn Creek
CK-2120 | T | 5748-03 | 7 | BEAR CREEK | 7 | Not Known
CK-2123 | T | 5748-06 | 11.3 | SHOVEL CREEK | 7.6 | Pick Creek
CK-2126 | T | 5748-07 | 12.1 | LOOKOUT PEAK | 0.1 | Bear Creek
CK-2140 | T | 6314-01 | 18.9 | HARRISON WEST | 46.5 | Davidson Creek
CK-2144 | P | 6314-01 | 999 | HARRISON WEST | 56.3 | Bremner Creek
CK-2146 | P | 6314-01 | 21.9 | HARRISON WEST | 64.4 | Coon Creek
CK-2147 | P | 6314-01 | 30.5 | HARRISON WEST | 66.9 | Tretheway Creek
CK-2148 | T | 6314-07 | 9.7 | SIMMS CREEK | 8.6 | Simms Creek
CK-2149 | T | 6314-08 | 15 | WALIAN CREEK | 7.2 | Walian Creek
CK-2159 | T | 6086-01 | 9 | LORENZETTA HUNTER | 9.8 | Hunter Creek | BCTS
CK-2160 | T | 6086-01 | 5 | LORENZETTA HUNTER | 12 | Lorenzetta Creek | BCTS
CK-2161 | P | 6086-02 | 12.2 | HUNTER EAST | 1.3 | Side Creek | BCTS
CK-2162 | MC | 8466-01 | 13 | LOST CREEK | 0.8 | Not Known
CK-2163 | MC | 8466-01 | 13 | LOST CREEK | 1.1 | Not Known
CK-2164 | MC | 8466-01 | 1600 | LOST CREEK | 1.4 | Not Known
CK-2165 | P | 8466-01 | 30.5 | LOST CREEK | 2.2 | Murdo Creek
CK-2166 | P | 8466-01 | 16 | LOST CREEK | 5 | Weatherhead Creek
CK-2167 | T | 8466-01 | 24.4 | LOST CREEK | 8.4 | Lost Creek | BCTS
CK-2168 |  | 8466.01 |  | Lost Creek | 8.3 |  | BCTS
CK-2169 |  | 8466.01 |  | Lost Creek | 14.14 |  | BCTS
CK-2170 |  | 8466.01 |  | Lost Creek | 16.6 |  | BCTS
CK-2171 |  | 8466.01 |  | Lost Creek | 17.305 |  | BCTS
CK-2172 | T | 8466-01 | 5.8 | LOST CREEK | 18.8 | Kenyon Creek | BCTS
CK-2174 | P | 8466-02 | 10.6 | LOST-MURDO | 0.7 | Side Creek | BCTS
CK-2175 | P | 8466-02 | 10.2 | LOST-MURDO | 1.2 | Not Known | BCTS
CK-2177 | T | 8466-04 | 7.6 | LOST-SOUTH | 4.9 | Side Creek
CK-2178 | T | 8466-06 | 12.5 | TEREPOCKI | 2.4 | Salsbury Creek | BCTS
CK-2179 | T | 8466-06 | 12 | TEREPOCKI | 5.2 | Salsbury Creek | BCTS
CK-2180 | T | 8466-06 | 3.6 | TEREPOCKI | 5.5 | Not Known
CK-2183 | T | 8466-07 | 10 | LOST-NORTH | 3.1 | side creek
CK-2186 | T | 8466-10 | 16.3 | MOUNT KETTLEY | 0.2 | Not Known | BCTS
CK-2188 |  | 8466.11 |  | Lost Blacklock CK | 0.45 |  | BCTS
CK-2189 |  | 8466.11 |  | Lost Blacklock CK | 1.98 |  | BCTS | h
CK-2190 |  | 8466.11 |  | Lost Blacklock CK | 2.15 |  | BCTS | h
CK-2191 |  | 8466.11 |  | Lost Blacklock CK | 2.47 |  | BCTS | h
CK-2196 | P | 6996-01 | 999 | NAHATLATCH | 0.8 | Nahatlatch River
CK-2200 |  | 6996.02 |  | Nehatlatch-Kookipi | 0.08 |  | BCTS
CK-2201 |  | 6996.02 |  | Nehatlatch-Kookipi | 3.18 |  | BCTS
CK-2202 |  | 6996.02 |  | Nehatlatch-Kookipi | 15.86 |  | BCTS | h
CK-2203 | T | 6996-03 | 4 | KOOKIPI THREE | 2.4 | Not Known | BCTS
CK-2204 | T | 8019-01 | 7.2 | NORTH AINSLIE CREEK | 10.8 | Goulah Creek
CK-2214 |  | 8126.01 |  | Peers Ck | 0.263 |  | BCTS
CK-2217 | T | 8394-01 | 12.2 | PITT RIVER | 2.2 | Side Creek
CK-2218 | P | 8394-01 | 999 | PITT RIVER | 8 | Fish Hatchery Creek
CK-2219 | P | 8394-01 | 999 | PITT RIVER | 9.8 | Corbold Creek
CK-2222 | T | 8394-01 | 12.5 | PITT RIVER | 18.2 | Side Creek
CK-2223 | T | 8394-01 | 3 | PITT RIVER | 20.2 | Side Creek
CK-2224 | P | 8394-01 | 23.8 | PITT RIVER | 23 | Shale Creek
CK-2225 | T | 8394-01 | 14.4 | PITT RIVER | 24.6 | Blue Creek
CK-2226 | P | 8394-02 | 999 | PITT-BOISE | 0.3 | Pitt River
CK-2227 | T | 8394-02 | 9.4 | PITT-BOISE | 2 | Side Creek
CK-2228 | T | 8394-02 | 10.5 | PITT-BOISE | 3.2 | Side Creek
CK-2229 | T | 8394-02 | 6 | PITT-BOISE | 4.7 | Side Creek
CK-2230 | P | 8394-02 | 40.3 | PITT-BOISE | 7.6 | Boise Creek
CK-2233 | P | 8394-04 | 999 | PITT-STEVE | 0.7 | Steve Creek
CK-2234 | P | 8125-01 | 17.2 | RUBY CREEK | 17 | West Fork Ruby Creek
CK-2234 |  | 8125.03 |  | Ruby Ck | 13.52 |  | BCTS
CK-2235 | T | 8127-01 | 24.5 | SCUZZY CREEK | 6.6 | Scuzzy Creek
CK-2240 |  | 8128.01 |  | Spuzzum Ck | 5.025 |  | BCTS
CK-2241 | P | 8128-01 | 18.8 | SPUZZUM CREEK | 25.4 | not known | BCTS | h
CK-2243 | T | 8128-02 | 13.5 | SPUZZUM-URQUHART | 6.6 | not known
CK-2244 | T | 8128-02 | 8.5 | SPUZZUM-URQUHART | 11.5 | Urquhart Creek
CK-2247 | T | 8128-06 | 18 | SPUZZUM SIX | 0.4 | South Fork Urquhart Creek
CK-2248 |  | 8128.07 |  | Spuzzum Ck | 0.2 |  | BCTS
CK-2249 | T | 8128-07 | 11 | SPUZZUM SEVEN | 5.4 | Side Creek | BCTS | h
CK-2250 | T | 8128-07 | 11.3 | SPUZZUM SEVEN | 5.9 | Side Creek | BCTS | h
CK-2252 | T | 8128-10 | 11.5 | SPUZZUM TEN | 4 | Southwest Fork
CK-2253 | T | 6092-01 | 999 | SQUEAH | 3.2 | not known
CK-2254 | T | 6092-01 | 10 | SQUEAH | 6.6 | not known
CK-2255 | T | 6092-01 | 999 | SQUEAH | 8.6 | not known
CK-2256 | T | 6092-01 | 999 | SQUEAH | 11.8 | Kieikum Creek
CK-2260 | P | 8013-01 | 21.4 | STAVE RIVER | 4.1 | Roaring Creek
CK-2261 | P | 8013-01 | 999 | STAVE RIVER | 8.5 | Winslow Creek
CK-2264 | T | 8013-01 | 13 | STAVE RIVER | 13 | Side Creek
CK-2271 | P | 8013-01 | 24 | STAVE RIVER | 26.2 | Stave River
CK-2272 | MC | 8013-01 | 15 | STAVE RIVER | 26.7 | Side Creek
CK-2273 | MC | 8013-01 | 18 | STAVE RIVER | 30.9 | not known
CK-2274 | T | 8013-01 | 6 | STAVE RIVER | 31.6 | Side Creek
CK-2275 | MC | 8013-01 | 16 | STAVE RIVER | 32.8 | Side Creek | BCTS | h
CK-2277 | P | 8013-02 | 8.6 | WINSLOW CREEK | 0.9 | Beaver Dam Creek | BCTS | h
CK-2282 | T | 7510-06 | 999 | SUMALLO SIX | 0.2 | Side Creek
CK-2286 | P | 7978-01 | 999 | TSILEUH CREEK | 17.7 | South Fork Tsileuh Creek
CK-2287 | T | 8148-01 | 20 | SILVERHOPE | 0.6 | Silverhope Creek (structure # 13)
CK-2288 | T | 7972-01 | 6 | UZTLIUS CREEK | 6.4 | not known
CK-2289 | P | 7972-01 | 999 | UZTLIUS CREEK | 8.7 | not known
CK-2290 | P | 7972-01 | 999 | UZTLIUS CREEK | 16.7 | not known
CK-2291 | P | 7972-01 | 999 | UZTLIUS CREEK | 17.7 | not known
CK-2292 | P | 7972-01 | 24.4 | UZTLIUS CREEK | 18.5 | Utzlius Creek
CK-2293 | P | 7972-01 | 21.3 | UZTLIUS CREEK | 19 | Uztlius Creek
CK-2294 | P | 7972-01 | 23.6 | UZTLIUS CREEK | 20.5 | Uztlius Creek
CK-2295 | P | 7972-01 | 26.3 | UZTLIUS CREEK | 21.9 | Uztlius Creek
CK-2297 | T | 7972-01 | 5.5 | UZTLIUS CREEK | 25.9 | not known
CK-2298 | P | 7972-01 | 999 | UZTLIUS CREEK | 27.5 | Uztlius Creek
CK-2299 | P | 7972-01 | 23.6 | UZTLIUS CREEK | 28.1 | Uztlius Creek
CK-2300 | P | 7972-01 | 999 | UZTLIUS CREEK | 30.8 | not known
CK-2301 | P | 7972-01 | 999 | UZTLIUS CREEK | 32.7 | not known
CK-2302 | T | 7972-01 | 5.7 | UZTLIUS CREEK | 35.4 | not known
CK-2304 | T | 7972-01 | 17.7 | UZTLIUS CREEK | 6.6 | East Anderson Creek
CK-2305 | P | 7972-02 | 999 | UZTLIUS-E ANDERSON | 11.7 | East Anderson Creek
CK-2306 | T | 7972-01 | 8 | UZTLIUS CREEK | 12.6 | not known
CK-2307 | P | 7972-02 | 999 | UZTLIUS-E ANDERSON | 12.8 | East Anderson Creek
CK-2315 |  | 8013.02 |  | Stave-Winslow | 4.178 |  | BCTS | h
CK-2319 | T | 7558-01 | 14.4 | GARNET CREEK | 10.1 | Side Creek
CK-2321 | T | 5913-02 | 8 | BLUE MTN TWO | 2.2 | Martyn Creek 2
CK-2323 | T | 6314-01 | 3.2 | HARRISON WEST | 61 | Not Known
CK-2327 | T | 8013-01 | 6 | STAVE RIVER | 0 | Side Creek
CK-2328 | T | 8149-01 | 24.4 | JONES LAKE | 12.7 | Flat Creek
CK-2330 |  | 8466.11 |  | Lost Blacklock CK | 1.37 |  | BCTS | h
CK-2331 | T | 8013-01 | 999 | STAVE RIVER | 5.1 | Camp Creek
CK-2332 | MC | 8013-01 | 18 | STAVE RIVER | 1.4 | Side Creek
CK-2333 | MC | 8013-01 | 14 | STAVE RIVER | 3 | Side Creek
CK-2334 | MC | 8013-01 | 18 | STAVE RIVER | 4.4 | Side Creek
CK-2335 | MC | 8013-01 | 12 | STAVE RIVER | 7.2 | Side Creek
CK-2336 | MC | 8013-01 | 12 | STAVE RIVER | 7.2 | Side Creek
CK-2338 | MC | 8013-01 | 15 | STAVE RIVER | 12.2 | not known
CK-2339 | MC | 8013-01 | 14 | STAVE RIVER | 13.6 | Side Creek
CK-2343 | MC | 8013-01 | 12 | STAVE RIVER | 28.1 | Side Creek
CK-2345 | P | 8013-02 | 21.4 | WINSLOW CREEK | 2.4 | Bradley Creek | BCTS | h
CK-2346 | T | 8394-02 | 10.9 | PITT-BOISE | 0.9 | not known
CK-2348 | P | 5748-02 | 24.4 | COGBURN CREEK | 4.8 | (No Creek Present)
CK-2349 | MC | 8013-01 | 12 | STAVE RIVER | 5.2 | Side Creek
CK-2350 | MC | 8013-01 | 14 | STAVE RIVER | 6.7 | Side Creek
CK-2351 | P | 7972-05 | 15 | UZTLIUS-STOYOMA EAST | 3.5 | Stoyoma Creek | BCTS
CK-2353 |  | 8013.02 |  | Stave-Winslow | 1.84 |  | BCTS | h
CK-2354 | P | 5748-01 | 11 | HARRISON EAST | 16.8 | Side Creek
CK-2357 | T | 8124-10 | 21.9 | CANTELON TEN | 0.1 | Cantelon Creek | BCTS
CK-2358 | MC | 8466-01 | 18 | LOST CREEK | 3.1 | not known
CK-2363 |  | 8128.01 |  | Spuzzum Ck | 24.65 |  | BCTS | h
CK-2365 | MC | 8466-01 | 999 | LOST CREEK | 1.1 | Side Creek
CK-2369 |  | 8128.21 |  | Spuzzum Ck | 2.304 |  | BCTS
CK-2370 |  | 8240.01 |  | Karen Ck | 1.882 |  | BCTS
CK-2371 | P | 8240-01 | 18.3 | KAREN CREEK | 2.26 | Not Known | BCTS
CK-2371 |  | 8240.01 |  | Karen Ck | 2.261 |  | BCTS
CK-2373 | MC | 6314-07 | 11 | SIMMS CREEK | 3.79 | Side Creek
CK-2378 | P | 8013-01 | 30.5 | STAVE RIVER | 8.8 | Winslow Side Channel
CK-2379 | P | 8241-01 |  | CHEHALIS | 0 | Chehalis River
CK-2380 | P | 8241-08 |  | CHEHALIS-FLEETWOOD | 12 | Upper Maisal Creek
CK-2382 | MC | 8241-02 | 1.2 | CHEHALIS-STATLU | 24.6 | Side Creek
CK-2386 | T | 5127-17 | 11.5 | CENTRE CREEK | 5.1 | Centre Creek | BCTS
CK-2387 | P | 5127-01 | 999 | CHILLIWACK RIVER | 6.7 | Paleface Creek Side Channel | BCTS
CK-2394 | T | 5748-02 | 999 | COGBURN CREEK | 0.2 | Big Silver Creek
CK-2395 | P | 5748-01 |  | HARRISON EAST | 0.3 | Big Silver River
CK-2400 | T | 5127-16 | 11.7 | NESAKWATCH CREEK | 1.07 | not known | BCTS
CK-2401 | P | 5127-24 | 6.4 | NESAKWATCH LAKE | 1.64 | not known | BCTS
CK-2406 | T | 8394-01 | 12.3 | PITT RIVER | 18.5 | not known
CK-2416 | P | 6092-01 | 6 | SQUEAH | 13 | Kleikum Creek
CK-2419 | T | 8013-01 | 3.7 | STAVE RIVER | 17 | Side Creek
CK-2420 | T | 8013-01 | 999 | STAVE RIVER | 17.5 | not known
CK-2423 | T | 8013 | 2.1 | STAVE LAKE | 29.5
CK-2440 | P | 8013-01 |  | STAVE RIVER | 31.8 | Side Creek
CK-2441 | T | 10452-01 | 16 | DEWDNEY WEST | 1.5 | Fifteen Mile Creek
CK-2467 | T | 8148-01 | 16.2 | SILVERHOPE | 8.4 | Unknown