## 2011 Inspection List
Site # | Road Name | Project File ID# / Br. | KM | Crossing Name | Owner | Design Load Rating | Load Rating from 2011 Inspection | Comments
CK-2002 | AMERICAN CREEK | 8123-01 | 4.6 | Three Mile Creek | BCTS | 54 tonnes | 54 tonnes | Replace guardrails, risers and sideblocks. Post bridge ahead signs. Replace missing delineator, clean bridge deck and consider brushing approaches. Due to canyon, consider blocking access to public until guardrails replaced.
CK-2003 | AMERICAN CREEK | 8123-01 | 8.5 | American Creek | OPS | unknown | 5 tonnes | Replace or deactivate.
CK-2008 | ANDERSON SEVEN | 8074-07 | 0.1 | Anderson River | OPS | unknown | 2 tonnes | The structure is classified as a WBC, inspect with regular road inspections.
CK-2010 | BLUE MTN TWO | 5913-02 | 2 | Martyn Creek East Fork | OPS | NA | NA | An old log bridge that has been replaced with a ford, inspect with regular road inspections.
CK-2011 | BLUE MTN TWO | 5913-02 | 0.1 | Copper Creek | OPS | 54 tonnes | 54 tonnes | Post bridge ahead signs. Place fenders or concrete no post barriers on approaches.
CK-2012 | BLUE MTN TWO | 5913-02 | 0.8 | McFadden Creek | OPS | 68 tonnes | 68 tonnes | Post bridge ahead signs.
CK-2013 | BLUE MTN FIVE | 5913-05 | 1.5 | Not known | OPS | unknown | unknown | NOT INSPECTED - District to advise if an inspection is required in 2012.
CK-2014 | CANTELON CREEK | 8124-01 | 9 | Not Known | BCTS | 54 tonnes | 0 tonnes | Replace or deactivate.
CK-2018 | CANTELON CREEK | 8124-01 | 0.3 | Cantelon Creek | BCTS | 68 tonnes | 68 tonnes | Replace guardrail, risers and sideblocks. Post bridge ahead signs. Replace missing delineators and patch left approach ballast wall.
CK-2020 | CHEHALIS | 8241-01 | 6.1 | Pretty Creek | OPS | 150 tonnes | 150 tonnes | Check grouted joints next inspection.
CK-2021 | CHEHALIS | 8241-01 | 10.6 | Boulder Creek | OPS | 136 tonnes | 136 tonnes | Monitor left abutment.
CK-2022 | CHEHALIS | 8241-01 | 15.2 | Statlu Creek | OPS | 91 tonnes | 91 tonnes
CK-2023 | CHEHALIS | 8241-01 | 21.8 | Upper Bentley Creek | OPS | 136 tonnes | 136 tonnes | Need to verify age of guardrail, risers and sideblocks or reinspect. If old or suspect then replace.
CK-2024 | CHEHALIS | 8241-01 | 23.8 | Dick Creek | OPS | 136 tonnes | 136 tonnes | Monitor bearing pads.
CK-2025 | CHEHALIS | 8241-01 | 26.4 | Second Creek | OPS | 136 tonnes | 136 tonnes | Monitor bearing pads.
CK-2026 | CHEHALIS | 8241-01 | 27.4 | Third Creek | OPS | 136 tonnes | 136 tonnes | Replace missing delineator.
CK-2031 | CHEHALIS-STATLU | 8241-02 | 1.8 | Statlu Creek | OPS | 136 tonnes | 136 tonnes | Previuos inspection noted poor ballast wall and there is info on the file saying work has been completed to it. Need to verify.
CK-2032 | CHEHALIS-STATLU | 8241-02 | 4.9 | Statlu Creek | OPS | 136 tonnes | 136 tonnes | Post bridge ahead signs. Place fenders or concrete no post barriers on approaches.
CK-2033 | CHEHALIS-STATLU | 8241-02 | 6 | Alice Creek | OPS | 136 tonnes | 136 tonnes
CK-2035 | CHEHALIS-SOUTHSTATLU | 8241-03 | 0.1 | Statlu River | OPS | 136 tonnes | 136 tonnes | Replace guardrail, risers and blocks. Replace missing delineators and fenders/concrete no post barriers.
CK-2037 | CHEHALIS-SOUTHSTATLU | 8241-03 | 3.7 | Towhead Creek | OPS | 136 tonnes | unknown | NOT INSPECTED - SNOW - inspect in 2012
CK-2038 | CHEHALIS-SOUTHSTATLU | 8241-03 | 5.9 | South Statlu Creek | OPS | unknown | unknown | NOT INSPECTED - SNOW - inspect in 2012
CK-2040 | CHEHALIS-FLEETWOOD | 8241-08 | 3.1 | Lower Bentley Creek | OPS | 136 tonnes | 136 tonnes | Replace missing delineators. Post bridge ahead signs.
CK-2041 | CHEHALIS | 8241-01 | 3.7 | Chehalis River | OPS | 136 tonnes | 136 tonnes | Clean bridge deck.
CK-2042 | CHEHALIS-FLEETWOOD | 8241-08 | 4.3 | Maisal Creek | OPS | 136 tonnes | 136 tonnes | Replace missing delineator. Post bridge ahead signs.
CK-2045 | CHEHALIS-MYSTERY | 8241-11 | 6.9 | Mystery creek | OPS | 68 tonnes | 68 tonnes | Post bridge ahead signs.
CK-2046 | CHEHALIS-MYSTERY | 8241-11 | 10.3 | Mystery creek | OPS | 68 tonnes | 68 tonnes
CK-2047 | CHEHALIS-MYSTERY | 8241-11 | 11.9 | Mystery Creek | OPS | 54 tonnes | 54 tonnes | Replace delineators. Post bridge ahead signs.
CK-2048 | CHILLIWACK RIVER | 5127-01 | 1 | Side Creek | BCTS | 54 tonnes | 54 tonnes | Provide cover, corrugation profile and steel thickness at next inspection.
CK-2050 | CHILLIWACK RIVER | 5127-01 | 8 | Paleface Creek | BCTS | 68 tonnes | 68 tonnes | Post bridge ahead signs and missing delineators.
CK-2051 | CHILLIWACK RIVER | 5127-01 | 8.1 | Paleface Creek | BCTS | 68 tonnes | 68 tonnes | Post bridge ahead signs.
CK-2052 | CHILLIWACK RIVER | 5127-01 | 11.1 | Depot Creek | BCTS | 41 tonnes | 5 tonnes | Replace ties, subdeck, running planks, guardrail, and risers. Wingwalls are completely rotten and need to be replaced prior to industrial activity. Place no post or log fenders prior to industrial activity. Post bridge ahead and load rating signs.
CK-2066 | CHILLIWACK-TAMIHI CR | 5127-06 | 10.3 | Stapley Creek | OPS | unknown | 63 tonnes | The structure is undersized and is diverting water down the road; remove or replace ASAP.
CK-2067 | CHILLIWACK-TAMIHI CR | 5127-06 | 10.6 | Tamihi Creek | OPS | 68 tonnes | 68 tonnes | Post bridge ahead signs.
CK-2078 | CENTRE CREEK | 5127-17 | 2.3 | Centre Creek | BCTS | 68 tonnes | unknown | NOT INSPECTED - NEED KEY FOR ACCESS - inspect in 2012
CK-2087 | DEWDNEY CREEK | 7995-01 | 4.9 | Cedar Flat Creek | OPS | 54 tonnes | 54 tonnes | Post bridge ahead signs.
CK-2091 | FLORENCE LAKE | 8648-01 | 2.8 | Rolley Creek | OPS | 68 tonnes | 68 tonnes | Replace guardrail, risers and blocks. Grade approcahes
CK-2092 | FLORENCE LAKE | 8648-01 | 4.2 | Rockwell Creek | OPS | 68 tonnes | 68 tonnes | Grade approaches.
CK-2093 | FLORENCE LAKE | 8648-01 | 7 | 79 Creek | OPS | 54 tonnes | 54 tonnes | Grade approaches.
CK-2094 | FLORENCE LAKE | 8648-01 | 7.8 | not known | OPS | 54 tonnes | 54 tonnes | Grade/place material on approaches and deck.
CK-2095 | FLORENCE LAKE | 8648-01 | 9.4 | Kearsley Creek | OPS | 54 tonnes | 54 tonnes
CK-2096 | FLORENCE LAKE | 8648-01 | 13.11 | Not Known | OPS | 68 tonnes | 68 tonnes | Replace guardrail, risers and blocks. Grade approaches.
CK-2097 | FLORENCE LAKE | 8648-01 | 13.6 | Not Known | OPS | 68 tonnes | 68 tonnes | Grade approaches.
CK-2098 | FLORENCE LAKE | 8648-01 | 13.9 | Sayers Creek | OPS | 68 tonnes | 68 tonnes | Grade approaches.
CK-2099 | FLORENCE LAKE | 8648-01 | 14.1 | Con Creek | OPS | 68 tonnes | 68 tonnes | Patch D/S ballast wall to cover exposed rebar. Grade approaches
CK-2103 | GARNET CREEK | 7558-01 | 8.8 | East Fork Garnet Creek | OPS | 68 tonnes | 68 tonnes | Post bridge ahead signs.
CK-2107 | HARRISON EAST | 5748-01 | 24.8 | Cogburn Creek | OPS | 136 tonnes | 136 tonnes
CK-2109 | HARRISON EAST | 5748-01 | 35.3 | Hornet Creek | OPS | 136 tonnes | 136 tonnes | Cribs are nearing the end of their inustrial life and will require replacement soon.
CK-2110 | HARRISON EAST | 5748-01 | 40.5 | Clear Creek | OPS | 136 tonnes | 68 tonnes | Cribs are nearing the end of their inustrial life and will require replacement soon.
CK-2111 | HARRISON EAST | 5748-01 | 48.9 | Big Silver River | OPS | 109 tonnes | 109 tonnes | No signed drawings on file but discussion with Associated Engineering regarding L120 design. Design was completed while construction was taking place. A close proximity inspection has been scheduled for 2012.
CK-2112 | HARRISON EAST | 5748-01 | 51.7 | Not Known | OPS | 136 tonnes | 136 tonnes
CK-2114 | HARRISON EAST | 5748-01 | 56.5 | Gold Creek | OPS | 136 tonnes | 136 tonnes | Monitor hairline cracks in girders.
CK-2121 | BEAR CREEK | 5748-03 | 7.4 | Bear Creek | OPS | unknown | unknown | NOT INSPECTED - Inspect in 2012.
CK-2122 | SHOVEL CREEK | 5748-06 | 0.1 | Big Silver Creek | OPS | 136 tonnes | 136 tonnes | Post bridge ahead signs.
CK-2123 | SHOVEL CREEK | 5748-06 | 7.6 | Pick Creek | OPS | 63 tonnes | 63 tonnes | NOT INSPECTED - BRIDGE REPLACED THIS YEAR
CK-2124 | SHOVEL CREEK | 5748-06 | 2.9 | Spade Creek | OPS | 63 tonnes | 63 tonnes | NOT INSPECTED - BRIDGE REPLACED THIS YEAR
CK-2126 | LOOKOUT PEAK | 5748-07 | 0.1 | Bear Creek | OPS | unknown | unknown | NOT INSPECTED - Inspect in 2012.
CK-2128 | HARRISON WEST | 6314-01 | 5.9 | Not Known | OPS | 68 tonnes | 68 tonnes | Inspect shear connectors and deck.
CK-2129 | HARRISON WEST | 6314-01 | 12.5 | Cartmell Creek | OPS | 54 tonnes | 54 tonnes
CK-2132 | HARRISON WEST | 6314-01 | 17.4 | Simms Creek | OPS | 68 tonnes | 68 tonnes
CK-2134 | HARRISON WEST | 6314-01 | 23.5 | Hale Creek | OPS | 54 tonnes | 54 tonnes | UPDATE LOAD RATING SIGN - inspection notes it posted at 68 tonnes. Inspect grout pockets and deck joints.
CK-2138 | HARRISON WEST | 6314-01 | 34.5 | 20 Mile Creek | OPS | 54 tonnes | 54 tonnes | UPDATE LOAD RATING SIGN
CK-2139 | HARRISON WEST | 6314-01 | 42 | Kirkland Creek | OPS | 54 tonnes | 41 tonnes | REPLACE TIES, SUBDECK, WEAR PLANKS, GUARDRAIL AND RISERS. Place log fenders or concrete no post barriers and brush approaches. Ensure load rating sign is correct, design load rating is L60 or 54 tonnes.
CK-2140 | HARRISON WEST | 6314-01 | 46.5 | Davidson Creek | OPS | 54 tonnes | 54 tonnes | Install log fenders or concrete no post barriers. UPDATE LOAD RATING SIGN.
CK-2141 | HARRISON WEST | 6314-01 | 49.1 | Trio Creek | OPS | 136 tonnes | 136 tonnes
CK-2143 | HARRISON WEST | 6314-01 | 55.4 | Doctors Creek | OPS | 68 tonnes | 68 tonnes | Has wrong load rating signs posted, ost updated load rating signs and brush approaches.
CK-2149 | WALIAN CREEK | 6314-08 | 7.2 | Walian Creek | OPS | unknown | unknown | NOT INSPECTED - RECREATION REPLACED THIS STRUCTURE THIS SUMMER - NEED ASBUILT ON FILE. District to advise if 2012 inspection is warranted.
CK-2154 | JONES-WEST | 8149-03 | 0.6 | Wahleach Creek | OPS | 68 tonnes | 68 tonnes | Bridge identification indicates L75 rating, require asbuilt for confirmation.
CK-2157 | LORENZETTA HUNTER | 6086-01 | 2.2 | Hunter Creek | BCTS | 54 tonnes | 54 tonnes | Replace rotten planks, install fenders or concrete no post barriers, fill gaps between crib logs and tiebacks, install bridge ahead and load rating signs, brush approaches and remove gravel from running surface.
CK-2161 | HUNTER EAST | 6086-02 | 1.3 | Side Creek | BCTS | 150 tonnes | 27 tonnes | CK2158 was inspected and subsequently I inspected CK2161
CK-2172 | LOST CREEK | 8466-01 | 18.8 | Kenyon Creek | BCTS | 54 tonnes | unknown | Inspection indicates a deactivated structure and BCTS indicates they did not deactivate this structure - must have inspected wrong structure. Inspect in 2012 to figure out discrepency.
CK-2174 | LOST-MURDO | 8466-02 | 0.7 | Side Creek | BCTS | 54 tonnes | 5 tonnes | Consider complete replacment, monitor annually.
CK-2175 | LOST-MURDO | 8466-02 | 1.2 | Not Known | BCTS | 54 tonnes | 5 tonnes | Consider complete replacment, monitor annually.
CK-2176 | LOST-SOUTH | 8466-04 | 2 | Darlene Creek | BCTS | 68 tonnes | 5 tonnes | Consider complete replacment, monitor annually.
CK-2178 | TEREPOCKI | 8466-06 | 2.4 | Salsbury Creek | BCTS | 54 tonnes | 5 tonnes | Consider complete replacment, monitor annually.
CK-2199 | NAHATLATCH | 6996-01 | 30.3 | Tachewana Creek | OPS | 68 tonnes | 68 tonnes
CK-2205 | NORTH AINSLIE CREEK | 8019-01 | 17.4 | Side Creek | OPS | 136 tonnes | 136 tonnes | Monitor eroding outlet.
CK-2206 | NORTH AINSLIE CREEK | 8019-01 | 19.4 | Not Known | OPS | unknown | unknown | NOT INSPECTED - Inspect in 2012.
CK-2207 | MOWHOKAM | 8019-02 | 9.6 | Mowhokam Creek | OPS | 68 tonnes | 54 tonnes | Fasten ties to girders. Consider full replacement soon.
CK-2208 | MOWHOKAM | 8019-02 | 16.3 | Side Creek | OPS | 136 tonnes | 136 tonnes
CK-2210 | MOWHOKAM EAST | 8019-03 | 6.51 | Mowhokam Creek | OPS | 68 tonnes | 0 tonnes | Condemned, remove ASAP. Block access.
CK-2211 | NORTH EMORY CREEK | 8147-01 | 2.8 | Side Creek | OPS | 68 tonnes | 91 tonnes
CK-2213 | PEERS CREEK | 8126-01 | 0.2 | Coquihalla River | BCTS | unknown | TBD | Inspect with snooper truck in 2012, concernede with concrete cap on pier 2. post bridge ahead sign on woods approach.
CK-2232 | PITT-BUCKLIN | 8394-03 | 3 | Bucklin Creek | OPS | 91 tonnes | 0 tonnes | Condemned, remove ASAP. Block access.
CK-2235 | SCUZZY CREEK | 8127-01 | 6.6 | Scuzzy Creek | OPS | unknown | unknown | Structure looks to have had work completed on it last year with no information in the file. Provide asbuilt and information on steel for updated load rating.
CK-2236 | SOWAQUA CREEK | 7004-01 | 9.6 | Not Known | OPS | 68 tonnes | 2 tonnes | Woods crib is hanging, structure could be condemned by next year, remove or replace.
CK-2237 | SOWAQUA CREEK | 7004-01 | 14.6 | Montigny Creek | OPS | 68 tonnes | unknown | Require asbuilts to verify loading (bridge identification indicates L75 loading). The 2007 Inpsection photos show poor bearing (uneven) of the girders on the H-Pile and minor steel deformation.
CK-2248 | SPUZZUM SEVEN | 8128-07 | 0.2 | Spuzzum Creek | BCTS | 54 tonnes | 54 tonnes | Replace guardrail, risers, sideblocks and grading strips; post bridge ahead signs; replace fenders and missing delineators; and brush prior to use.
CK-2253 | SQUEAH | 6092-01 | 3.2 | not known | OPS | 68 tonnes | 5 tonnes | Replace entire structure soon.
CK-2254 | SQUEAH | 6092-01 | 6.1 | not known | OPS | 68 tonnes | 5 tonnes | Patch holes in deck and replace entire structure soon. Post load rating.
CK-2255 | SQUEAH | 6092-01 | 7.9 | not known | OPS | 68 tonnes | 5 tonnes | Post load rating and replace entire structure soon.
CK-2256 | SQUEAH | 6092-01 | 11.8 | Kieikum Creek | OPS | 68 tonnes | 2 tonnes | Post load rating and replace entire structure soon.
CK-2260 | STAVE RIVER | 8013-01 | 4.1 | Roaring Creek | OPS | 68 tonnes | 68 tonnes | Replace guardrail, risers and sideblocks. Post bridge ahead signs.
CK-2262 | STAVE RIVER | 8013-01 | 10.5 | Side Creek | OPS | 68 tonnes | 20 tonnes | Post bridge ahead and load rating signs. Remove beaver dam and inspect in low water. Plan to replace entire structure soon.
CK-2263 | STAVE RIVER | 8013-01 | 11.4 | Side Creek | OPS | 54 tonnes | 54 tonnes | Remove beaver dam and assess cribs and stringers in low water. Pull gravel surfacing, lay geotextile and replace surfacing - min depth of 600mm. Place curbs, and log fenders and post bridge ahead and load rating signs.
CK-2264 | STAVE RIVER | 8013-01 | 13 | Side Creek | OPS | 54 tonnes | 10 tonnes | Post updated load rating. Plan to replace entire structure.
CK-2265 | STAVE RIVER | 8013-01 | 13.2 | Side Creek | OPS | 80 tonnes | 41 tonnes | Remove gravel fill, lay geotextile over stringers and backfill to 600mm depth. Post bridge ahead and load rating signs.
CK-2266 | STAVE RIVER | 8013-01 | 16.8 | Side Creek | OPS | 68 tonnes | 27 tonnes | Post updated load rating.
CK-2267 | STAVE RIVER | 8013-01 | 19 | Ole Creek | OPS | 68 tonnes | 5 tonnes | Post updated load rating.
CK-2268 | STAVE RIVER | 8013-01 | 20 | Side Creek | OPS | 68 tonnes | 68 tonnes
CK-2269 | STAVE RIVER | 8013-01 | 21.6 | Stave River | OPS | 68 tonnes | 68 tonnes | Post bridge ahead signs. Monitor camp crib for settlement.
CK-2270 | STAVE RIVER | 8013-01 | 23.6 | Side Creek | OPS | unknown | 68 tonnes | Steel identification indicates L75 rating, send asbuilts for confirmation. Repair damaged guardrail and post bridge ahead signs.
CK-2272 | STAVE RIVER | 8013-01 | 26.7 | Side Creek | OPS | unknown | 68 tonnes
CK-2278 | SUMALLO RIVER | 7510-01 | 1.4 | Sumalo River | OPS | 68 tonnes | 68 tonnes | Post bridge ahead signs.
CK-2279 | SUMALLO RIVER | 7510-01 | 4.7 | Tearse Creek | BCTS | 54 tonnes | 54 tonnes | Place missing fenders/no posts. Post bridge ahead signs.
CK-2284 | TSILEUH CREEK | 7978-01 | 4.4 | Tikwalus Creek | OPS | 91 tonnes | 54 tonnes | Monitor crib scour. Replace missing fenders, post bridge ahead and load rating signs.
CK-2285 | TSILEUH CREEK | 7978-01 | 12.5 | Black Creek | OPS | 68 tonnes | 68 tonnes | Grade and ditch approaches and dig out sump. Replace missing delineator and post bridge ahead signs.
CK-2287 | SILVERHOPE | 8148-01 | 0.6 | Silverhope Creek | OPS | 68 tonnes | 68 tonnes | Replace missing delineator and post bridge ahead signs. Load rating subject to regrouting bearing plates at abutment supports.
CK-2296 | UZTLIUS CREEK | 7972-01 | 24.5 | Uztlius Creek | OPS | 68 tonnes | 68 tonnes | Send asbuilt.
CK-2304 | UZTLIUS CREEK | 7972-01 | 6.6 | East Anderson Creek | OPS | 41 tonnes | 0 tonnes | On side road and already barricaded. Remove soon.
CK-2307 | UZTLIUS CREEK | 7972-01 | 12.6 | not known | OPS | 68 tonnes | 68 tonnes | Replace guardrail, risers and sideblocks. Post bridge ahead signs.
CK-2308 | UZTLIUS-E ANDERSON | 7972-02 | 14.8 | not known | OPS | 68 tonnes | 5 tonnes | Steel superstructure overspaning log stringer bridge. Due to undermined crib and failing fill under newer sill suggest leaving load rating at 5 tonnes. Plan to remove and reinstall on new abutments.
CK-2309 | UZTLIUS-E ANDERSON | 7972-02 | 17.1 | not known | OPS | unknown | 68 tonnes | Clean inlet at first opportunity.
CK-2310 | UZTLIUS-E ANDERSON | 7972-02 | 18.5 | not known | OPS | unknown | 68 tonnes
CK-2315 | WRAY-BERKEY CREEK | 8113-02 | 4.2 | Berkey Creek | BCTS | unknown | 0 tonnes | Bridge condemned. Barricade and post or remove.
CK-2316 | FOLEY CREEK | 5127-13 | 12.8 | Foley Creek | BCTS | 54 tonnes | 54 tonnes | Replace guardrail, riser and sideblocks. Replace all 4 delineators and fenders. Post bridge ahead signs.
CK-2317 | FOLEY CREEK | 5127-13 | 11.9 | Foley Creek | BCTS | 68 tonnes | 68 tonnes | Post bridge ahead signs.
CK-2319 | GARNET CREEK | 7558-01 | 10.1 | Side Creek | OPS | 63 tonnes | 63 tonnes
CK-2320 | NAHATLATCH | 6996-01 | 19.1 | Not Known | OPS | 68 tonnes | 68 tonnes
CK-2321 | BLUE MTN TWO | 5913-02 | 2.2 | Martyn Creek 2 | OPS | NA | NA | An old log bridge that has been replaced with a ford, inspect with regular road inspections.
CK-2327 | STAVE RIVER | 8013-01 | 0 | Side Creek | OPS | 68 tonnes | 68 tonnes | Monitor right abutment scour.
CK-2331 | STAVE RIVER | 8013-01 | 5.1 | Camp Creek | OPS | unknown | 54 tonnes | Remove gravel fill, place geotextile and replace; ensure 600mm gravel depth. Place log fenders and curbs, brush approaches and post load rating.
CK-2332 | STAVE RIVER | 8013-01 | 1.4 | Side Creek | OPS | 68 tonnes | 68 tonnes | Clean outlet.
CK-2333 | STAVE RIVER | 8013-01 | 3 | Side Creek | OPS | 68 tonnes | 68 tonnes | Clean inlets.
CK-2334 | STAVE RIVER | 8013-01 | 4.4 | Side Creek | OPS | 68 tonnes | 68 tonnes
CK-2337 | STAVE RIVER | 8013-01 | 10.8 | not known | OPS | 68 tonnes | 68 tonnes | Clean inlets.
CK-2338 | STAVE RIVER | 8013-01 | 12.2 | not known | OPS | 68 tonnes | unknown | File indicates an Eliptical CSP at this location not WBC. Inspect in 2012 to figure out discrepency.
CK-2340 | STAVE RIVER | 8013-01 | 16.1 | not known | OPS | 68 tonnes | unknown | NOT INSPECTED - Inspect in 2012.
CK-2341 | STAVE RIVER | 8013-01 | 16.9 | Side Creek | OPS | 54 tonnes | 91 tonnes | This is a WBC, inspect with regular road inspections. Looks like structure has had work completed to it recently (ie span has shortened, additional gravel fill placed)
CK-2342 | STAVE RIVER | 8013-01 | 20.1 | side creek | OPS | 68 tonnes | 68 tonnes
CK-2346 | PITT-BOISE | 8394-02 | 0.9 | not known | OPS | 109 tonnes | 5 tonnes | Recommend bridge replacement.
CK-2355 | COGBURN CREEK | 5748-02 | 2 | Not Known | OPS | 136 tonnes | 136 tonnes
CK-2356 | KOOKIPI NINE | 6996-09 | 0.5 | Kookipi Creek | BCTS | 136 tonnes | 136 tonnes | Replace missing fender and post bridge ahead signs.
CK-2359 | STAVE RIVER | 8013-01 | 12 | not known | OPS | 68 tonnes | 68 tonnes
CK-2360 | KOOKIPI SEVEN | 6996-07 | 4.2 | Not Known | BCTS | 68 tonnes | 68 tonnes | Post bridge ahead signs.
CK-2361 | KOOKIPI SEVEN | 6996-07 | 5.27 | Not known | BCTS | 68 tonnes | 68 tonnes | Replace missing delineator, post bridge ahead signs and fix right D/S barriers. Consider some cutbank stability for safety and protection of bridge.
CK-2362 | KOOKIPI SEVEN | 6996-07 | 6.5 | West Fork Kookipi Creek | BCTS | 68 tonnes | 68 tonnes | Post bridge ahead sings.
CK-2364 | CONNOR CREEK | 9745-01 | 0.05 | Conner Creek | BCTS | 68 tonnes | 68 tonnes
CK-2366 | STAVE RIVER | 8013-01 | 15.6 | not known | OPS | 68 tonnes | 68 tonnes
CK-2367 | STAVE RIVER | 8013-01 | 19.1 | not known | OPS | 68 tonnes | 68 tonnes
CK-2368 | KAREN CREEK | 8240-01 | 0.17 | Dewdney Creek | BCTS | 68 tonnes | 68 tonnes | Replace damaged sideblocks and consider replacing all guardrail, risers and sideblocks due to age. Replace missing delineator and post bridge ahead signs.
CK-2372 | SOWERBY CREEK | 8112-01 | 1.6 | Sowerby Creek | OPS | 68 tonnes | 68 tonnes | Post bridge ahead signs.
CK-2378 | STAVE RIVER | 8013-01 |  | Winslow Side Channel | OPS | 68 tonnes | 68 tonnes | Repair fill at right abutment and grout over exposed rebar on right ballast wall. Post bridge ahead signs.
CK-2379 | LOST_LEASE | 8466.03 | 0.5 | Side Creek | BCTS | unknown | unknown | site does not exist in CBR - NOT INSPECTED. District to advise.
CK-2394 = CK-2116 | HARRISON EAST | 5748-01 | 62 | Big Silver Creek | OPS | 136 tonnes | 0 tonnes | Post and barricade or replace.
CK-2395 | ENGLISH CREEK | 5748-20 | 0.3 | Big Silver River | OPS | 136 tonnes | 10 tonnes | Cast in place footings on pier have scoured out and need to ensure proper bearing before load rating can be returned to design loading. Completely seal (concrete) footings and riprap for protection. Limit loading to 10 tonnes until repir work can be completeld. Replace guardrail, risers and sideblocks; grout left ballast wall to completely cover exposed rebar; replace all 4 delineators; post bridge ahead and updated load rating signs. Send asbuilt info to RCO.
CK-2417 | STAVE RIVER | 8013-01 | 13.1 | not known | OPS | 68 tonnes | 68 tonnes | Repair/replace D/S guardrail and post bridge ahead signs.
CK-2422 | STAVE RIVER | 8013-01 | 25.2 | not known | OPS | unknown | TBD | These are not major culverts; however they seem undersized for the site. Please send hydrology and design to RCO for a review.
CK-2441 | DEWDNEY WEST | 10452-01 | 1.5 | Fifteen Mile Creek | BCTS | 68 tonnes | 68 tonnes | Post bridge ahead signs.
CK-2442 | AMERICAN EIGHT | 8123-08 | 0.15 | American Creek | BCTS | 68 tonnes | 68 tonnes | Post bridge ahead sign and replace missing delineator.
CK-2443 | NORRISH CREEK | 10326-01 | 11 | Hansen Creek | OPS | 91 tonnes | 91 tonnes
CK-2444 | NORRISH CREEK | 10326-01 | 12.9 | Cyr Creek | OPS | 91 tonnes | 91 tonnes
CK-2445 | NORRISH CREEK | 10326-01 | 16.1 | East Fork | OPS | 91 tonnes | 91 tonnes
CK-2447 | NORRISH CREEK | 10326-01 | 18 | Tom Creek | OPS | 150 tonnes | unknown | NOT INSPECTED - Inspect in 2012.
CK-2454 | NORRISH CREEK | 10326-01 | 8.4 | Unknown | OPS | 150 tonnes | 150 tonnes
CK-2455 | NORRISH CREEK | 10326-01 | 8.9 | Unknown | OPS | 150 tonnes | 150 tonnes
CK-2456 | NORRISH CREEK | 10326-01 | 9.2 | Unknown | OPS | 150 tonnes | 150 tonnes
CK-2463 | HARRISON EAST | 5748-01 | 64.2 | Hunger Creek | OPS | unknown | 27 tonnes | Replace delineators, post bridge ahead and load rating signs. Monitor crib scour on town approach.
CK-2466 | GARNET CREEK | 7558-01 | 8.2 | Unknown | OPS | 68 tonnes | 68 tonnes | Post bridge ahead signs.
CK-2471 | CHEHALIS-MAISAL | 8241-16 | 3.2 | Side Creek | OPS | 136 tonnes | 136 tonnes
CK-2472 | CHEHALIS-MAISAL | 8241-16 | 6 | Upper Maisal Creek | OPS | 136 tonnes | 0 tonnes | Replace ties, deck, guardrail, and risers. Place concrete no post barriers or log fenders and replace delineators prior to industrial activity
CK-2500 | STS'AILES | 6314.01 | 71.5 | Spring Crk | OPS | 113 Tonnes | 113 Tonnes
Note on A4: Tyson W. Miller: CK2007 was supposed to be inspected
Note on A9: Tyson W. Miller: CK2015 was supposed to be inspected
Note on A112: Tyson W. Miller: was supposed to have inspected CK2306