## 2012 Inspection Summary List
Site ID | Rd Name | FSR | Branch | Owner | CROSSING_NAME | Design Load Rating | 2012 Load Rating | Comments
CK-2007 | ANDERSON SEVEN | 8074 | 07 | Ops | Anderson River | 41 tonnes | 41 tonnes | U/S abutment req's riprap. Place log fenders, bridge ahead and load rating signs
CK-2015 | CANTELON CREEK | 8124 | 01 | BCTS | Not Known | 54 tonnes | 2 tonnes | Req's complete replacement
CK-2016 | CANTELON CREEK | 8124 | 01 | BCTS | Not known | 54 tonnes | 0 tonnes | Bridge condemned, remove or replace
CK-2019 | CAYOOSE CREEK | 8110 | 01 | Ops | Skagit River | 62 tonnes | 62 tonnes | Replace missing delineators, post bridge ahead and load rating signs
CK-2020 | CHEHALIS | 8241 | 01 | Ops | Pretty Creek | 150 tonnes | 150 tonnes
CK-2023 | CHEHALIS | 8241 | 01 | Ops | Upper Bentley Creek | 136 tonnes | 136 tonnes
CK-2024 | CHEHALIS | 8241 | 01 | Ops | Dick Creek | 136 tonnes | 136 tonnes | Replace guardrail, risers and blocks
CK-2027 | CHEHALIS | 8241 | 01 | Ops | Skwellepil Creek | 68 tonnes | 68 tonnes
CK-2031 | CHEHALIS-STATLU | 8241 | 02 | Ops | Statlu Creek | 136 tonnes | 136 tonnes | Place running planks to extend life of treated deck
CK-2032 | CHEHALIS-STATLU | 8241 | 02 | Ops | Statlu Creek | 136 tonnes | 136 tonnes | Replace guardrail, risers and blocks. Replace log fenders at right approach
CK-2035 | CHEHALIS-SOUTHSTATLU | 8241 | 03 | Ops | Statlu River | 136 tonnes | 136 tonnes | Replace missing delineator and log fenders
CK-2037 | CHEHALIS-SOUTHSTATLU | 8241 | 03 | Ops | Towhead Creek | 136 tonnes | 136 tonnes | Replace guardrail, risers and blocks. Post bridge ahead signs
CK-2038 | CHEHALIS-SOUTHSTATLU | 8241 | 03 | Ops | South Statlu Creek | 136 tonnes | 0 tonnes | Bridge condemned, block access
CK-2041 | CHEHALIS | 8241 | 01 | Ops | Chehalis River | 136 tonnes | 136 tonnes | Clean deck
CK-2044 | CHEHALIS-MYSTERY | 8241 | 11 | Ops | Chehalis River | 41 tonnes | 2 tonnes | Replace ties, deck, guardrail and risers. Post load rating and bridge ahead signs
CK-2047 | CHEHALIS-MYSTERY | 8241 | 11 | Ops | Mystery Creek | 54 tonnes | 54 tonnes | Replace all 4 delineators and post bridge ahead and laod rating signs
CK-2050 | CHILLIWACK RIVER | 5127 | 01 | BCTS | Paleface Creek | 68 tonnes | 68 tonnes | Replace missing delineators, post bridge ahead signs and brush with aactivity
CK-2051 | CHILLIWACK RIVER | 5127 | 01 | BCTS | Unknown | 68 tonnes | 68 tonnes | Post bridge ahead and load rating signs. Brush with activity
CK-2053 | LIUMCHEN CREEK | 5127 | 02 | Ops | Tamihi Creek | 64 tonnes | 64 tonnes | Post bridge ahead and load rating signs. Monitor delaminating steel girders
CK-2065 | CHILLIWACK-TAMIHI CR | 5127 | 06 | Ops | Fumerol Creek | 68 tonnes | 0 tonnes | Monitor for failure
CK-2066 | CHILLIWACK-TAMIHI CR | 5127 | 06 | Ops | Stapley Creek |  | TBD | Structure is undersized and diverting water down the road
CK-2068 | SLESSE CREEK | 5127 | 07 | Ops | Slesse Creek | 54 tonnes | 54 tonnes
CK-2072 | BENCH | 5127 | 10 | Ops | Wells Ranch Creek | 68 tonnes | 68 tonnes
CK-2074 | CHIPMUNK CREEK | 5127 | 12 | Ops | Chipmunk Creek | 54 tonnes | 41 tonnes | Fasten deck to girders, post load rating and bridge ahead signs
CK-2076 | FOLEY CREEK | 5127 | 13 | Ops | Foley Creek | 54 tonnes | 54 tonnes | Replace running planks and post load rating and bridsge adead signs
CK-2077 | AIRPLANE CREEK | 5127 | 14 | Ops | Foley Creek | 54 tonnes | 54 tonnes | Post bridge ahead and load rating signs; replace delineators
CK-2078 | CENTRE CREEK | 5127 | 17 | BCTS | Centre Creek | 68 tonnes | 68 tonnes | Post bridge ahead signs, clean deck and remove tires
CK-2085 | CHILLIWACK SOUTH | 5127 | 26 | BCTS | Chilliwack River | 81 tonnes | 81 tonnes | Post bridge ahead and load rating signs, brush approaches and place fenders with activity
CK-2086 | CHILLIWACK SOUTH | 5127 | 26 | BCTS | Center Creek | 68 tonnes | 68 tonnes | Reinstalled this year - no formal inspection completed
CK-2091 | FLORENCE LAKE | 8648 | 01 | Ops | Rolley Creek | 68 tonnes | 68 tonnes | Replace guardrail, risers and blocks
CK-2093 | FLORENCE LAKE | 8648 | 01 | Ops | 79 Creek | 54 tonnes | 54 tonnes | Post bridge ahead and laod rating signs
CK-2096 | FLORENCE LAKE | 8648 | 01 | Ops | Not Known | 68 tonnes | 68 tonnes | Replace guardrail, risers and blocks. Clean deck and grade
CK-2104 | HARRISON EAST | 5748 | 01 | Ops | Slollicum Creek | 91 tonnes | 91 tonnes
CK-2106 | HARRISON EAST | 5748 | 01 | Ops | Bear Creek | 68 tonnes | 68 tonnes
CK-2110 | HARRISON EAST | 5748 | 01 | Ops | Clear Creek | 127 tonnes | 68 tonnes
CK-2113 | HARRISON EAST | 5748 | 01 | Ops | Snowshoe Creek | 136 tonnes | 136 tonnes | Post load rating
CK-2115 | HARRISON EAST | 5748 | 01 | Ops | Big Silver Creek | 136 tonnes | 136 tonnes | Post bridge ahead and load rating signs
CK-2117 | COGBURN CREEK | 5748 | 02 | Ops | North Fork Creek |  | 0 tonnes | Close bridge by barricades. Monitor concrete abutments for movement
CK-2120 | BEAR CREEK | 5748 | 03 | Ops | Not Known | 54 tonnes | 27 tonnes | Post load rating and bridge ahead signs. Replace delineators
CK-2121 | BEAR CREEK | 5748 | 03 | Ops | Bear Creek | unknown | unknown | Send record drawings to CEG. Replace bridge ahead signs and delineators
CK-2126 | LOOKOUT PEAK | 5748 | 07 | Ops | Bear Creek | unknown | 0 tonnes | Block access and remove the remaining stringers before failure
CK-2127 | TALC CREEK | 5748 | 10 | Ops | Talc Creek | 91 tonnes | 10 tonnes | Short term fix is to replace the deck and inspect the ties closely at this time; and place riprap in front of both abutments. Long term fix would be to replace the entire structure
CK-2128 | STS'AILES | 6314 | 01 | Ops | Not Known | 68 tonnes | 68 tonnes | Replace 1 transition and clean deck
CK-2130 | STS'AILES | 6314 | 01 | Ops | Wells Creek | 136 tonnes | 136 tonnes
CK-2131 | STS'AILES | 6314 | 01 | Ops | Not Known | 136 tonnes | 136 tonnes
CK-2132 | STS'AILES | 6314 | 01 | Ops | Simms Creek | 68 tonnes | 68 tonnes
CK-2133 | STS'AILES | 6314 | 01 | Ops | Walian Creek | 136 tonnes | 136 tonnes | Repair damaged guardrail, replace missing delineator and update load rating sign
CK-2134 | STS'AILES | 6314 | 01 | Ops | Hale Creek | 54 tonnes | 54 tonnes | Repair damaged guardrail, replace missing delineator and update load rating sign
CK-2136 | STS'AILES | 6314 | 01 | Ops | Mystery Creek | 63 tonnes | 63 tonnes | Update load rating sign
CK-2139 | STS'AILES | 6314 | 01 | Ops | Kirkland Creek | 54 tonnes | 54 tonnes | Replace failed fill with keyed in rock and move CNPs closer to bridge
CK-2149 | WALIAN CREEK | 6314 | 08 | Ops | Walian Creek | NA | NA | Bridge has been removed
CK-2152 | JONES LAKE | 8149 | 01 | Ops | Not Known | 68 tonnes | 68 tonnes
CK-2153 | JONES LAKE | 8149 | 01 | Ops | Boulder Creek | 68 tonnes | 68 tonnes | Post bridge ahead signs
CK-2167 | LOST CREEK | 8466 | 01 | BCTS | Lost Creek | 68 tonnes | 68 tonnes | Post bridge ahead and load rating signs
CK-2171 | LOST CREEK | 8466 | 01 | BCTS | Kenyon Creek | 54 tonnes | 54 tonnes | Replace guardrail and risers, replace missing delineators, and post bridge ahead and load rating signs
CK-2172 | LOST CREEK | 8466 | 01 | BCTS | Kenyon Creek | 54 tonnes | 10 tonnes | Clean inlet and post load rating
CK-2173 | LOST CREEK | 8466 | 01 | BCTS | Side Creek | unknown | 5 tonnes | Post updated load rating
CK-2174 | LOST-MURDO | 8466 | 02 | BCTS | Side Creek | 54 tonnes | 54 tonnes | Post bridge ahead and load rating signs. Place delineators
CK-2175 | LOST-MURDO | 8466 | 02 | BCTS | Not Known | 54 tonnes | 54 tonnes | Replace D/S left fill with keyed in rock
CK-2176 | LOST-SOUTH | 8466 | 04 | BCTS | Darlene Creek | 68 tonnes | 5 tonnes | Post updated load rating
CK-2178 | TEREPOCKI | 8466 | 06 | BCTS | Salsbury Creek | 54 tonnes | 0 tonnes | Close bridge and barricade
CK-2186 | MOUNT KETTLEY | 8466 | 10 | BCTS | Not Known | 68 tonnes | 41 tonnes | Replace sill prior to industrial activity
CK-2188 | LOST-BLACKLOCK | 8466 | 11 | BCTS | Side Creek | 68 tonnes | 68 tonnes | Replace guardrail, risers and blocks. Install delineators, bridge ahead signs and load rating signs
CK-2194 | MASELPANIK CREEK | 5674 | 01 | Ops | Klesilkwa Creek | 68 tonnes | 68 tonnes | Replace guardrail, risers and blocks. Install delineators, bridge ahead signs and load rating signs
CK-2197 | NAHATLATCH | 6996 | 01 | Ops | Log Creek | 68 tonnes | 68 tonnes | Post 1 new load rating sign
CK-2198 | NAHATLATCH | 6996 | 01 | Ops | Squakum Creek | 68 tonnes | 68 tonnes | Place CNPs or fenders at all 4 corners
CK-2200 | KOOKIPI CREEK | 6996 | 02 | BCTS | Nahatlatch River | 54 tonnes | 54 tonnes | Replace fenders with activity and post load rating and bridge ahead signs
CK-2201 | KOOKIPI CREEK | 6996 | 02 | BCTS | Kookipi Creek | 54 tonnes | 54 tonnes
CK-2202 | KOOKIPI CREEK | 6996 | 02 | BCTS | Side Creek | 91 tonnes | 91 tonnes | Post bridge ahead and load rating signs
CK-2204 | NORTH AINSLIE CREEK | 8019 | 01 | Ops | Goulah Creek | unknown | 41 tonnes | Post load rating and bridge ahead signs. Replace delineators
CK-2207 | MOWHOKAM | 8019 | 02 | Ops | Mowhokam Creek | 68 tonnes | 41 tonnes | Post load rating and bridge ahead signs. Replace delineators
CK-2209 | MOWHOKAM EAST | 8019 | 03 | Ops | Mohawkum Creek | unknown | unknown | Send record drawings to CEG for updated laod rating. Place fenders with activity
CK-2210 | MOWHOKAM EAST | 8019 | 03 | Ops | Mowhokam Creek | unknown | unknown | Send record drawings to CEG for updated laod rating. Place fenders with activity
CK-2211 | NORTH EMORY CREEK | 8147 | 01 | Ops | Side Creek | 68 tonnes | 68 tonnes | Repair D/S left fill prior to activity
CK-2214 | PEERS CREEK | 8126 | 01 | BCTS | Peers Creek | 54 tonnes | 54 tonnes | Post load rating and bridge ahead signs. Replace delineators
CK-2217 | PITT RIVER | 8394 | 01 | Ops | Side Creek | unknown | unknown | Send record drawings to CEG for updated laod rating. Replace missing delineator
CK-2220 | PITT RIVER | 8394 | 01 | Ops | not known | unknown | unknown | Send record drawings to CEG for updated laod rating. Replace missing delineator
CK-2222 | PITT RIVER | 8394 | 01 | Ops | Side Creek | 63 tonnes | 10 tonnes | Post updated load rating
CK-2224 | PITT RIVER | 8394 | 01 | Ops | Shale Creek | 91 tonnes | 41 tonnes | Replace running planks and subdeck prior to activity; closely inpsect the ties at this time. Replace guardrail and risers. Post updated load rating
CK-2225 | PITT RIVER | 8394 | 01 | Ops | Blue Creek | unknown | 0 tonnes | Block access and post
CK-2226 | PITT-BOISE | 8394 | 02 | Ops | Pitt River | 91 tonnes | 41 tonnes | Replace running planks, guardrail and risers. Replace subdeck on span 1. replace missing delineatorsand post load rating and bridge ahead signs
CK-2227 | PITT-BOISE | 8394 | 02 | Ops | Side Creek | 63 tonnes | 63 tonnes | Post load rating and bridge ahead signs
CK-2228 | PITT-BOISE | 8394 | 02 | Ops | Side Creek | 68 tonnes | 27 tonnes | Post load rating and bridge ahead signs
CK-2231 | PITT-BUCKLIN | 8394 | 03 | Ops | Second Canyon Pitt River
CK-2234 | RUBY CREEK | 8125 | 01 | BCTS | West Fork Ruby Creek | 54 tonnes | 54 tonnes | Replace guardrail, risers and blocks; brush approaches and post bridge ahead and load rating signs
CK-2236 | SOWAQUA CREEK | 7004 | 01 | Ops | Not Known
CK-2237 | SOWAQUA CREEK | 7004 | 01 | Ops | Montigny Creek
CK-2239 | SOWERBY CREEK | 8112 | 01 | Ops | Sowerby Creek | 68 tonnes | 68 tonnes | Replace guardrail, risers and blocks. Post load rating and bridge ahead signs. Replace missing delineators
CK-2253 | SQUEAH | 6092 | 01 | Ops | not known | 68 tonnes | 2 tonnes | Post updated load rating. Consider replacing rotten running planks
CK-2254 | SQUEAH | 6092 | 01 | Ops | not known | 68 tonnes | 2 tonnes | Post updated load rating
CK-2255 | SQUEAH | 6092 | 01 | Ops | not known | 68 tonnes | 2 tonnes | Post updated load rating
CK-2256 | SQUEAH | 6092 | 01 | Ops | Kieikum Creek | 68 tonnes | 2 tonnes | Post updated load rating
CK-2261 | STAVE RIVER | 8013 | 01 | Ops | Winslow Creek | 54 tonnes | 54 tonnes | Replace missing delineators and post bridge ahead and load rating signs
CK-2262 | STAVE RIVER | 8013 | 01 | Ops | Side Creek | 85 tonnes | 85 tonnes
CK-2263 | STAVE RIVER | 8013 | 01 | Ops | Side Creek | 54 tonnes | TBD | Clean debris from inlet and inspect again
CK-2264 | STAVE RIVER | 8013 | 01 | Ops | Side Creek | 70 tonnes | 70 tonnes | Replace missing delineators, replace fenders and post bridge ahead and load rating signs
CK-2265 | STAVE RIVER | 8013 | 01 | Ops | Side Creek | 74 tonnes | 74 tonnes | Replace missing delineators and post bridge ahead and load rating signs
CK-2266 | STAVE RIVER | 8013 | 01 | Ops | Side Creek | 70 tonnes | 70 tonnes
CK-2267 | STAVE RIVER | 8013 | 01 | Ops | Ole Creek | 70 tonnes | 70 tonnes
CK-2286 | TSILEUH CREEK | 7978 | 01 | Ops | South Fork Tsileuh Crk | 68 tonnes | 68 tonnes | Replace missing delineators, brush and post bridge ahead and load rating signs
CK-2287 | SILVERHOPE | 8148 | 01 | Ops | Silverhope Creek | 68 tonnes | 68 tonnes | Replace missing delineators and post load rating and bridge ahead signs
CK-2300 | UZTLIUS CREEK | 7972 | 01 | Ops | not known | 68 tonnes | 68 tonnes | Replace ties and deck in 2013 to keep design load rating. Repair guardrail and install fenders. Post bridge ahead and load rating signs
CK-2306 | UZTLIUS-E ANDERSON | 7972 | 02 | Ops | not known | unknown | 10 tonnes | Post updated load rating
CK-2308 | UZTLIUS-E ANDERSON | 7972 | 02 | Ops | not known | 68 tonnes | 5 tonnes | Post load rating
CK-2312 | WEAVER LAKE ONE | 6261 | 01 | Ops | Weaver Creek | 54 tonnes | 54 tonnes | Post load rating and bridge ahead signs. Place fenders
CK-2331 | STAVE RIVER | 8013 | 01 | Ops | Camp Creek | unknown | 27 tonnes | Post load rating and bridge ahead signs. Replace missing delineators
CK-2338 | STAVE RIVER | 8013 | 01 | Ops | not known | 68 tonnes | 68 tonnes
CK-2340 | STAVE RIVER | 8013 | 01 | Ops | not known | 68 tonnes | 68 tonnes
CK-2352 | WINSLOW CREEK | 8013 | 02 | BCTS | Side Creek | 68 tonnes | 68 tonnes | Replace guardrail, risers, and blocks. Replace missing delineators and patch left D/S slab girder. Post load ratings and bridge ahead signs
CK-2357 | CANTELON TEN | 8124 | 10 | Ops | Cantelon Creek | 54 tonnes | 2 tonnes | Post load rating
CK-2376 | MOUNT KETTLEY | 8466 | 10 |  | Side Creek (Lost-Mt. Kettley) | NA | NA | Superstructure removed
CK-2379 | LOST_LEASE | 8466 | 3 | Ops | Unknown | 63 tonnes | 63 tonnes
CK-2386 | CENTRE CREEK | 5127 | 17 | Ops | Centre Creek | 54 tonnes | 5 tonnes | Replace ties, deck, guardrail and risers. Post load rating and bridge ahead signs
CK-2390 | CEDARFLAT CREEK | 7995 | 02 | Ops | Cedar Flat Creek | 68 tonnes | 1 tonnes | Post load rating
CK-2395 | ENGLISH CREEK | 5748 | 20 | Ops | Big Silver River | 136 tonnes | 136 tonnes | Grout left ballast wall where rebar exposed. Replace missing delineators and place no posts or fenders prior to activity. Monitor repaired footing
CK-2400 | NESAKWATCH LAKE | 5127 | 24 | BCTS | not known | 68 tonnes | 68 tonnes | Post bridge ahead and laod rating signs
CK-2401 | NESAKWATCH LAKE | 5127 | 24 | BCTS | not known | 68 tonnes | 68 tonnes | Post bridge ahead and laod rating signs
CK-2443 | NORRISH CREEK | 10326 | 01 | Ops | Hansen Creek | 91 tonnes | 91 tonnes
CK-2444 | NORRISH CREEK | 10326 | 01 | Ops | Cyr Creek | 91 tonnes | 91 tonnes
CK-2445 | NORRISH CREEK | 10326 | 01 | Ops | East Fork | 91 tonnes | 91 tonnes
CK-2446 | NORRISH CREEK | 10326 | 01 | Ops | Tom Creek | 150 tonnes | 150 tonnes
CK-2447 | NORRISH CREEK | 10326 | 01 | Ops | Tom Creek | 150 tonnes | 150 tonnes | Grout over exposed rebar on all slabs
CK-2448 | NORRISH CREEK | 10326 | 01 | Ops | Sally Creek | 136 tonnes | 136 tonnes | Replace guardrail, risers and blocks. Replace missing delineators and 175mm of gravel surfacing
CK-2449 | NORRISH CREEK | 10326 | 01 | Ops | Unknown | 63 tonnes | 63 tonnes
CK-2450 | NORRISH CREEK | 10326 | 01 | Ops | Unknown | 63 tonnes | 63 tonnes
CK-2451 | NORRISH CREEK | 10326 | 01 | Ops | Unknown | 63 tonnes | 63 tonnes
CK-2452 | NORRISH CREEK | 10326 | 01 | Ops | Rose Creek | 150 tonnes | 150 tonnes
CK-2453 | NORRISH CREEK | 10326 | 01 | Ops | Norrish Creek | 91 tonnes | 91 tonnes | repair downstream right guardrail and monitor fill on left approach
CK-2457 | NORRISH CREEK | 10326 | 01 | Ops | Unknown | 91 tonnes | 91 tonnes
CK-2458 | NORRISH CREEK | 10326 | 01 | Ops | Unknown | 91 tonnes | 91 tonnes
CK-2462 | HORNET CREEK | 5748 | 19 | Ops | Unknown | unknown | 27 tonnes | Post load rating signs
CK-2467 | SILVERHOPE | 8148 | 01 | Ops | Unknown | pedestrian | pedestrian | Replace 1 delineator
CK-2468 | HARRISON EAST | 5748 | 01 | Ops | Unknown | 68 tonnes | 68 tonnes | Grout damaged deck
CK-2469 | HARRISON EAST | 5748 | 01 | Ops | Unknown | 136 tonnes | 136 tonnes | Clean deck and replace missing delineator
CK-2472 | CHEHALIS-MAISAL | 8241 | 16 | Ops | Upper Maisal | 136 tonnes | 136 tonnes | Replace missing delineators, place fenders and post bridge ahead and load rating signs
CK-2473 | NAHATLATCH | 6996 | 01 | Ops | Whistle Pig Creek | unknown | 10 tonnes | Replace with activity
CK-2474 | NAHATLATCH | 6996 | 01 | Ops | Unknown | 68 tonnes | 68 tonnes | Replace guardrail, risers and blocks with activity. Grout damaged panel
CK-2475 | NAHATLATCH | 6996 | 01 | Ops | Nahatlatch River | 68 tonnes | 20 tonnes | Replace running planks, guardrail and risers. Place CNPs or fenders and brush
CK-2476 | PUCKAT CREEK | 10485 | 01 | Ops | Puckat Creek | 91 tonnes | 91 tonnes
CK-2477 | NAHATLATCH | 6996 | 01 | Ops | Nahatlatch Creek | 80 tonnes | 80 tonnes
CK-2478 | NAHATLATCH | 6996 | 01 | Ops | Nahatlatch Creek | unknown | 5 tonnes | Replace with activity
CK-2479 | GRIZZLY | 6996 | 16 | Ops | Grizzly Creek | 68 tonnes | 68 tonnes | Replace imssing delineators, place CNPs or fenders and post load rating and bridge ahead signs
CK-2493 | RUBY ELEVEN | 8125 | 11 | BCTS | Mahood Creek | 68 tonnes | 68 tonnes | Post bridge ahead signs, clean deck
CK-2501 | CHEHALIS-FLEETWOOD | 8241 | 08 | Ops | Unknown | 91 tonnes | 91 tonnes
CK-2502 | CHEHALIS-FLEETWOOD | 8241 | 08 | Ops | Unknown | unknown | 54 tonnes | Place new curbs and post load rating and bridge ahead signs prior to activity