## Sheet1
Bush Creek East Fire (K21633) Reviewed by Tim Giles, PGeo, August 4, 2023
Waypoint | Coordinates |  | Photo # | Culvert Size | Culvert Condition
| Easting | Northing
Adams 1 | 307194 | 5657964 | 970, 971, 972 | 600 cmp | big creek draw, active creek, partially blocked, inlet needs cleaned, old culvert downstream
Adams 2 | 307187 | 5657771 | 973 | 500 cmp | ok, clean sump
Adams 3 | 307144 | 5657422 | 974 | 500 cmp | ok, clean sump
Adams 4 | 307165 | 5657296 | 975 |  | x-drain culvert, elevated about 1 m above ditch base
Adams 5 | 307166 | 5657216 | 976 | 300 cmp | x-drain culvert, flow in ditch from south
Adams 6 | 307114 | 5657026 | 977 | 450 cmp | long culvert on two creeks, partially plugged by carbonates
Adams 7 | 307158 | 5656922 |  |  | culvert on fire map, not found in field
Adams 8 | 307198 | 5658643 | 978 | 500 cmp | ok, clean sump
Adams 9 | 307224 | 5656444 |  |  | culvert on fire map, not found in field
Adams 10 | 307225 | 5655964 | 979 | 500 plastic | all good unless it burns
Adams 11 | 307080 | 5655703 | 980 | 500 cmp | ok, clean sump
Adams 12 | 306918 | 5655601 | 981, 982, 983 | 600 cmp | big road fill on top of smallish culvert, catch basin mostly clear, big gullied watershed above
Adams 13 | 307053 | 5655331 |  |  | culvert on fire map, not found in field
Adams 14 | 307096 | 5654258 |  |  | culvert on fire map, not found in field
Adams 15 | 306982 | 5654072 | 984 | 1000 cmp | big creek, big road fill, long culvert, carbonate build up at inlet
Adams 16 | 307077 | 5653953 | 985 | 400 plastic | x-drain, elevated 30 cm above ditch
Adams 17 | 307136 | 5653788 | 986 | 400 plastic | under access road, ok
Adams 18 | 307128 | 5653732 |  | 300 cmp | crushed inlet, sump needs cleaned, upgrade
Adams 19 | 307129 | 5653638 |  |  | culvert on fire map, not found in field
Adams 20 | 307018 | 5653362 |  |  | culvert on fire map, not found in field
Adams 21 | 307022 | 5653083 |  |  | culvert on fire map, not found in field
Adams 22 | 306987 | 5652916 | 987 | 1000 cmp | big creek, oblique to flow, active (old culvert may still be in road, exposed just up ditch)
Adams 23 | 306945 | 5652864 | 988 | 600 cmp | badly mangled inlet limits flow
Adams 24 | 306929 | 5652852 | 989 | 600 cmp | 30 m downchain from Adams 23, partially blocked
Adams 25 | 306908 | 5652799 | 990 | 400 cmp | under access road, mostly blocked but still active
Adams 26 | 306890 | 5652759 | 991 | 400 cmp | x-drain, ditch relief, elevated 30 cm above ditch, no creek above
Bush 1 | 306940 | 5652495 | 992 | 500 cmp | start of Bush FSR, relieves Adams FSR ditch