## Sheet1
HPCC West Procter 2019-2022 fuel treatment: budget worksheet with assumptions
November 28, 2018
Unit | #ha | m3/ha L1 volume (>12.5cm dbh) harvested | total m3 | % sawlog | sawlog volume | % pulp | pulp volume | avg sawlog price / m3 | pulp price / m3 | blended price / m3 | gross revenue /ha | Gross project revenue | logging cost /m3 | logging cost /ha | hauling cost / m3 | hauling cost / ha | blended stumpage rate / m3 | stumpage / ha | post-harvest fuel reduction cost/ha | post-harvest fuel reduction cost/m3 | supervision cost/ha | total supervision cost | admin cost / ha | total admin cost | supervision and admin cost/ha | total cost /ha | Total cost | net cost / ha | NET COST TOTAL = FES funds requested | total cost / m3 | net cost / m3 | % project funding from FES
Assumption made (see below) |  | A |  | B |  | C |  | D | E |  |  |  | F |  | G |  | H |  | I |  | J |  | K
West Procter 1 2019 | 20 | 180 | 3600 | 40% | 1440 | 60% | 2160 | 80 | 45 | 59 | 10620 | 212400 | 40 | 7200 | 19 | 3420 | 2 | 360 | 2500 | 13.8889 | 300 | 6000 | 750 | 15000 | 1050 | 14530 | 290600 | 3910 | 78200 | 80.7222 | 21.7222 | 26.91%
West Procter 2 2020 | 20 | 180 | 3600 | 40% | 1440 | 60% | 2160 | 80 | 45 | 59 | 10620 | 212400 | 40 | 7200 | 19 | 3420 | 2 | 360 | 2500 | 13.8889 | 300 | 6000 | 750 | 15000 | 1050 | 14530 | 290600 | 3910 | 78200 | 80.7222 | 21.7222 | 26.91%
West Procter 3 2021 | 20 | 180 | 3600 | 40% | 1440 | 60% | 2160 | 80 | 45 | 59 | 10620 | 212400 | 40 | 7200 | 19 | 3420 | 2 | 360 | 2500 | 13.8889 | 300 | 6000 | 750 | 15000 | 1050 | 14530 | 290600 | 3910 | 78200 | 80.7222 | 21.7222 | 26.91%
TOTAL | 60 |  | 10800 |  | 4320 |  | 6480 |  |  |  |  | 637200 | [14 empty] | 871800 |  | 234600
Assumptions
A | Harvest volumes based on initial summary data from timber recce/ cruise plots in treatment area. Expectation is that approximately 2/3 of the total stand volume will be removed--mostly hemlock
B | Sawlog percentage based on timber plot summary that indicates high percentage of small diameter and low quality hemlock including many damaged trees left from 1980s era highgrading
C | Pulp volume includes Grade 6 logs (~12.5 to 17.5cm dbh) which will be used for pulp instead of being burned on site (enhanced utilization). Estimate approximately 30 m3/ha of pulp will be Grade 6.
D | Sawlog price based on assumption that hemlock sawlogs (50%) will be worth $60/m3 and other species (50%) will be worth average of $100/ m3 (mix of fir/larch/cedar/pine). Based on current delivered log prices.
E | Pulp price based on expected price to be negotiated with Celgar pulp mill. Similar to current pricing. Celgar has indicated support for the project and is willing to take small diameter (to 1" top). Actual price TBD. Pulp market volatile.
F | Logging cost based on expected all-found logging rate, including spur road and landing development. Logging rate will be high because of low volume / ha, high levels of dispersed retention, very small piece size, and high expectations of tidy results (community watershed).
G | Based on current hauling costs from Procter to Celgar pulp mill and Interfor. May go up a bit due to slower loading of Grade 6 pulp logs.
H | Based on current HPCC tabular stumpage rates. Blended rate based on % pulp assumptions. Stumpage assessment will depend on what Celgar stratum the pulp is placed in.
I | Based on local industry standards for clean-up of post-harvest logging debris in WUI areas. Understory is 6,000 SPH so lots of slash expected even with improved utilization of Grade 6.
J | Supervision costs based on Qualified Professional conducting average of 6 hours of inspections and documentation per week at $60/hour. Total project expected to take 16 weeks.
K | Administration costs include cutting permit development, negotiation of log prices, tendering and contract administration, book-keeping, reporting, etc. Admin costs ~5% of project budget.