## Summary
Block | Area | Planning | Assessments | Prescription | Treatment ** | Supervison | Total
WAE-15A | 41 | 4100 | 1681 | 4100 | 102500 | 8200 | 120581
KOKANEE Crown_LOT | 80 | 6400 | 6400 | 800 | 200000 | 16000 | 236800
Smallwood All | 85 | 6800 | 7225 | 8500 | 212500 | 15000 | 250025
TOTAL | 206 | 17300 | 15306 | 13400 | 515000 | 39200 | 607406
| YEAR | WAE-15A | AREA | KOKANEE- CROWNLOT |  | SMALLWOOD |  | TOTAL
| 18/19 | 820 |  | 800 |  | 850 |  | 2470
| 19/20 | 62651 | 20 | 19200 | 0 | 20825 | 0 | 102676
| 20/21 | 57110 | 21 | 108400 | 40 | 108425 | 45 | 273935
| 21/22 | 0 |  | 108400 | 40 | 121925 | 40 | 230325
| TOTAL | 120581 |  | 236800 |  | 252025 |  | 609406 | 609406

## WAE_15A
Block | Area | Year | Planning |  |  |  | Assessments |  |  | Prescription |  |  | Treatment ** |  |  | Supervision |  |  | Total
|  |  | Activity |  | Cost | Total | Area | Cost | Total | Area | Cost | Total | Area | Cost * | Total | Area | Cost | Total
WAE-15A | 41 | 18/19 | meetings/consultation | 20% | 100 | 820 | [12 empty] | 820
| 41 | 19/20 | meetings/consultation | 70% | 100 | 2870 | 41 | 50 | 1681 | 41 | 100 | 4100 | 20 | 2500 | 50000 | 20 | 200 | 4000 | 62651
| 41 | 20/21 | meetings/consultation | 10% | 100 | 410 | [6 empty] | 21 | 2500 | 52500 | 21 | 200 | 4200 | 57110
WAE-15A | [5 empty] | 4100 |  |  | 1681 |  |  | 4100 |  |  | 102500 |  |  | 8200 | 120581
* Cost could vary from 1200-2500 depending of best method assess for the site
**Treatment is describe as :
mechanical treatment of piling, burning, or chipping, and prunning, and fethering of reserves if necessary.

## KOKANEE_CROWNLOT
Block | Area | Year | Planning |  |  |  | Assessments |  |  | Prescription |  |  | Treatment |  |  | Supervision |  |  | Total
|  |  | Activity |  | Cost | Total | Area | Cost | Total | Area | Cost | Total | Area | Cost | Total | Area | Cost | Total
KOKANEE crown_lot | 80 | 18/19 | meetings/consultation | 10% | 100 | 800 | [12 empty] | 800
| 80 | 19/20 | meetings/consultation | 60% | 100 | 4800 | 80 | 100 | 6400 | 80 | 100 | 8000 | [6 empty] | 19200
| 80 | 20/21 | meetings/consultation | 5% | 100 | 400 | [6 empty] | 40 | 2500 | 100000 | 40 | 200 | 8000 | 108400
| 80 | 21/22 | meetings/consultation | 5% | 100 | 400 | [6 empty] | 40 | 2500 | 100000 | 40 | 200 | 8000 | 108400
| TOTAL |  |  |  |  | 6400 |  |  | 6400 |  |  | 8000 |  |  | 200000 |  |  | 16000 | 236800
**Treatments are describe as :
Mechanical treatment of piling, burning, or chipping, and fethering of reserves if necessary.
Hand treatment of piling, pruning, and burning.- feathering of reserve.
0
* Cost of treatment could vary from 1200-2500 depending of best method assessed for the site
** *AREA are estimate and will most likely be less after some field verification and assessments.

## SMALLWOOD
Block | Year | Area | Planning |  |  |  | Assessments |  |  | Prescription |  |  | Treatment |  |  | Supervision |  |  | Total | Year
|  |  | Activity |  | Cost | Total | Area | Cost | Total | Area | Cost | Total | Area | Cost | Total | Area | Cost | Total
Smallwood total 85 ha | 18/19 | 85 | meetings/consultation | 10% | 100 | 850 | [12 empty] | 850 | 18/19
SMA-16A (8ha) | 19/20 | 85 | meetings/consultation | 60% | 100 | 5100 | 85 | 100 | 7225 | 85 | 100 | 8500 | [6 empty] | 20825 | 19/20
SMA-017A(56 ha) | 20/21 | 85 | meetings/consultation | 5% | 100 | 425 | [6 empty] | 40 | 2500 | 100000 | 40 | 200 | 8000 | 108425 | 20/21
SMA-15-55(21 ha) | 21/22 | 85 | meetings/consultation | 5% | 100 | 425 | [6 empty] | 45 | 2500 | 112500 | 45 | 200 | 9000 | 121925 | 21/22
TOTAL | [5 empty] | 6800 |  |  | 7225 |  |  | 8500 |  |  | 212500 |  |  | 17000 | 252025
**Treatments are describe as :
Mechanical treatment of piling, burning, or chipping, and fethering of reserves if necessary.
Hand treatment of piling, pruning, and burning.- feathering of reserve.
0
* Cost of treatment could vary from 1200-2500 depending of best method assessed for the site
** *AREA are estimate and will most likely be less after some field verification and assessments.