## Sheet1
Nass Operating Agreeement Five Year Plan May 1 2020
| Licensee: | CRD
| Tenure: | A16884
| AAC: | 291000
| Shapefiles Submitted: | Yes/No
| KMLs submitted: | Yes/No
Submission Date:
| Block Identifier | Merch Area (ha) | Estimated Net Merch Volume (m3) | General Location | Mapsheet (1:20000) | Planned Harvest Year | Status (P=Proposed/ R=Recce'd/ W=Work in Progress/ F=Field Marked/ C=Cutting Authority Issued)
| 1 | 48.5468 | 16800 | Bell-Irving River | 104A025 | 2025 | P
| 184 | 14.5355 | 5075 | Oweegee Creek | 104A062 | 2025 | P
| 184 | 6.5767 | 2303 | Oweegee Creek | 104A062 | 2025 | P
| 212 | 29.056 | 9425 | Bell-Irving River | 104A024 | 2025 | P
| 371 | 109.6465 | 40875 | Bowser Lake | 104A043 | 2025 | P
| 373 | 111.2711 | 41625 | Bowser Lake | 104A043 | 2025 | P
| 373 | 49.8674 | 18750 | Bowser Lake | 104A043 | 2025 | P
| 377 | 24.3719 | 9600 | Bowser Lake | 104A043 | 2025 | P
| 378 | 13.931 | 5460 | Bowser Lake | 104A043 | 2025 | P
| 420-4 | 10.5934 | 3200 | Nass River | 104A015 | 2023 | P
| 424-1 | 5.2558 | 1800 | Nass River | 104A015 | 2023 | P
| 424-2 | 5.5881 | 1800 | Nass River | 104A015 | 2023 | P
| 427 | 86.024 | 30100 | Nass River | 104A005 | 2023 | P
| 431-3 PolyA | 4.4469 | 1200 | Axnegrelga Creek | 103P096 | 2022 | P
| 431-3 PolyB | 3.7876 | 1000 | Axnegrelga Creek | 103P096 | 2022 | P
| 431-3 PolyC | 0.93494 | 300 | Axnegrelga Creek | 103P096 | 2022 | P
| 431-3 PolyD | 4.3738 | 1400 | Axnegrelga Creek | 103P096 | 2022 | P
| 431-4 | 33.1676 | 11550 | Axnegrelga Creek | 103P096 | 2022 | P
| 434 | 16.4227 | 4800 | Axnegrelga Creek | 103P096 | 2024 | P
| 444-1 | 7.8661 | 1950 | Nass River | 104A005 | 2024 | P
| 451 | 86.3881 | 21500 | Nass River | 104A005 | 2024 | P
| 454 | 22.6119 | 6600 | Gleason Creek | 104A005 | 2024 | P
| 455 | 17.4993 | 5025 | Gleason Creek | 103P095 | 2024 | P
| 457 PolyA | 7.4583 | 2250 | Axnegrelga Creek | 103P096 | 2022 | P
| 457 PolyB | 8.3005 | 2905 | Axnegrelga Creek | 103P096 | 2022 | P
| 457 PolyC | 2.2063 | 775 | Axnegrelga Creek | 103P096 | 2022 | P
| 457 PolyD | 1.7096 | 450 | Axnegrelga Creek | 103P096 | 2022 | P
| 457 PolyE | 3.9242 | 1400 | Axnegrelga Creek | 103P096 | 2022 | P
| 457 PolyF | 7.3439 | 2865 | Axnegrelga Creek | 103P096 | 2022 | P
| 457 PolyG | 4.4394 | 1650 | Axnegrelga Creek | 103P096 | 2022 | P
| 458 | 4.1659 | 1525 | Axnegrelga Creek | 103P096 | 2022 | P
| 459 PolyA | 3.5077 | 1550 | Axnegrelga Creek | 103P096 | 2022 | P
| 459 PolyB | 8.4867 | 2075 | Axnegrelga Creek | 103P096 | 2022 | P
| B02-S01 | 32.8996 | 14805 | Bear River | 104A011 | 2020 | P
| B02-S02-1 | 4.1976 | 1250 | Bear River | 104A011 | 2020 | P
| B02-S02-2 | 4.092 | 1325 | Bear River | 104A011 | 2020 | P
| B02-S03 | 11.3908 | 4400 | Bear River | 104A001 | 2020 | P
| B02-S06 | 9.5383 | 3300 | Bear River | 104A001 | 2020 | P
| B02-S07 | 10.5694 | 3950 | Bear River | 103P091 | 2020 | P
| B02-S08 | 31.7807 | 8200 | Bear River | 103P091 | 2020 | P
| B05 | 8.8053 | 2640 | Bell-Irving River | 104A035 | 2025 | P
| B12 | 162.1879 | 51840 | Bell-Irving River | 104A025 | 2025 | P
| B13 | 60.9473 | 182110 | Bell-Irving River | 104A025 | 2025 | P
| B14 | 35.2682 | 10500 | Bell-Irving River | 104A025 | 2025 | P
| C01-112 | 14.5025 | 3262 | Bell-Irving River | 104A072 | 2025 | P
| C14-362 | 12.4595 | 4062 | Bowser Lake | 104A043 | 2022 | C
| C14-366 | 1.3011 | 450 | Bowser Lake | 104A043 | 2022 | C
| C14-368 | 6.6171 | 1800 | Bowser Lake | 104A043 | 2022 | C
| C14-369 | 5.0913 | 1500 | Bowser Lake | 104A043 | 2022 | C
| C15-356 | 65.7683 | 22750 | Bell-Irving River | 104A053 | 2022 | C
| C15-364 | 11.5097 | 3850 | Bowser Lake | 104A043 | 2022 | C
| C15-379 | 34.1868 | 11900 | Bowser Lake | 104A043 | 2022 | C
| C16-158 | 19.1397 | 6650 | Bell-Irving River | 104A072 | 2025 | P
| C16-A15 | 10.3167 | 3610.8393 | Bell-Irving River | 104A072 | 2025 | P
| C16-A16 | 10.9339 | 3826.8517 | Bell-Irving River | 104A072 | 2025 | P
| C16-A17 | 11.9984 | 4199.4307 | Bell-Irving River | 104A072 | 2025 | P
| C16-A18 | 10.8714 | 3804.9785 | Bell-Irving River | 104A072 | 2025 | P
| C16-A19 | 22.2625 | 7791.8827 | Bell-Irving River | 104A072 | 2025 | P
| C16-A21 | 25.4907 | 8921.7478 | Bell-Irving River | 104A082 | 2025 | P
| C17-374 | 149.2187 | 59687.4969 | Bowser Lake | 104A043 | 2022 | C
| C17-380 | 86.4821 | 34592.8308 | Bowser Lake | 104A043 | 2022 | C
| C17-382 | 1.6728 | 669.1151 | Bowser Lake | 104A043 | 2022 | C
| C18-375 | 56.0595 | 22423.8045 | Bowser Lake | 104A043 | 2022 | P
| C18-376 | 84.1924 | 33676.951 | Bowser Lake | 104A043 | 2022 | P
| C19-152 | 34.2262 | 11465.7842 | Oweegee Creek | 104A062 | 2024 | P
| C19-153 | 29.726 | 9958.2061 | Oweegee Creek | 104A062 | 2024 | P
| C19-154 | 10.7328 | 3595.4929 | Oweegee Creek | 104A062 | 2024 | P
| C19-160 | 11.4139 | 3823.6554 | Oweegee Creek | 104A062 | 2024 | P
| C19-164 | 6.9925 | 2342.483 | Bell-Irving River | 104A072 | 2024 | P
| C19-165 | 1.8491 | 619.4509 | Bell-Irving River | 104A071 | 2024 | P
| C19-166 | 2.8289 | 947.6663 | Bell-Irving River | 104A071 | 2024 | P
| C19-167 | 3.5422 | 1186.6424 | Bell-Irving River | 104A072 | 2024 | P
| C19-168 | 14.3417 | 4804.485 | Bell-Irving River | 104A071 | 2024 | P
| C19-169 | 4.4854 | 1502.6134 | Bell-Irving River | 104A072 | 2024 | P
| H1 | 21.4525 | 5899.4457 | Nass River | 103P095 | 2020/21 | P
| H10 | 76.7566 | 21108.0614 | Nass River | 103P086 | 2020/21 | P
| H11 | 12.1967 | 3354.1014 | Nass River | 103P086 | 2020/21 | P
| H12 | 40.8017 | 11220.4797 | Nass River | 103P086 | 2020/21 | P
| H13 | 53.6983 | 14767.0332 | Nass River | 103P086 | 2020/21 | P
| H14 | 16.8806 | 4642.1781 | Nass River | 103P086 | 2020/21 | P
| H15 | 11.5693 | 3181.5495 | Nass River | 103P076 | 2020/21 | P
| H16 | 18.2128 | 5008.5216 | Derrick Lake | 103P077 | 2020/21 | P
| H17 | 12.2466 | 3367.8244 | Derrick Lake | 103P067 | 2020/21 | P
| H18 | 24.2358 | 6664.8441 | Derrick Lake | 103P067 | 2020/21 | P
| H19 | 15.3354 | 4217.2234 | Derrick Lake | 103P067 | 2020/21 | P
| H2 | 15.7939 | 4343.3299 | Nass River | 103P095 | 2020/21 | P
| H21 | 11.0539 | 3039.8339 | Nass River | 103P095 | 2020/21 | P
| H3 | 6.332 | 1741.2893 | Nass River | 103P095 | 2020/21 | P
| H4 | 60.8585 | 16736.0904 | Nass River | 103P095 | 2020/21 | P
| H5 | 9.0335 | 2484.2207 | Nass River | 103P095 | 2020/21 | P
| H6 | 5.6519 | 1554.2707 | Nass River | 103P095 | 2020/21 | P
| H7 | 4.8502 | 1333.8016 | Nass River | 103P085 | 2020/21 | P
| H8 | 85.0009 | 23375.2573 | Nass River | 103P085 | 2020/21 | P
| H9 | 5.7957 | 1593.8168 | Nass River | 103P086 | 2020/21 | P
| HWY PL8 | 8.954 | 1990 | Derrick Lake | 103P067 | 2020/21 | P
| I07-B07 | 10.1313 | 2988.7362 | Bell-Irving River | 104A025 | 2024 | C
| I07-B08 | 1.8324 | 540.5446 | Bell-Irving River | 104A025 | 2024 | C
| I07-B09 | 6.9591 | 2052.9328 | Bell-Irving River | 104A025 | 2024 | C
| I07-B10 | 16.02 | 4725.9134 | Bell-Irving River | 104A025 | 2024 | C
| I07-B11-A | 1.6277 | 480.1608 | Bell-Irving River | 104A035 | 2024 | C
| I07-B11-B | 6.7198 | 1982.3278 | Bell-Irving River | 104A035 | 2024 | C
| K01-210 | 44.7092 | 14530.5016 | Bell-Irving River | 104A024 | 2024 | C
| Kotcho11 | 11.8319 | 3845.3731 | Bell-Irving River | 104A025 | 2024 | P
| Kotcho14 | 4.1328 | 1343.1627 | Bell-Irving River | 104A025 | 2024 | P
| Kotcho15 | 6.5682 | 2134.6492 | Bell-Irving River | 104A025 | 2024 | P
| Kotcho16 | 26.0061 | 8451.984 | Bell-Irving River | 104A025 | 2024 | P
| Kotcho18 | 2.5039 | 813.7761 | Bell-Irving River | 104A025 | 2024 | P
| Kotcho19 | 30.5233 | 9920.0618 | Bell-Irving River | 104A025 | 2024 | P
| Kotcho2 | 13.7623 | 4472.7446 | Bell-Irving River | 104A034 | 2024 | P
| Kotcho21 | 21.953 | 7134.7316 | Bell-Irving River | 104A025 | 2024 | P
| Kotcho7 | 25.6262 | 8328.5111 | Bell-Irving River | 104A024 | 2024 | P
| Kotcho8 | 7.4683 | 2427.2136 | Bell-Irving River | 104A024 | 2024 | P
| Kotcho9 | 19.8848 | 6462.5639 | Bell-Irving River | 104A025 | 2024 | P
| M1 | 55.4922 | 20809.5892 | Meziadin Lake | 104A005 | 2024 | P
| M10 | 68.6308 | 25736.5617 | Nass River | 103P095 | 2024 | P
| M10-426-3 | 20.0039 | 7501.4723 | Gleason Creek | 104A005 | 2021 | C
| M10-441-2 | 6.6726 | 2502.2344 | Nass River | 104A005 | 2021 | C
| M10-442 | 35.0695 | 13151.0521 | Nass River | 104A005 | 2020 | C
| M11 | 12.5738 | 4715.1765 | Nass River | 103P095 | 2023 | P
| M12 | 17.0615 | 6398.0606 | Nass River | 103P095 | 2023 | P
| M12-420-1 | 106.5248 | 39946.8144 | Nass River | 104A015 | 2021 | C
| M12-420-3 | 30.558 | 11459.2583 | Nass River | 104A005 | 2021 | C
| M13 | 31.67 | 11876.2367 | Nass River | 103P095 | 2023 | P
| M13-428 | 129.3727 | 48514.7705 | Nass River | 104A015 | 2022 | C
| M15-441-4 | 1.5502 | 581.3124 | Nass River | 104A005 | 2021 | C
| M15-443 | 9.3733 | 3514.9862 | Nass River | 104A005 | 2021 | C
| M15-444 | 22.4302 | 8411.3388 | Nass River | 104A005 | 2020 | C
| M15-453 | 10.4512 | 3919.2006 | Nass River | 104A005 | 2021 | C
| M4 | 11.1208 | 2780.2083 | Meziadin Lake | 104A004 | 2021/22 | P
| M5 | 17.757 | 4439.2403 | Meziadin Lake | 104A005 | 2021/22 | P
| M6 | 54.2331 | 13558.2779 | Meziadin Lake | 103P095 | 2021/22 | P
| M7 | 60.631 | 15157.7528 | Meziadin Lake | 103P095 | 2021/22 | P
| M8 | 17.7768 | 4444.197 | Meziadin Lake | 103P095 | 2021/22 | P
| M9 | 17.3878 | 4346.9555 | Meziadin Lake | 103P095 | 2021/22 | P
| Madely7 | 68.4548 | 13690.9604 | Brown Bear | 104A006 | 2023 | P
| Madely9 | 140.048 | 28009.6052 | Axnegrelga Creek | 103P096 | 2023 | P
| NR11 | 3.8748 | 1162.4272 | Paw Creek | 103P085 | 2021/22 | P
| NR14 | 10.2688 | 3080.639 | Paw Creek | 103P085 | 2021/22 | P
| NR16 | 14.5153 | 4354.5852 | Nass River | 103P086 | 2021/22 | P
| NR17 | 33.3071 | 9992.1316 | Paw Creek | 103P086 | 2021/22 | P
| NR18 | 22.3228 | 6696.8305 | Paw Creek | 103P086 | 2021/22 | P
| NR18 | 7.0247 | 2107.3992 | Paw Creek | 103P086 | 2021/22 | P
| NR19 | 40.5178 | 12155.3284 | Paw Creek | 103P086 | 2021/22 | P
| NR20 | 23.6037 | 7081.101 | Little Paw Creek | 103P085 | 2021/22 | P
| NR20 | 9.9834 | 2995.0163 | Little Paw Creek | 103P085 | 2021/22 | P
| NR20 | 15.7727 | 4731.8044 | Little Paw Creek | 103P085 | 2021/22 | P
| T01-122-1 | 70.6992 | 21209.7706 | Snowbank Creek | 104A071 | 2024 | C
| T01-122-2 | 10.6493 | 3194.7786 | Snowbank Creek | 104A071 | 2024 | C
| T01-122-3 | 1.6022 | 480.6499 | Snowbank Creek | 104A071 | 2024 | C
| T01-122-6 | 0.41075 | 123.2262 | Snowbank Creek | 104A071 | 2024 | C
| T01-171 | 38.0143 | 11404.2951 | Snowbank Creek | 104A071 | 2024 | C
| T01-176 | 1.7093 | 512.7963 | Snowbank Creek | 104A071 | 2024 | C
| T01-176-5 | 2.1579 | 647.3826 | Snowbank Creek | 104A071 | 2024 | C
| T01-176-6 | 1.8688 | 560.6358 | Snowbank Creek | 104A071 | 2024 | C
| T01-180 | 8.5612 | 2568.3646 | Snowbank Creek | 104A071 | 2024 | C
| WN 44 | 8.4843 | 2545.2925 | Harper | 103P067 | 2021/22 | P
| WN 48 | 10.0511 | 3015.33 | Harper | 103P067 | 2021/22 | P
| WN 6-1 | 16.6678 | 5000.3255 | White River | 103P095 | 2021/22 | P
| WN 6-2 | 7.3543 | 2206.3006 | White River | 103P095 | 2021/22 | P
| WN 6-3 | 19.4322 | 5829.6693 | White River | 103P095 | 2021/22 | P
| WN11 | 24.2127 | 7263.8074 | White River | 103P095 | 2021/22 | P
| WN11A | 6.9176 | 2075.272 | White River | 103P095 | 2021/22 | P
| WN26 | 12.4866 | 3745.9719 | Nass River | 103P095 | 2021/22 | P
| WN938A | 3.5235 | 1057.0547 | Nass River | 103P086 | 2021/22 | P
| WN938A | 9.5024 | 2850.7163 | Nass River | 103P086 | 2021/22 | P
|  | 4051.5082 | 1473952.6353
| AAC (m3): | 291000
| 5 years x AAC (m3): | 1455000
| Submitted total (m3): | 1473952.6353