## Sheet1
Moose Recovery - Project Evaluation Draft
Murphy LU
Verification needed | Project Description | Funding Covered by: | Meeting Comments | Moose Inventory Status | Moose Habitat |  | Area Affected |  |  |  |  | Deactivation | Deactivation Effectiveness |  | Barrier Cost | FN Support | Stakeholder Support | Caribou | Wolf Use | Reclamation | Overall Assessment of Deactivation Option
[7 empty] | Comments from Meeting | Road length | Total Area | GIS Estimate | Total Area | Strategy
| Licensee_road_# |  |  | (Year assessed) | HVMS/Suitability | Capability |  | (km road) | (km road x 2) | (km road) | (km x 2) | Proposed | (H,M,L) | Comments (based on Ortho) | ($) | (Yes; No; Why) | (Yes; No; Why) | (Overlap/Not) | (Increase/Decrease) | (feasible)
| WF_1_DONE | N/A | Works already completed |  | High Suitability | Moderate | [5 empty] | tank trap; road ripping
| WF_2_DONE | N/A | Works already completed |  | High Suitability | Moderate | [5 empty] | tank trap; road ripping
| WF_3 | WF | NSR behind this point; WF need to survey this summer, then can permanently remove |  | on edge of high suitability | Moderate capability adjacent to high capability along north side of Murphy Lk | ~3km of road plus 3km NSR | 6 | 12 | 3.9 km NSR + 7.87 spur roads = 11.84km | 23.68 | pyramid blocks for now; after summer survey complete full rehab | [8 empty] | High | Results in access mgmt of a large area in high suitability/moderate capability
| WF_4 | WF | deactivate inblock roads |  | in suitable habitat disturbed by roads, edging onto suitable area w/o road disturbance; road leads into wetland area | Moderate capability | ~400m | 0.4 | 0.8 | 0.55 | 1.1 | deep ripping for 100m | L | Looks to be open area where ATV/vehicle could drive around deactivation point? | [6 empty] | Moderate | road leads into wetland area; however a small amount of road deactivated into an area with # of surrounding roads NOTE: is there potential to do further work in this area wrt loop roads?
| WF_5 | WF | deactivate inblock roads; may be NSR (once WF permit expires) |  | in suitable habitat not disturbed by roads; road leads into wetland area with adjacent cover | Moderate capability | ~400m | 0.4 | 0.8 | 0.65 | 1.3 | deep ripping for 100m | L | Looks to be open area where ATV/vehicle could drive around deactivation point? | [6 empty] | Moderate | road leads into wetland area with adjacent cover; however a small amount of road deactivated into an area with # of surrounding roads NOTE: is there potential to do further work in this area wrt loop roads?
| WF_6 | WF | deactivate in block road just off main road |  | in suitable habitat disturbed by roads; adjacent to non-suitable habitat | High capability | n/a | n/a | n/a | 1.9 | 3.8 | 100m ripping; rehab | M | Looks to be forested area on either side of road to aid deactivation | [6 empty] | Moderate | in forested area providing cover for moose and aiding with deactivation; leads into creek/wet area that is forested and with some other roads in area leading in
| Tolko_10 | n/a | GATE_currently exists; a strategy to stop loop road access into DCC |  | high suitability | high capability | n/a | n/a | n/a | n/a | n/a | temporary pyramid blocks to allow access when needed | M | in forested area; temporary | [6 empty] | Low | temporary measures to prevent loop road but access is needed some parts of the year; significant number of roads north and south of access point
| WF_7 | WF | further effort to block loop road to DCC |  | in suitable habitat not disturbed by roads | on edge of high capability into non-capable | n/a | n/a | n/a | n/a | n/a | temporary pyramid blocks to allow access when needed | L-M | depending on location of blocks, could be forested on both sides of the road or open on one side | [6 empty] | Low | temporary measures to prevent loop road but access is needed some parts of the year; significant number of roads north and south of access point
Verify location of bridge to be pulled; is it on main road (MAIN EXT. 7456-04) or adjacent block road (BRA926)? Assessment is based on BRA926 road deactivation. | WF_8 | WF | potential to remove bridge; logstringer; WF could retire # of roads above it; Tolko is done in the area as well as BCTS; NEED TO CHECK that no access needed (silv); Stakeholders will raise issue |  | Access point and associated roads are not in suitable habitat; but ~0.5 km from suitable habitat; some wetlands in close proximity | In area identified as not capable moose habitat; but ~0.5 km from strip of VH capable habitat | n/a | n/a | n/a | 5.85 | 11.7 | permanent potential - pull bridge; outside Murphy watershed but still a positive effect | H | Need to identify where bridge is as can't see on ortho | [6 empty] | Moderate | Bridge removal is permanent deactivation measure, as long as vehicles can't drive through after removal; area is not great moose habitat but some wetlands in the area and deactivation would remove access to a core area with some cover and adjacent feed
| WF_9 | WF | WF can remove, no longer needs in |  | in suitable habitat not disturbed by roads; in area of wetlands and lakes | moderate capability; in area lacking adequate cover | ~1km | 1 | 2 | 1.9 | 3.8 | road ripping | M | Looks to be in open cutblock; suggest locating deactivation in area where vehicles can't find a way around rehab point | [6 empty] | Moderate | If deactivation can be located so as to fully prevent vehicle access, it does provide a core area of forested and non-forested habitat with wetland/lake areas for forage
Further road on Ortho that's not shown on Roads layers...verify if these exist and if part of this proposal | WF_10/FLNRO | WF | issues with resident wanting access to their water-access only cabins; within OGMA; Canim to support |  | OGMA; high suitability disturbed by roads | high capability; along Murphy Lake; in adequate cover | n/a | n/a | n/a | 0.8 | 1.6 | road ripping; rehab road; WF needs culvert at Marset ck so can't yet remove but will prevent access beyond culvert | H | in forested area |  | Yes, Canim has raised concern in the past and will support WF deactivation effort | No, residents with lakefront cabins use road and have raised issue in the past when access mgmt measures have been completed |  |  |  | Moderate (if further road network west of deactivation is verified could be High) | In high capable and high suitable habitat adjacent to Murphy Lake;
Verify where on road deactivation point should be? | FLNRO_1 | FLNRO | permanent deactivation; NSR |  | High Suitability not disturbed by roads | moderate capability; along Murphy Lake; in adequate cover | n/a | n/a | n/a | 1.75 | 3.5 | road ripping | M | Looks to be in open cutblock, potentially on slope assisting with deactivation effectiveness; suggest locating deactivation in area where vehicles can't find a way around rehab point | [6 empty] | Moderate | in moderate capability, high suitability moose habitat, small amount of road being removed into a cutblock with adjacent cover and some wetlands to N
| FLNRO_2 | FLNRO | permanent deactivation; NSR |  | High suitability disturbed by roads | moderate capability along Murphy Lake; in adequate cover | n/a | n/a | n/a | 1.9 | 3.8 | road ripping | M | Looks like forested area before opens to cutblock where deactivation could be effective. | [6 empty] | Low-Moderate | in moderate capability, high suitability moose habitat, small amount of road being removed into a cutblock with adjacent cutblocks and roads that are being kept open...could be more effective if roads in area of 10.629078.5765524 were also deactivated
| WF_11 | FLNRO | permanent deactivation |  | adjacent to suitable habitat disturbed by roads | moderate capability; in adequate cover | n/a | n/a | n/a | 1.5 | 3 | road ripping | M | Looks like a creek crossing could be removed as deactivation point? If not, lower effectiveness as looks like open cutblock | [6 empty] | Moderate | in moderate capability, high suitability moose habitat, small amount of road being removed but into a cutblock surrounded by forested area and wetland complexes;
| WF_12 | FLNRO | permanent deactivation |  | in suitable habitat disturbed by roads | moderate capability on edge of low; lacking adequate cover | n/a | n/a | n/a | 5.2 | 10.4 | road ripping | M | Looks like forested area on both sides of the road | [6 empty] | Low | Another road accesses area beyond the deactivation point and therefore low effectiveness, unless another deactivation point can occur around 10.627165.5767704 Or 10.626599.5768446
| Tolko_1 | FLNRO | permanent deactivation |  | High Suitability not disturbed by roads | moderate capability; within adequate cover | n/a | n/a | n/a | 3.8 | 7.6 | road ripping; WF may have issue with this one - to CONFIRM | M | Looks to be forested area on both sides of the road | [6 empty] | Moderate | in moderate capability, high suitability moose habitat, moderate amount of road deactivated into area with low-moderate other roads
| Tolko_2 | FLNRO | permanent deactivation; outside Murphy WSD |  | High Suitability not disturbed by roads | moderate capability; within adequate cover | 200 ha block removed from access | n/a | n/a | 5.5 plus spur roads | 11 | road ripping; deactivated past this point by Tolko to Tolko 3 | M | Looks to be forested on both sides of the road | [6 empty] | Moderate | in moderate capabilty, high suitability moose habitat, large amount of road deactivated into area that has already seen rehab work and removes a loop road.
| Tolko_3 | FLNRO | permanent deactivation; outside Murphy WSD |  | adjacent to suitable habitat not disturbed by roads | low capability; within adequate cover | "" | n/a | n/a | see Tolko 2 | see Tolko 2 | road ripping; joins Tolko 2; to remove loop road access | M | Looks to be forested on both sides of the road | [6 empty] | Moderate | in low capability, high suitability moose habitat, large amount of road deactivated into area that has already seen rehab work and removes a loop road
| Tolko_4 | FLNRO | permanent deactivation; permit and NSR |  | not high suitability habitat (but surrounded by suitable habitat disturbed by roads) | high capability; within adequate cover | ~5km road permit + ~3km NSR | 8 | 16 | 9.95 | 19.9 | road ripping | M | Looks to be forested on both sides of the road | [6 empty] | Moderate | in high capability moose habitat and runs through modelled suitable habitat, large amount of road deactivated as result of this work Looks to be a road connection/gold rush trail to another set of roads at 10.608622.5771764 - would be more effective if this can be deactivated as well but can't because of snowmobile trail?
| Tolko_5 | FLNRO | permanent deactivation |  | not high suitability habitat (but surrounded by suitable habitat disturbed by roads) | moderate capability, without adjacent cover | n/a | n/a | n/a | 0.6 | 1.2 | road ripping | M | Looks to be forested on both sides of the road | [6 empty] | Moderate | in moderate capability, outside of modelled suitable habitat but surrounded by it; deactivation removes short road into cutblock; leading into wetland complex
| Tolko_6 | FLNRO | permanent; NSR; private land driveway just before this access pt that needs to be left open |  | not high suitability habitat (but surrounded by suitable habitat disturbed by roads) | moderate capability; within adequate cover | n/a | n/a | n/a | 4.4 | 8.8 | road ripping | M | Looks to be forested on both sides of the road | [6 empty] | Moderate | in moderate capability, outside of modelled suitable habitat but surrounded by it; deactivation sits off main road and removes moderate amount of road, including loop road through area and within some wetland complexes
| FLNRO_3 | FLNRO | permanent; NSR |  | into HVMW; suitable habitat disturbed by roads | moderate capability; within adequate cover | n/a | n/a | n/a | 2.3 | 4.6 | road ripping | M | Looks to be forested on both sides of the road | [6 empty] | Moderate | in moderate capability; in suitable habitat leading into high value wetlands for moose; short amount of road removing access into wetland complexes; effectiveness increases in combination with other deactivation in the area
| FLNRO_4 | FLNRO | permanent; NSR; small loop road removed |  | adjacent to wetlands; in suitable habitat disturbed by roads | moderate capability; within adequate cover | n/a | n/a | n/a | 1 | 2 | road ripping | M | Looks to be forested on both sides of the road; plus some wetland areas | [6 empty] | Moderate | in moderate capability; in suitable habitat leading through wetlands that may be important for moose; removes short loop road; effectiveness increases in combination with other deactivation in the area
| FLNRO_5 | FLNRO | permanent; NSR |  | suitable habitat disturbed by roads | moderate capability; within adequate cover | n/a | n/a | n/a | 1.8 | 3.6 | road ripping | M | Looks to be forested on both sides of the road; plus potentially a creek crossing that could assist with deactivation | [6 empty] | Moderate | in moderate capability; in suitable habitat; removes short amount of road; effectiveness increases in combination with other deactivation in the area
Is there potential to move deactivation point west further to remove more road? | FLNRO_6 | FLNRO | permanent; NSR; loop road |  | suitable habitat undisturbed by roads; | moderate capability; within adequate cover | n/a | n/a | n/a | 3.1 | 6.2 | road ripping | M | Could be forested on both sides of the road (hard to tell from Ortho) | [6 empty] | Moderate | in moderate capability; in suitable habitat; removes a short loop road adjacent to a number of wetlands complexes; effectiveness increases in combination with other deactivation in the area
| Tolko_7 | FLNRO | permanent deactivation; adjacent to private land (Tolko_6) think they don't use this access route - Tolko will confirm |  | suitable habitat disturbed by roads; road leads into wetland complexes | moderate capability; within adequate cover | n/a | n/a | n/a | 0.8 | 1.6 | road ripping | L | Looks to be open area where ATV/vehicle could drive around deactivation point? | [6 empty] | Low | In moderate capability; in suitable habitat disturbed by roads; into wetland complex area; short amount of road into cutblock removed; however looks like there is another access into this area from the east? Is there potential to deactivate around 10.614278.5773567?
| FLNRO_7 | FLNRO | small inblock; permanent NSR; WF permit is recent but deactivation probably OK |  | suitable habitat disturbed by roads; | moderate capability; within adequate cover | n/a | n/a | n/a | 2.4 | 4.8 | road ripping | L | Looks to be open area where ATV/vehicle could drive around deactivation point? | [6 empty] | Moderate | In moderate capability; in suitable habitat disturbed by roads; short amount of road into cutblock removed in area with significant number of other roads; effectiveness increases in combination with other deactivation in the area
verify location of deactivation - on main road or in-block road? Area affected is based on in-block road | FLNRO_8 | FLNRO | small inblock; permanent NSR; Esketmc permit |  | suitable habitat disturbed by roads; | moderate capability; within adequate cover | n/a | n/a | n/a | 2.5 | 5 | road ripping | M | Looks to be forested on both sides of the road | [6 empty] | Moderate | In moderate capability; in suitable habitat disturbed by roads; short amount of road into cutblock removed in area with significant number of other roads; effectiveness increases in combination with other deactivation in the area
| FLNRO_9 | FLNRO | block end of road into # of small in-blocks |  | suitable habitat disturbed by roads | moderate capability; within adequate cover | n/a | n/a | n/a | 1.8 | 3.6 | road ripping | M | Looks to be forested area as well as potential creeks to aid with deactivation | [6 empty] | Moderate | in moderate capabilty; in suitable habitat disturbed by roads; short amount of road into cutblocks at the end of a road creating ~13000ha of unroaded forested area
| FLNRO_10 | FLNRO | block into in-block road |  | suitable habitat undisturbed by roads; | moderate capability; within adequate cover | n/a | n/a | n/a | 1.7 | 3.4 | road ripping | L | Looks to be open area where ATV/vehicle could drive around deactivation point? | [6 empty] | Moderate | in moderate capability; in suitable habitat undisturbed by roads; short amount of road into a cutblock at the end of a road; with other deactivation in this area, increases effectiveness of the area which has good forested areas, lacking wetlands
This one missing from Attribute table - confirm with licensees if needed or already covered by another point | FLNRO_11 | FLNRO | temporary blocks to remove loop road |  |  | suitable; in moderate capability | [5 empty] | road ripping
| WF_13 | FLNRO | recent WF (last years pass) but should be ok to deactivate |  | suitable habitat disturbed by roads | moderate capability; within adequate cover | n/a | n/a | n/a | 1 | 2 | road ripping | M | Looks to be forested area on both sides of the road | [6 empty] | Moderate | in moderate capability; in suitable habitat disturbed by roads with adjacent wetlands; short amount of NEW road being deactivated; in area with number of other roads, however other deactivation efforts will assist with rehab of the area
| FLNRO_12 | FLNRO | closing off a loop road; remove section of road to prevent access through loop |  | suitable habitat disturbed by roads; edging onto undisturbed suitable | moderate capability; within adequate cover | in WTP forest | n/a | n/a | 0 | 0 | road ripping | M | Looks to be forested area on both sides of the road | [6 empty] | Low-Moderate | removes a loop road through moderate capability; suitable habitat disturbed by roads; however stretch of road through habitat still open - could further deactivation occur around 10.613395.5764661 which would remove another 1km of road?
| Tolko_8 |  | recent Tolko harvest with more potential behind; consider leaving for now and fully rehab in a year or two |  | suitable habitat undisturbed by roads; | moderate capability; within adequate cover | n/a | n/a | n/a | 3 | 6 | road ripping | M | Looks to be forested area on both sides of the road | [6 empty] | Moderate (IN A COUPLE YEARS) | in moderate capability; in suitable habitat disturbed by roads with adjacent wetlands; could remove up to 3 km of road if full loop is deactivated by Tolko in couple years and in combination with other efforts in this area
| Tolko_9 |  | temporary blocks until harvest complete |  | suitable habitat disturbed by roads | moderate capability; within adequate cover | n/a | n/a | n/a | 4.5 | 9 | pyramid blocks | L | temporary; looks to be open area where ATV/vehicle could drive around blocks? | [6 empty] | Low | temporary measures for now until harvesting completed, then would be a high option as removes a loop road of ~5km into moderate capability, suitable habitat around wetland complex
Missing from Attribute table | WF_17 |  |  |  |  | suitable; 3 blockages prevent access into core area | [5 empty] | road ripping
Missing from Attribute table | WF_18
Missing from Attribute table | WF_19
| WF_14 |  | permanent deactivation |  | suitable habitat undisturbed by roads | moderate capability; with adequate cover | n/a | n/a | n/a | 3.4 | 6.8 | road ripping | M | Looks to be forested area on both sides of the road | [6 empty] | Moderate | in moderate capability, suitable habitat undisturbed by roads, adjacent to lake with no further roads between this area and lake;
| WF_15 |  | permanent deactivation |  | suitable habitat undisturbed by roads | moderate capability; with adequate cover | in WTP/riparian area | n/a | n/a | 2.5 | 5 | pulling Open bottom arch (bridge) | H | pulling bridge in forested area | [6 empty] | Moderate | in moderate capability, suitable habitat undisturbed by roads, removes ~5km of road into large area of older harvest with some wetland areas
Confirm location of deactivation as currently sits off main loop road, only removing ~2km of road? | WF_16 |  | permanent deactivation - would like to take out a loop road but potentially part of loop already deactivated - depending on mining activity; need to confirm |  | suitable habitat running through both disturbed and undisturbed by roads | moderate capability; with adequate cover |  | n/a | n/a | 2 | 4 | road ripping | M | Looks to be forested area on both sides of the road | [6 empty] | Moderate | Currently looks to remove ~2km of road through moderate capability, suitable habitat running north to Spout Lake into wetland area with limited other roads; however effectiveness of area could be increased if loop road is removed as discussed at meeting - confirm.
| FLNRO_13 |  | permanent deactivation |  | suitable habitat running through both disturbed and undisturbed by roads | moderate capability; with adequate cover |  | n/a | n/a | 1.3 | 2.6 | road ripping | L | Looks to be open area where ATV/vehicle could drive around deactivation point? | [6 empty] | Moderate | in moderate capability, suitable habitat leading into cutblock with adjacent wetlands and limited roads behind the access point; other efforts in this area increase effectiveness
| FLNRO_14 |  | permanent deactivation |  | suitable habitat disturbed by roads | moderate capability; with adequate cover |  | n/a | n/a | 1.1 | 2.2 | road ripping | M | Looks to be forested area on both sides of the road | [6 empty] | Moderate | in moderate capability, suitable habitat leading into cutblock with adjacent wetlands and limited roads behind the access point; other efforts in this area increase effectiveness
| FLNRO_15 |  |  |  | suitable habitat disturbed by roads | moderate capability; with adequate cover
| FLNRO_16 |  |  |  | suitable habitat disturbed by roads | moderate capability; without adequate cover
| FLNRO_17 |  |  |  | not suitable habitat, adjacent to suitable undisturbed by roads | moderate capability; without adequate cover
| FLNRO_18 |  |  |  | not suitable habitat, adjacent to suitable undisturbed by roads | moderate capability; without adequate cover
| FLNRO_19 |  |  |  | suitable habitat undisturbed by roads | moderate capability (edge of high); within adequate cover
| FLNRO_20 |  |  |  | suitable habitat disturbed by roads | moderate capability; within adequate cover
| FLNRO_21 |  |  |  | suitable habitat disturbed by roads | moderate capability; within adequate cover
| FLNRO_22 |  |  |  | suitable habitat disturbed by roads | moderate capability; within adequate cover
| FLNRO_23 |  |  |  | not suitable habitat, adjacent to suitable disturbed by roads | moderate capability; within adequate cover
| FLNRO_24 |  |  |  | suitable habitat disturbed by roads | moderate capability; within adequate cover
| FLNRO_25 |  |  |  | suitable habitat disturbed by roads | moderate capability; within adequate cover
| FLNRO_26 |  |  |  | suitable habitat disturbed by roads | moderate capability; within adequate cover
| FLNRO_27 |  |  |  | suitable habitat disturbed by roads | moderate capability; within adequate cover
| FLNRO_28 |  |  |  | suitable habitat disturbed by roads | moderate capability; without adequate cover
| FLNRO_29 |  |  |  | not suitable habitat, adjacent to suitable disturbed by roads | moderate capability; without adequate cover
| FLNRO_30 |  |  |  | suitable habitat disturbed by roads | moderate capability; without adequate cover
| FLNRO_31 |  |  |  | suitable habitat disturbed by roads; some wetlands in the area | low capability; without adequate cover
| FLNRO_32 |  |  |  | suitable habitat undisturbed by roads | low capability; without adequate cover
| FLNRO_33 |  |  |  | suitable habitat undisturbed by roads; adjacent to wetlands | moderate capability; within adequate cover
| FLNRO_34 |  |  |  | suitable habitat disturbed by roads | high capability; within adequate cover
| FLNRO_35 |  |  |  | suitable habitat undisturbed by roads | moderate capability; within adequate cover
| FLNRO_36 |  |  |  | suitable habitat disturbed by roads; north of small lake | high capability; within adequate cover
| FLNRO_37 |  |  |  | suitable habitat disturbed by roads; north of small lake | high capability; within adequate cover
| FLNRO_38 |  |  |  | suitable habitat disturbed by roads; close to HVMW | moderate capability (edge of high); within adequate cover
| FLNRO_39 |  |  |  | suitable habitat disturbed by roads; close to HVMW | moderate capability (edge of high); within adequate cover
| FLNRO_40 |  |  |  | not suitable habitat, adjacent to suitable disturbed by roads | moderate capability; within adequate cover
| FLNRO_41 |  |  |  | suitable habitat undisturbed by roads | moderate capability; without adequate cover
| FLNRO_42 |  |  |  | suitable habitat undisturbed by roads | moderate capability; within adequate cover
| FLNRO_43 |  |  |  | suitable habitat disturbed by roads | moderate capability; within adequate cover
| FLNRO_44 |  |  |  | suitable habitat disturbed by roads | moderate capability; within adequate cover
| FLNRO_45 |  |  |  | suitable habitat disturbed by roads | moderate capability; within adequate cover
| FLNRO_46 |  |  |  | suitable habitat disturbed by roads; adjacent wetlands | moderate capability; without adequate cover
| FLNRO_47 |  |  |  | suitable habitat disturbed by roads; adjacent wetlands | moderate capability; without adequate cover
| FLNRO_48 |  |  |  | not suitable habitat, adjacent to suitable disturbed by roads | moderate capability; without adequate cover (adjacent to cover)
| FLNRO_49 |  |  |  | suitable habitat disturbed by roads | moderate capability; without adequate cover
| FLNRO_50 |  |  |  | suitable habitat undisturbed by roads | moderate capability; without adequate cover
| FLNRO_51 |  |  |  | suitable habitat undisturbed by roads | moderate capability; within adequate cover
| FLNRO_52 |  |  |  | suitable habitat undisturbed by roads | moderate capability; without adequate cover
| FLNRO_53 |  |  |  | edge of suitable undisturbed by roads | high capability; within adequate cover
| FLNRO_54 |  |  |  | edge of suitable undisturbed by roads; leads into wetland | high capability; without adequate cover
| FLNRO_55 |  |  |  | not suitable habitat, adjacent to suitable undisturbed by roads | high capability; without adequate cover
| FLNRO_56 |  |  |  | edge of suitable undisturbed by roads | high capability; within adequate cover
| FLNRO_57 |  |  |  | edge of suitable undisturbed by roads | high capability; within adequate cover
| FLNRO_58 |  |  |  | suitable disturbed by roads (edge of undisturbed); adjacent to HVMW | moderate capability; within adequate cover
| FLNRO_59 |  |  |  | suitable disturbed by roads (edge of undisturbed) | high capability; within adequate cover
| FLNRO_60 |  |  |  | suitable undisturbed by roads | moderate capability; within adequate cover
| FLNRO_61 |  |  |  | suitable undisturbed by roads | moderate capability; within adequate cover
| FLNRO_62 |  |  |  | suitable undisturbed by roads | moderate capability; within adequate cover
| FLNRO_63 |  |  |  | suitable disturbed by roads | moderate capability; within adequate cover
| FLNRO_64 |  |  |  | suitable disturbed by roads | moderate capability; within adequate cover
| FLNRO_65 |  |  |  | suitable disturbed by roads; adjacent to wetlands | high capability; within adequate cover
| FLNRO_66 |  |  |  | not suitable habitat (surrounded by suitable); leads into wetlands | moderate capability; without adequate cover
| FLNRO_67 |  |  |  | suitable disturbed by roads; leads into wetlands | moderate capability; without adequate cover
| FLNRO_68 |  |  |  | suitable disturbed by roads | moderate capability; without adequate cover
| FLNRO_69 |  |  |  | not suitable habitat (surrounded by suitable) | high capability; without adequate cover
| FLNRO_70 |  |  |  | not suitable habitat (surrounded by suitable) | high capability; without adequate cover
Note on B41: Cheryl Williston: linked to a current proposed CP25 and proposed access mgmt as part of the permit?? Does this fall under this funding?
Note on M41: Cheryl Williston: what is proposed as this is linked with current CP?
Note on B46: Cheryl Williston: Just south of Spout Lake; issues with loop road plus mining NOW and road creations
Note on K46: cwillist: Need to confirm location of deactivation, could be more road.

## Sheet2
Tolko Comments
no new planning in this area; just silviculture
some gates that could be used to address loop roads
Moffat area to the north that could have better access mgmt in place
Kane - prefer to not do gates - exclusive access
pyramid blocks - pretty effect unless someone really wants them out and lives close by; dig into ground
used to block roads that access will be needed again; good on bridges

## Sheet3
0.25
0.4
1.4
0.3
0.3
0.25
0.37
0.3
1.2
0.1
0.3
0.8
1.1
0.3
0.5
7.87