Meeting Notes								July 7, 2021

MLIB: Brian Toth (Absent: Lisa Krebs, Adele Chingee, Stephanie Rocheleau)

BC: Bryan Williams, Heather Wiebe, Ryan Bichon, Loni Arman (Absent: Russ Laroche, Darcy Peel, Janet Hughes)

ECCC: Jaspal Aulakh, Renée Lapointe, Robin Steenweg (Absent: Ian Parnell)

Action Review: Completed – see action log for ongoing actions.

Action

| Apr. 14-May 12 | BC to respond to IMA, funding work plan, G2G (not being the mechanism BC wants for agreement) and Sec 11 – 7.2 MOU. - Bryan will provide letter prior to May 26th - - Look at March 26 work plan funding submission for components for the 7.2 MOU - June 23rd – Letter being completed, there will be a formal response from the Minister to address Chief Chingee’ s June 15th letter, email from ED Laroche responding to Chief Chingee’s concern in the June 15th letter regarding MLIB topic on PA agenda. - Update | Bryan W |
| --- | --- | --- |
| May 12 | Funding for “Hire a Tech” BC needs to step back and understand further – Loni to talk with COLT and Science Leads. Understand the difference - More discussions required - Currently have partial funding through KS feeding and DNA analysis projects (1 technician 3 days a week for 3 months) – will discuss during Agenda item 3. Doug - What is confusing is that we would like 1 or more MLIB assistants to work on multiple projects. With funding from the physiological effects project and the supplemental feeding projects, we can afford 1 technician 3 days a week for 3 months to help with both projects (do the feeding and help the student collect physiological samples). We have more work for that person (or 2) if we could afford to hire them (e.g., more days per week and more weeks). | BC |
| May 12 | Estimated costs for Ethnographers 41,000 - Lisa will provide exact figure. | Lisa |
| May 12 | All parties need to review draft IMA and all comments/emails from previous group - BC Complete | All |
| June 23 | Park Boundary expansion – Bryan to connect with Parks to understand why consultation was at notification and where they are in the approval process. - MLIB/BC meeting occurred on June 24th - Meetings have occurred next meeting on July 23rd. | Bryan W |
| June 23 | BC to draft a MOU (term sheet) ID headers, parameters, roles, and responsibilities – other provisions to be worked on together - Will be ready for discussion for July 21st meeting | BC (Bryan W) |
| June 23 | MLIB to have an internal discussion on restoration – ID priority herds, MLIB’s capacity, how to be involved in work (writing prescriptions, ground truthing, actual on the ground work) | Lisa/Brian |
| July 7 | Loni to insert extra 50,000 into spreadsheet. |  |
| July 7 | Brian to look into if MLIB has applied for funding from the Federal Gov for habitat restoration and conservation |  |

Funding Update: Heather

- Looking to have all funding aligned to get our letters out. Need a dollar figure for our projects. BC has an additional $50,000 – this could be used to cover off LUP or additional funding for ethno or any combo that makes sense to MLIB.

- Always opportunities for funding later in year for additional work.

- We don’t have mandate to start LUP process for Parsnip specifically. But being able  to outline MLIB interests would be a good start. These interests could be an input into other tables (ESI/herd planning/PA etc).

- Herd Planning for Hart Ranges will be in Fall.

Update on WI work: Brian T.

- Nothing quite complete due to DISA.

- Built for KS and Hart North and would likely extend to other herds that aren’t being addressed under other initiatives.

- Largely GIS so shouldn’t be difficult to get other herds done.

- Looking at near term permitted activities, designing maps to show these activities

- Understanding of current state

- Provide long term perspective on habitat tools

- Brian completed a table:

- Once complete use outputs as a LUP input - understanding habitat and pressures. This would give tools to use into other land use consideration process

Forestry Referrals (CE/LUP): Brian T.

- Lisa and Brian now tied to MLIB forestry referral process. Using consultation to help Scott scope out his process.

- Have a tool to keep all consultation from info shares that creates a live instrument as a part of caribou recovery and includes MLIB interests. Info stays up to date.

- Ryan proposed FRPA changes (forest operations map) FOM is part of this where all info from all licensees will be available online.

- Dashboard map -would be good to get good imagery for this such as Blackstone.

Federal 2 Billion Tree Program: Renee/Robin

- Presentation (provided)

- Gives program overview and goal

- Goal solutions to fight climate change – carbon sequestration as a goal.

- Program shared amongst 3 programs NRCAN, ECCC and AAFC – see slide

- Number of presentations that have been held on these topics during COVID

- IF interest in hearing more let Renee know

- Program secured for 5 yrs but looking for 10 yrs

- Focus on incremental tree planting – not talking about where licensees already have to replant

- Has MLIB applied for funding through this for habitat restoration and conservation? Brian to find out

- Canada is going to hire a Bio for this in the Pacific region

- Contact: nrcan.2btrees-2garbres.rncan@canada.ca

Restoration for Central Group: All

- Need info on central group on what have been developed for prescriptions.

- Brian and Nadia to have a meeting on this.

Closing: Heather:

Next steps: Been valuable to split apart discussions. Projects feel like we have a clear path we will transfer funds. What should we do for summer schedule for this?

Reserve spot for 4 weeks from now and if we don’t need it then cancel.