Meeting Notes							July 21, 2021

MLIB: Lisa Krebs,  Brian Toth (Absent: Adele Chingee, Stephanie Rocheleau)

BC: Heather Wiebe, Ryan Bichon, Loni Arman (Absent: Bryan Williams, Russ Laroche, Darcy Peel, Janet Hughes)

ECCC: Jaspal Aulakh, Renée Lapointe (Absent: Ian Parnell)

Action Review: Completed – see action log for ongoing actions.

- Welcome- Heather

- Action Review – Loni

- MOU Term Sheet  – Bryan to present - Discussion

- Meeting Frequency/Length – Heather to lead Discussion

Break ~ 10 min

- Upcoming Predator Control Engagement/Consultation – Heather/Loni

Action Review

| Apr. 14-May 12 | BC to respond to IMA, funding work plan, G2G (not being the mechanism BC wants for agreement) and Sec 11 – 7.2 MOU. - Bryan will provide letter prior to May 26th - - Look at March 26 work plan funding submission for components for the 7.2 MOU - June 23rd – Letter being completed, there will be a formal response from the Minister to address Chief Chingee’ s June 15th letter, email from ED Laroche responding to Chief Chingee’s concern in the June 15th letter regarding MLIB topic on PA agenda. - Update | Bryan W |
| --- | --- | --- |
| June 23 | Park Boundary expansion – Bryan to connect with Parks to understand why consultation was at notification and where they are in the approval process. - MLIB/BC meeting occurred on June 24th - Meetings have occurred next meeting on July 23rd. | Bryan W |
| June 23 | BC to draft a MOU (term sheet) ID headers, parameters, roles, and responsibilities – other provisions to be worked on together - Will be ready for discussion for July 21st meeting | BC (Bryan W) |
| June 23 | MLIB to have an internal discussion on restoration – ID priority herds, MLIB’s capacity, how to be involved in work (writing prescriptions, ground truthing, actual on the ground work) | Lisa/Brian |

MOU Term Sheet: Heather

- D

Meeting Frequency

- H

Predator Control

- D