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PART 1.0

RESOURCE MANAGEMENT PLAN: OVERALL SUMMARY

1.1 BACKGROUND

Forest Renewal BC was created in 1994 to aid in directing and managing an array of investments designed to renew British Columbia’s forests and forest economy. To this end Forest Renewal BC was mandated to: 

plan and implement a program of investments to renew the forest economy of British Columbia by enhancing the productive capacity and environmental values of forest lands, and by creating jobs, providing training for forest workers, and strengthening local communities that depend on the forest industry.

To achieve this mandate Forest Renewal BC established seven strategic objectives (SO’s):

1. Sustainable Harvest (SH)

Invest in the production of faster-growing, higher-quality stands of second-growth timber.

2. Enhance Environmental Values (EEV)

Invest in restoring forest watersheds and in promoting environmental stewardship and strong environmental values in BC’s forests.

3. Strengthen Sustainable Forest Management (SSFM)

Invest in the development of relevant, useable, timely information and tools keyed to achieving sustainable forest management.

4. Strengthen and Expand the Value-added Sector

Strengthen and expand BC’s value-added sector through strategic investments with leading industry partners. 

5. Stimulate Workforce Development to Strengthen the Forest Sector

Provide re-employment services to long-term forest-sector workers who are facing permanent displacement. 

6. Sustain and Diversify Forest Community Economies

Provide support to forest-dependent communities that are experiencing significant forest-sector job loss, to help them stabilise and diversify their forest economies and to increase First Nations participation in the forest sector. 

7. Increase Forest Renewal BC’s Effectiveness and Efficiency

Increase effectiveness and efficiency to optimise the impact of investments, while maintaining low administrative costs 

To achieve these SO’s, Forest Renewal BC had to work closely with both the Ministry of Forests (MoF) and the Ministry of Environment, Lands and Parks (MELP)
.

The purpose and functions of the BC Ministry of Forests , as the stewards of British Columbia’s forests, are to:

a) encourage maximum productivity of the forest and range resources in the Province; 

b) manage, protect and conserve the forest and range resources of the Crown, having regard to the immediate and long term economic and social benefits they may confer on the Province; 

c) plan the use of the forest and range resources of the Crown, so that the production of timber and forage, the harvesting of timber, the grazing of livestock and the realisation of fisheries, wildlife, water, outdoor recreation and other natural resource values are co-ordinated and integrated, in consultation and co-operation with other ministries and agencies of the Crown and with the private sector; 

d) encourage a vigorous, efficient and world competitive timber processing industry in the Province; and 

e) assert the financial interest of the Crown in its forest and range resources in a systematic and equitable manner.

The purpose and functions of the Ministry of Environment, Lands and Parks was:

a) to encourage and maintain an optimum quality environment through specific objectives for the management and protection of land, water, air and living resources of British Columbia;

b) to undertake inventories and to plan for and assist in planning, as required, for the effective management, protection and conservation of all water, land, air, plant life and animal life;

c) to manage, protect and conserve all water, land, air, plant life and animal life, having regard to the economic and social benefits they may confer on British Columbia;

d) to set standards for, collect, store, retrieve, analyse and make available environmental data;

e) to monitor environmental conditions of specific developments and to assess and report to the minister on general environmental conditions in British Columbia;

f) to undertake, commission and co-ordinate environmental studies;

g) to develop and sustain public information and education programs to enhance public appreciation of the environment;

h) to plan for, design, construct, operate and maintain structures necessary for the administration of this Act or for another purpose or function assigned by the Lieutenant Governor in Council;

i) to plan for, co-ordinate, implement and manage a program to protect the welfare of the public in the event of an environmental emergency or disaster.

(Please note that the responsibilities of MELP and MOF have now changed. On June 5, 2001 Order in Council (OIC) 565 rescinded MELP as a Ministry and renamed it the Ministry of Sustainable Resource Management (MSRM). The same OIC also created the Ministry of Water, Land and Air Protection (MWLAP). Some former responsibilities of MOF were also placed within MSRM.)

When the mandates of all three organisations were compared, it became apparent that there was significant overlap between them. These overlaps in mandates required that all three parties work together in order for Forest Renewal BC to realise its first three strategic objectives (SH, EEV and SSFM).

To achieve their SH, EEV and SSFM strategic objectives, Forest Renewal BC established performance targets. These performance targets set tangible goals for each SO.

The SH strategic objective calls for the continuing improvement of immature forests within the Vancouver Forest Region through incremental and backlog silviculture works to achieve a total increased productivity of 710,000 cubic meters of volume in those stands that are treated.

The EEV strategic objective is to complete the restoration of at least 20% of the priority key watersheds by March 2004, with the focus of the program being on the “target” watersheds (the highest 131 priority key watersheds).

The SSFM strategic objective is less tangible, as it deals with areas where a lack of scientific knowledge exists, and where the priorities lie in filling in those knowledge gaps. In general however, the targets for SSFM are:

· By Oct 1, 1999, standard requirements supporting SSFM will be defined for Inventory Information, Environmental Risk Assessment, Decision Tools, and monitoring for Timber Supply Reviews (TSR’s) and Land and Resource Management Plans (LRMP’s). 

· By April 1, 2000, key gaps will be identified in information requirements for specific TSR's and LRMP's and corporate targets will be set for addressing the gaps. 

· Evidence will show that monitoring information is being used to confirm or modify strategic plans and decisions. 

· Evidence will show that new tools and approaches are being developed in experimental management pilots and considered in strategic processes. 

· Evidence will show that forest management is moving towards sustainability (i.e. meeting eligibility standards for international sustainability certification).

Together, the activities conducted under these three strategic objectives are referred to as the land-based activities. The Resource Management Plan (RMP) concept was created to aid Forest Renewal BC in the realisation of their strategic objectives through the achievement of their performance targets. This is done by providing definitive, timely data regarding the best land-based activities to conduct in various areas of the region to maximise returns on investment.

1.2 STRATEGY AT A GLANCE

Overview:

The Resource Management Plan (RMP) addresses land-based activities from the perspective of biological needs and forest resource management priorities. The plan forms a compendium of priorities determined by BC Ministry of Forests (MOF), BC Ministry of Sustainable Resource Management (MSRM), ), BC Ministry of Water, Land, and Air Protection (MWLAP), major licensees, woodlot licensees, and other stakeholders. The RMP is designed to provide guidance to all agencies within the forest sector in British Columbia to determine the best activities for investment regardless of the funding source or the agency actually completing the work.

The 2002/2003 RMP expands and improves upon previous Resource Management Plans. Over the course of Forest Renewal BC’s existence funding for various activities and programs has changed. Much of what was previously eligible for Forest Renewal BC funding is no longer eligible. This RMP presents priority opportunities for those programs and activities that remain eligible for Forest Renewal BC funding.

It is also important to link and describe how the RMP links to the present Provincial Government’s New Era Document, which specifies the government’s commitments for the management of British Columbia’s forest land. The RMP supports the New Era Document as follows:

1. Working Forest – A Working Forest is a defined area or portion of the land base that is dedicated primarily to forest harvesting. The RMP addresses this commitment through repeated reference to the Working Forest, specifically within each of the applicable nine Strategic SSFM Goals, as well as a specific discussion in the text of the RMP.

2. Strategic Land Use Plans – The government has made it a high priority to complete strategic-level plans such as Land and Resource Management Plans and Landscape Unit Plans within the next 2 years. Completion of these plans will zone the land base into different areas of management activity and should bring more certainty to resource management decisions. The completion of Strategic Land Use Plans is very closely linked to the implementation of a Working Forest. Once these Strategic Plans are completed the Working Forest can be clearly defined while ensuring other non-timber and environmental resource values are being adequately managed for across the Regional land base

The support of and completion of Strategic Land Use Plans is a priority objective of the RMP planning process.

3. Improve Access to World Markets – Many concerns surround access of British Columbia forest products to world markets. One major issue is the need for consumers to ensure that forest products they purchase are obtained from forests that are sustainably managed. The most common way to ensure this is independent third party verification commonly referred to as Certification. Obtaining acceptable Certification is very important to maintaining the economic, social and environmental needs of British Columbians.

This RMP contributes in many ways to the achievement of Forest Certification. By demonstrating a thorough and ongoing prioritised effort to reforest, rehabilitate, and manage the forests and forest lands of the Pacific Region for all forest and non-forest attributes, along with a continued effort to improve the knowledge base to address the priority issues that most greatly affect the management of these forests, the RMP plays a key role in helping move this region and its players forward towards Certification.

4. Maintain Environmental Values – There is strong concern among the citizens of BC regarding the maintenance or improvement of environment values. British Columbia’s forests provide not only timber products, but also other essential resources such as wildlife, fisheries, biodiversity, etc. The RMP helps to address these concerns by providing a prioritised list of the best investments within the region to address the ongoing concerns and issues of site and stream rehabilitation and key species management (fish, wildlife, and timber and non-timber plant species). By providing this information to the various levels of decision-makers, the RMP provides these managers with the information they need to make sound decisions regarding which high priority issues and works should be funded so that the investments will yield the greatest results in the areas of greatest concern. The RMP also ensures that the products produced from the investment of financial resources will be structured on a foundation of scientifically based information and principles.
5. Living Rivers Strategy – This initiative is supported by the RMP in several areas. These include various activities related to Watershed Restoration as well as Resource Inventories, Fish and Fish Habitat, Water Quality and Quantity, Species at Risk, and more. By recommending priority investments in these activities and strategic goals, there is a high probability this initiative will be successful.

6. Reduce the Regulatory Burden – By moving from an administratively prescriptive approach of regulatory enforcement to a more results-based approach there is strong potential to reduce excess regulation. The RMP supports this initiative by providing recommendations for investments in activities and knowledge gap research that are based upon sound scientific analysis. By providing these recommendations, the RMP directs the investments within the region towards works already known to provide the greatest returns, thereby reducing the need for a regulatory approach to investment decision-making.
General Strategy:

The Resource Management Plan for the Pacific Region examines land-based resource needs and priorities in terms of:

· Commitments, recommendations, and links to other land and resource management plans.

· The long-term resource implications of current investments.

· The value, risks, and benefits of the various activities and treatments.

· The necessary timelines to meet defined resource management objectives.

· Delivery recommendations, viable options, and consequences of not carrying out the activity.

· Consistency within programs and between delivery centres.

· Providing resource investment recommendations consistent with Forest Renewal BC investment principles and ground rules.

a) Sustainable Harvest

(1) Objectives:

· Increase the volume, economic value, and health of second-growth forests

· Increase the amount of land available for commercial timber production; and

· Support more informed silviculture investment decisions.
(2) Strategies:

· Develop a prioritised list of incremental silviculture opportunities in the region.

· Recommend a strategy to implement activities that would yield the highest possible returns per dollar invested on the forested land base.

(3) Activities:

The eligible activities under SH are:

· Backlog:

Backlog activities are designed to bring stands that were harvested, damaged, or destroyed before October 1, 1987 and presently insufficiently stocked, back into production.

· Impeded:

Activities on impeded areas are designed to bring stands that were harvested, damaged, or destroyed before October 1, 1987 and presently sufficiently stocked but impeded by brush, to the free growing stage.

· Enhanced Forestry:

Enhanced forestry activities treat free growing stands to enhance their value, volume, biodiversity, habitat supply, and/or health.

(4) Management units:

All

b) Enhancing Environmental Values

(1) Objective

To speed the recovery of fish habitat and water quality in priority key watersheds that have been damaged or are seriously threatened by forest development activities.

(2) Strategies

· Focus on the resource values of water quality and fish habitat.

· Identify priority key watersheds to guide program expenditures.

· Maintain an integrated approach towards restoration (i.e. deal collectively with hill slope, riparian and in-stream components).

· Encourage cost sharing with other agencies in order to maximise investment and ensure co-ordination.

· Increase accountability and improve monitoring and effectiveness evaluation.

(3) Watersheds

In the 2001-2002 RMP, the Ministry of Environment, Lands and Parks identified 543 watersheds within the Pacific Region. This most recent RMP adds two more watersheds to the list: Johnstone Straight and Queen Charlotte Straight. Of these 545 watersheds, 130 have been identified as being eligible for Forest Renewal BC investment.

c) Strengthening Sustainable Forest Management

(1) Objectives:
· Satisfy needs for timber fibre and non-timber forest products in perpetuity.

· Conserve soil and water.

· Sustain the resilience and renewal capacity of forests.

· Support the food security and livelihood needs of forest-dependant communities.

· Conserve biological diversity.

· Provide a more equitable sharing of the benefits from forest uses.

(2) Strategy:
Direct investments toward areas where increased knowledge will strengthen the existing strategic level decisions and plans used to meet the principles of sustainable forest management.

(3) Information Gaps
The highest priority issues that represented knowledge gaps in the Vancouver Forest Region were identified as:

· Unreliable or incomplete resource inventories on the land base.

· Lack of species at risk management strategies and objectives.

· The opportunities and impacts of alternate harvesting systems.

· Lack of fish and fish habitat management strategies and objectives.

· Lack of regional biodiversity management guidelines.

· Lack of ungulate habitat management strategies, objectives, and guidelines.

· Need to strengthen forest modelling.

· Lack of regional water quality and quantity management strategies and objectives.

· Unreliable or incomplete cultural heritage resource inventories.

(4) Management Units:
The SSFM component encompasses all planning units.

1.3 INTRODUCTION:

This Resource Management Plan consists of 3 key components:

· Sustainable Harvest

· Enhancing Environmental Values

· Supporting Sustainable Forest Management

Each of these components represents a forest resource management program administered by the BC Ministry of Forests, BC Ministry of Sustainable Resource Management, BC Ministry of Water, Land, and Air Protection, or all three. The activities and projects within these components are delivered by various agencies or licensees and thus these agencies and licensees have been integral participants in the compilation of this RMP.

The Vancouver Forest Region consists of 22 management units:

Eight Timber Supply Areas:

· Fraser

· Soo

· Strathcona

· Arrowsmith

· Kingcome

· Sunshine Coast

· Mid-Coast

· Queen Charlotte Islands

and 14 Tree Farm Licenses:

· TFL 26 – District of Mission

· TFL 19 - Western Forest Products Ltd.

· TFL 25 - Western Forest Products Ltd.

· TFL 39 - Weyerhaeuser Canada Ltd.

· TFL 45 - International Forest Products Ltd.

· TFL 47 - TFL Forests Limited

· TFL 6 - Western Forest Products Ltd.

· TFL 10 - International Forest Products Ltd.

· TFL 44 - Weyerhaeuser Canada Ltd.

· TFL 46 - TFL Forests Limited

· TFL 54 - International Forest Products Ltd.

· TFL 57 - Iisaak Forest Resources Limited

· TFL 38 - International Forest Products Ltd.

· TFL 37 - Canadian Forest Products Ltd.

It is the responsibility of the Ministry of Forests (in co-ordination with the MSRM and MWLAP) under the terms of the Services Agreement jointly signed by MOF and Forest Renewal BC, to co-ordinate and produce the RMP. In doing so, the MOF compiled the Guidelines for the Development of Resource Management Plans for 2002 – 2003. These guidelines clarified the requirements of the RMP, what was to be included in the submissions, and what the process and timelines were to bring the RMP together. 

The RMP includes management issues and data from all agencies, licensees, and management units managing or occupying crown forest land within the Vancouver Forest Region. 

1.4 OVERVIEW OF RESOURCE MANAGEMENT ISSUES:

The Timber Supply Review process within the Vancouver Forest Region has resulted in significant reductions in the annual allowable cut in many of the Timber Supply Areas (TSAs). In addition, the presence of “at risk” wildlife species that require special management or no work zones, such as the marbled murrelet, spotted owl, and Vancouver Island marmot, has further eroded the forest land base from which timber may be extracted by conventional means. Combined with the falldown effect now affecting many TSAs, the region is faced with some serious potential wood fibre shortages, both in terms of volume and quality. To alleviate this the Sustainable Harvest portion of this RMP concentrates efforts on bringing backlog areas to free growing and enhancing the rate and quality of fibre production through the application of activities such as juvenile spacing, pruning, and fertilisation

Research efforts within this region, while covering a wide array of potential subjects, concentrate on investigating and assessing methods and treatments having potential to aid in addressing the issues stated above.

1.5 REGIONAL SUMMARIES of the RMP Component Data:

1.5.1 Sustainable Harvest Component:

1.5.1.1 Regional Rollup Enhanced Forestry Table

Vancouver Forest Region Sum of Districts (TSAs & TFLs)











Enhanced Forestry Table











For the 2002/03 Fiscal Year



































Activities

Treatment Area Goals (ha)




 
Plan 2002/03





2002/
2003/
2004/
2005/
2006/

Unit Cost
Funding 
Priority

Stand Tending

2003
2004
2005
2006
2007

($/ha)
($)


Surveys

32785 
29487 
29291 
27828 
28745 

37.57
1231852 


Spacing

4809 
4703 
4842 
4641 
4741 

1784.78
8583011 


Pruning

3011 
2370 
2296 
2253 
2138 

2271.01
6838500 


Fertilizing

16927 
14997 
16097 
13397 
15447 

352.91
5973500 


Other 

103 
153 
153 
153 
153 

1511.77
155000 



Totals hectares
57634 
51709 
52679 
48272 
51224 

395.28
22,781,863 


Planning and prescriptions 








572,700 



Total dollars







23,354,563 














Forest Health Enhancement











Spacing

90 
90 
80 
80 
80 

1,755.03 
158000 


Pruning

155 
155 
155 
155 
155 

1,858.41 
288100 


Other treatments

990 
690 
690 
690 
690 

150.25 
148750 



Totals hectares
1235 
935 
925 
925 
925 

481.63 
594,850 


























Habitat Supply and Biodiversity Enhancement











Riparian treatments

587 
465 
387 
380 
370 

2,902.48 
1703800 


Non-riparian treatments

205 
420 
625 
620 
620 

3,150.84 
646000 



Totals hectares
792 
885 
1012 
1000 
990 

2,966.77 
2,349,800 


























Domestic Range











Treatments

0 
0 
0 
0 
0 

#DIV/0!
0 














Enhanced Forestry Activities - Management Unit Total











Surveys

32785 
29487 
29291 
27828 
28745 

37.57 
1,231,852 


Spacing

4899 
4793 
4922 
4721 
4821 

1,784.23 
8,741,011 


Pruning

3166 
2525 
2451 
2408 
2293 

2,250.81 
7,126,600 


Fertilizing

16927 
14,997 
16,097 
13,397 
15,447 

352.91 
5,973,500 


Other stand tending activities

1885 
1728 
1855 
1843 
1833 

1,408.03 
2653550 



Totals hectares
59661 
51801 
52761 
48354 
51306 

431.21 
25,726,513 


Planning and prescriptions








572,700 


Studies funding








249600 



Total dollars







26,548,813 


1.5.1.2 Regional Rollup Backlog Program Table


Vancouver Forest Region Sum of Districts (TSAs & TFLs)












Backlog Program Table












For the 2002/03 Fiscal Year






































Activities

Treatment Area Goals (ha)




 
Plan 2002/03






2002/
2003/
2004/
2005/
2006/

Unit Cost
Funding 
Priority


Legal Obligations 

2003
2004
2005
2006
2007

($/ha)
($)



Surveys

1298 
1070 
815 
578 
610 

41.06 
53276 



Site preparation

40 
25 
5 
5 
5 

1,648.76 
66000 



Planting

279 
170 
65 
65 
65 

1,629.64 
454710 



Brushing

321 
281 
186 
50 
30 

1,444.82 
463249 



Max. density spacing

0 
0 
0 
0 
0 

0.00 
0 




Totals hectares
1937 
1547 
1071 
698 
710 

535.39 
1,037,235 



Seed purchase

11239 
9122 
6068 
4060 
3960 

0.72 
8100 




Total legal obligations







1,045,335 
















Backlog Reforestation












Surveys

11239 
9122 
6068 
4060 
3960 

34.00 
382170 



Site preparation

25 
100 
0 
0 
0 

699.16 
17500 



Planting

185 
235 
90 
90 
100 

1,360.36 
251695 



Brushing

1400 
1155 
515 
445 
400 

1,177.98 
1649200 




Totals hectares
12849 
10612 
6673 
4595 
4460 

179.05 
2,300,565 



Seed purchase

48090 
36050 
30050 
30050 
30050 

0.70 
33,500 



Prescriptions and planning dollars








103,500 




Total backlog reforestation







2,437,565 
















Impeded areas












Surveys

11710 
5989 
4040 
4435 
3004 

36.58 
428350 



Brushing

3162 
2290 
1555 
930 
820 

1,187.22 
3754000 



Density spacing

30 
0 
0 
0 
0 

2,497.42 
75000 




Totals hectares
14902 
8279 
5595 
5365 
3824 

285.69 
4,257,350 



Prescriptions and planning dollars








138,075 




Total impeded areas







4,395,425 
















Site Restoration












Fill planting

0 
20 
20 
20 
20 

0.00 
0 



Rehabilitation

66 
70 
60 
50 
50 

1,714.55 
113200 



Reforestation

30 
30 
30 
30 
30 

1,318.99 
39600 




Totals hectares
96 
120 
110 
100 
100 

1,590.41 
152,800 



Seed purchase

24,000 
18,050 
17,020 
17,020 
17,020 

0.70 
16,700 



Prescriptions and planning dollars








6,800 




Total site restoration 







176,300 
















Backlog Program Activities - Management Unit Total












Surveys

24247 
16181 
10923 
9073 
7574 

35.63 
863796 



Site preparation

131 
195 
65 
55 
55 

1,500.58 
196700 



Planting

494 
455 
205 
205 
215 

1,509.83 
746005 



Brushing

4883 
3726 
2256 
1425 
1250 

1,201.49 
5866449 



Density spacing

30 
0 
0 
0 
0 

2,494.76 
75000 




Totals hectares
29785 
20558 
13449 
10758 
9094 

260.13 
7747950 



Seed purchase

83329 
63222 
53138 
51130 
51030 

0.70 
58300 



Prescriptions and planning 








248,375 



Recommended studies








20,000 




Total backlog program







8,074,625 



* Seed purchase includes seedlings purchase. Units are number of seedlings, or specify.











1.5.1.3 Regional Rollup Performance Measures

Vancouver Forest Region Sum of Districts (TSAs & TFLs)

Performance Measures Based on Activities Planned for 2002/2003 based on (Type 1, Type 2 silviculture strategy or specify if other) 















Performance Measure

Tree
Nursery
Silv.
Site
Backlog 
Brush
Space
Prune
Fertilize
Support 
Totals



Improve-
Seedling
Survey
prep.
Plant




staff and




ment
Production







admin



Inputs












A
Planned treatment area (ha) in 2002/2003
494
0
18,820
131
494
4,883
4,929
3,166
16,927
51,729
















1.0
Timber Supply 












1.1
Potential volume/ha gain (m3/ha/yr)
0.41
0
0
0
2.9
0.41
0.25
0
0.46



1.2
Years the factor will apply
0
65
65
65
65
65
65
65
65



1.3
Pot. total merch. volume increment in 65 years (m3)
0
0
0
0
94,422
130,123
80,098
0
507,795

812,438















1.4
Est. yrs reduced to achieve management objectives 
 5-10
1-3
 5-10
0
5-20
5
 5-30
0
 5-10

















1.4
Est. area that will be reclassified as stocked (ha)


0







0

1.5
Est. area that will be declared as free growing (ha)


0







0















2.0
Wood Value












2.1
Percent improvement in total value at harvest 






5-15%
15-30%
1-5%




(Compared to no treatment)


























3.0
Employment












3.1
Estimated short term employment (person days/ha)
0.1
0.34
0.1
0.95
2
2.61
3.96
4.54
0.18
0.1


3.2
Estimated total employment (person days/year)
49
0
1,882
125
988
12,744
19,519
14,375
3,047
5,173


3.3
Estimated total full time equivalent positions (FTE)
0
0
10
1
5
71
108
80
17
29
322















4.1
Forest Health Enhancement (ha)










1,235















5.1
Habitat Supply












5.2
Planned area for specific wildlife forage or habitat maintenance in 2002/2003 (ha)










792

5.3
Est. area with secondary value provided to biodiversity (ha)










0

1.5.1.4 Proposed Studies List for the Vancouver Forest Region

Study/Research
Unit
Agency
$$$$

Mechanical Roadside Fertilization Study 
TFL 46
TFL 
$6,000 year 1
$15,000 yr 2, 3

Fertilization responses of juvenile western hemlock to N, P, S
TFL 39
Weyco
$28,000

Riparian Habitat Overview Assessment Proposal
TFL 47
TFL
$30,000

Low density and habitat development 
TFL 45 DCR
IFP
$15,000

Grizzly Bear Habitat Overview Assessment
TFL 47
TFL
$50,000

Native Grass Seed for Forestry Use
TFL 47
TFL
$18,600

Species Manipulation Trial
TFL 47 
TFL
$5,000
$4000 yr 2, 3


Riparian Habitat Overview Assessment
TFL 47
TFL
$10,000

Ungulate Browse Control Operational Trial
TFL 47
TFL
$7,000 yr 1
$18,000 over 4 yrs

Low density and Habitat development
TFL 45
IFP
$15,000

Examine insect defoliation impacts on Hw in QCI
TFL 39
Weyco
$50,000

Retro-tubing/Fertilization Screening Trials
TFL 39
Weyco
$39,00

Deer Browse Study
TFL 39 
Weyco
$10,000































1.5.1.5 Regional Rollup Summary Table

Vancouver Forest Region Sum of Districts (TSAs & TFLs)










Management Unit Summary Table For the 2002/03 Fiscal Year























Treatment Area Goals (ha)




 
Plan 2002/03




2002/
2003/
2004/
2005/
2006/

Unit Cost
Funding 



2003
2004
2005
2006
2007

($/ha)
($)

Enhanced Forestry Program Field Activities

59,661 
51,801 
52,761 
48,354 
51,306 

431 
25,726,513 


Planning, prescriptions and seedlings







822,300 

Backlog Program Field Activities

29,785 
20,558 
13,449 
10,758 
9,094 

260 
7,747,950 


Planning, prescriptions and seedlings







326,675 


Totals 
89,446 
72,359 
66,210 
59,111 
60,400 


34,623,438 























Performance Measures










Potential total merchentable volume increment in 65 years 





812,438
m3



Estimated ha that will be reclassified as stocked 





0
ha



Estimated ha that will be declared as free growing 





0
ha



Estimated total full time equivalent positions generated





322
FTEs



Forest health enhancement area 





1,235
ha



Planned area for specific wildlife forage or habitat maintenance





792
ha



Estimated area with secondary value provided to biodiversity 





0
ha



1.5.1.6 Regional Woodlots Rollup Enhanced Forestry Table

Vancouver Forest Region Sum of Woodlots for Crown Land











Enhanced Forestry Table











For the 2002/03 Fiscal Year



































Activities

Treatment Area Goals (ha)




 
Plan 2002/03





2002/
2003/
2004/
2005/
2006/

Unit Cost
Funding 
Priority

Stand Tending

2003
2004
2005
2006
2007

($/ha)
($)


Surveys

284
175
198
138


28
7,952


Spacing

187
163
123
76


1349
252,263


Pruning

167
140
82
107


1353
225,951


Fertilizing

222
315
286
229


442
98,124


Other 

0
10
7
7


0




Totals hectares
860
801
696
557



584,290


Planning and prescriptions 








55,171



Total dollars







639,461














Forest Health Enhancement











Spacing

30
5
5
5


1,232
36,960


Pruning

3
5
20
23


1353
4,059


Other treatments

17
3
3
3


1,508
25,636



Totals hectares
50
13
28
31


1,333
66,655


























Habitat Supply and Biodiversity Enhancement











Riparian treatments

31
28
16
20


3,000
93,000


Non-riparian treatments

5
5
5
5


1,100
5,500



Totals hectares
36
33
21
25


2,736
98,500


























Domestic Range











Treatments























Enhanced Forestry Activities - Management Unit Total











Surveys

284
175
198
138


28
7,952


Spacing

217
168
128
81


1333
289,223


Pruning

170
145
102
130


1353
230,010


Fertilizing

222
315
286
229


442
98,124


Other stand tending activities

53
46
31
35


2342
124,136



Totals hectares
945
847
745
613


793
749,445


Planning and prescriptions








55,171


Studies funding








3,300



Total dollars







807,916


1.5.1.7 Regional Woodlots Rollup Backlog Forestry Table

Vancouver Forest Region Sum of Woodlots for Crown Land

Backlog Program Table











For the 2002/03 Fiscal Year



































Activities

Treatment Area Goals (ha)
 
Plan 2002/03



2002/
2003/
2004/
2005/
2006/

Unit Cost
Funding 
Priority

Legal Obligations 
2003
2004
2005
2006
2007

($/ha)
($)


Surveys

25
33
5
100


55
1,375


Site preparation

0
0
0
0






Planting

0
0
0
0






Brushing

6
19
3
2


743
4,458


Max. density spacing

0
0
0
0






Totals hectares
31
52
8
102


188
5,833


number of seedlings needed

0
0
0
0



0



Total legal obligations






5,833














Backlog Reforestation










Surveys

5
20
16
16


37
185


Site preparation

44
33
33
7


1,727
75,988


Planting

41
38
33
10


1,204
49,364


Brushing

40
54
91
170


693
27,720


Totals hectares
130
145
173
203


1,179
153,257


number of seedlings needed

37,150
39,000
32,500
7,400



0


Prescriptions and planning dollars








25,239



Total backlog reforestation






178,496














Impeded areas











Surveys

25
20
0
0


40
1,000


Brushing

10
2
0
0


1,188
11,880


Density spacing

31
0
0
0


2,042
63,302


Totals hectares
66
22
0
0


1,154
76,182


Prescriptions and planning dollars








5,822



Total impeded areas






82,004














Site Restoration










Fill planting

20
0
0
0


1,231
24,620


Rehabilitation

10
6
0
0


2,391
23,910


Reforestation

8
0
0
0


1,719
13,752


Totals hectares
38
6
0
0


1639
62,282


number of seedlings needed

21,200
5,600
0
0






Prescriptions and planning dollars








16,888



Total site restoration 






141,452














Backlog Program Activities - Management Unit Total








Surveys

55
73
21
116


47
2,560


Site preparation

54
39
33
7


1,850
99,898


Planting

69
38
33
10


1,272
87,736


Brushing

56
75
93
172


787
44,058


Density spacing

31
0
0
0


2,042
63,302


Totals hectares
265
225
180
305


1,123
297,554


number of seedlings needed

58,350
44,600
32,500
7,400



0


Prescriptions and planning 








47,949


Recommended studies











Total backlog program






345,503


* Seed purchase includes seedlings purchase.  Units are number of seedlings, or specify.

1.5.1.8 Regional Woodlots Rollup Enhanced Forestry Table for Private Lands

Vancouver Forest Region Sum of Woodlots for Private Land











Enhanced Forestry Table

For the 2002/03 Fiscal Year



































Activities
Treatment Area Goals (ha)
 
Plan 2002/03



2002/
2003/
2004/
2005/
2006/

Unit Cost
Funding
Priority

Stand Tending
2003
2004
2005
2006
2007

($/ha)
($)


Surveys

40
32
30
30


27
1,080


Spacing

25
29
2
0


900
22,500


Pruning

45
45
30
5


1,551
69,795


Fertilizing

25
25
25
25


442
11,050


Other treatments
0
0
0
0






Totals hectares
135
131
87
60


774
104,425


Prescription ($)







9,269


Total dollars







113,694














Forest Health Enhancement









Spacing

5
5
0
0


900
4,500


Pruning

0
5
0
0


0
0


Other treatments
5
4
3
0


1,200
6,000


Totals hectares
10
14
3
3


1,050
10,500


























Habitat Supply and Biodiversity Enhancement







Riparian treatments
2
0
0
0


1,200
2,400


Non-riparian treatments
0
0
0
0



0


Totals hectares
2
0
0
0


1,200
2,400


























Domestic Range










Treatments

0
0
0
0



0














Enhanced Forestry Activities - Management Unit Total






Surveys

40
32
30
30


27
1,080


Spacing

30
34
2
0


900
27,000


Pruning

45
50
30
5


1,551
69,795


Fertilizing

25
25
25
25


442
11,050


Other treatments/ activities
7
4
3
3


1,200
8,400


Totals hectares
147
145
90
63



117,325


Prescription ($)







9,269


Studies funding










Total dollars







126,594














1.5.1.9 Regional Woodlots Rollup Backlog Forestry Table for Private Lands

Vancouver Forest Region Sum of Woodlots for Private Land











Backlog Forestry Table

For the 2002/03 Fiscal Year



































Activities
Treatment Area Goals (ha)
 

Plan 2002/03




2002/
2003/
2004/
2005/
2005/

Unit Cost
Funding 
Priority

Legal Obligations 
2003
2004
2005
2006
2006

($/ha)
($)


Surveys

0
0
0
0






Site preparation

0
0
0
0






Planting

0
0
0
0






Brushing

10
5
0
0


1,200
12,000


Max. density spacing

0
0
0
0






Totals hectares
10
5
0
0


1,200
1,2000


number of seedlings needed

0
0
0
0






Total legal obligations







12,000














Backlog Reforestation










Surveys

10
0
0
0


16
160


Site preparation

22
10
10
10


1,696
37,312


Planting

22
10
10
10


1,435
31,570


Brushing

20
22
30
40


1,200
24,000


Totals hectares
74
42
50
60


1,257
93,042


number of seedlings needed

11,000
10,000
10,000
10,000



0


Prescriptions and planning dollars








9,668


Total backlog reforestation






102,710














Impeded areas










Surveys

0
0
0
0






Brushing

0
0
0
0






Density spacing

0
0
0
0






Totals hectares
0
0
0
0






Prescriptions and planning dollars








1,000


Total impeded areas







1,000














Site Restoration










Fill planting

0
0
0
0
0


0


Rehabilitation

0
0
0
0
0


0


Reforestation

0
0
0
0
0


0


Totals hectares
0
0
0
0
0


0


number of seedlings needed

0
0
0
0
0





Prescriptions and planning dollars








0


Total site restoration 







0














Backlog Program Activities - Management Unit Total






Surveys

10
0
0
0


16
160


Site preparation

22
10
10
10


1,696
37,312


Planting

22
10
10
10


1,435
31,570


Brushing

30
27
30
40


1,200
36,000


Density spacing

0
0
0
0



0


Totals hectares
260
84
47
50


404
105,042


number of seedlings needed

11,000
10,000
10,000
10,000






Prescriptions and planning 








10,668


Recommended studies










Total backlog program







115,710


* Seed purchase includes seedlings purchase.  Units are number of seedlings, or specify.

1.5.2 Enhancing Environmental Values

1.5.2.1 Summary of Regional Priority Watersheds 

Category
Number of Watersheds
% of Total watersheds 

1
129
24

2
1
<1

2B
59
11

3
184
34

4
9
2

5
163
30

Total Number of Watersheds
545
100

Key Watersheds
227
42

Priority Key Watersheds
131
24

Target Watersheds
50
9

Transitional Watersheds
51
9

1.5.3 Strengthening Sustainable Forest Management

1.5.3.1 Regional Priority Goals


LRMP


CCFM


TSR


Success


Stakeholders


Linkage
Policy
Common
Urgency
TOTAL













Resource Inventories
10
5
10
4
5
5
4
5
5
53.0

Species at Risk
9
5
8
5
5
5
3
5
4
49.0

Alternate Harvesting
4
7
10
3
5
4
4
5
5
47.0

Fish Habitat


10
6
4
5
5
5
2
4
3.5
44.5

Biodiversity Guidelines
8
5
5
3
5
3.5
4
4
4
41.5

Ungulate Habitat
4
6
6
4
3.5
4
1
4
3.5
36.0

Strengthen Forest Models
5
4.5
5
3
4
4
4
3
2
34.5

Water Quality and Quantity
4
5.5
1
4
3
3
2
2
3
27.5

Cultural Heritage
3
3
2
4
4
4
0
1
4
25.0













� In the Spring of 2001, the Ministry of Environment, Lands and Parks was abolished and two new ministries were created: the Ministry of Sustainable Resource Management and Ministry of Water, Air, and Land. At the time of the RMP’s drafting, the mandates of these new ministries were still being drafted, however, it is anticipated that the Ministry of Sustainable Resource Management and Ministry of Water, Air, and Land will take on the RMP responsibilities previously held by the Ministry of Environment, Lands and Parks (MELP).
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