## Template (Reg or Dist)
Total Goals for Region
Category | Planned Goals | [5 empty] | Unit Costs | Comments (Estimated MPB / WF) | Category | Planned Funding
Activity | 2012 / 2013 | 2013 / 2014 | 2014 / 2015 | 2015 / 2016 | 2016 / 2017 | Total |  |  | Activity | 2012 / 2013 | 2013 / 2014 | 2014 / 2015 | 2015 / 2016 | 2016 / 2017 | Total $$
Current Reforestation (ha/trees) | [8 empty] | Current Reforestation
Surveys (Backlog NSR ) | 2500 | 2500 | 2500 | 500 | 500 | 8500 | 30 |  | Surveys (Backlog NSR ) | 75000 | 75000 | 75000 | 15000 | 15000 | 255000
Surveys and Overview Planning | [8 empty] | Surveys and Overview Planning | [5 empty] | 0
a) MPB | 5000 | 2500 | 1000 | 1000 | 1000 | 10500 | 55 |  | a) MPB | 275000 | 137500 | 55000 | 55000 | 55000 | 577500
b) Wildfire |  | 5000 | 2000 | 3000 | 0 | 10000 | 55 |  | b) Wildfire | 0 | 275000 | 110000 | 165000 | 0 | 550000
c)Non_Obligation NSR
d) Stand Maintenance SU
Site Preparation | 0 | 0 | 0 | 1500 | 2000 | 3500 | 350 |  | Site Preparation | 0 | 0 | 0 | 525000 | 700000 | 1225000
Brushing | 200 | 200 | 500 | 500 | 500 | 1900 | 762 |  | Brushing | 152400 | 152400 | 381000 | 381000 | 381000 | 1447800
Planting (Trees) | 500000 | 1000000 | 1000000 | 1000000 | 1000000 | 4500000 | 0.57 |  | Planting (Seedlings) | 285000 | 570000 | 570000 | 570000 | 570000 | 2565000
Sowing (Trees) | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 5000000 | 0.21
Timber Supply Mitigation (ha) | [5 empty] | 8300 |  |  | Timber Supply Mitigation
Surveys and Overview Planning | 2500 | 2500 | 2500 | 2500 | 2500 | 12500 | 30 |  | Surveys and Overview Planning | 75000 | 75000 | 75000 | 75000 | 75000 | 375000
Brushing / Cleaning | 0 | 0 | 0 | 0 | 0 | 0 | 800 |  | Brushing / Cleaning | 0 | 0 | 0 | 0 | 0 | 0
Spacing | 500 | 750 | 1000 | 1000 | 1000 | 4250 | 1500 |  | Spacing | 750000 | 1125000 | 1500000 | 1500000 | 1500000 | 6375000
Fertilization | 600 | 600 | 600 | 600 | 600 | 3000 | 220 |  | Fertilization | 132000 | 132000 | 132000 | 132000 | 132000 | 660000
Pruning | [5 empty] | 0 |  |  | Pruning | 0 | 0 | 0 | 0 | 0 | 0
0
Additional Activities | [8 empty] | Additional Activities
Infrastructure _Roads (km, Culvert) | [5 empty] | 0 | NA |  | Infrastructure _Roads
Program Support (Admin) | [5 empty] | 0 |  |  | Sowing $$ | 210000 | 210000 | 210000 | 210000 | 210000 | 1050000
Total | [8 empty] | Total
[9 empty] | GRAND TOTAL | 787400 | 1209900 | 1191000 | 1711000 | 1721000 | 6620300
Assumptions
Assumptions

## Annual Operational Plan
Region Annual Operational Plan for Current Reforestation and Timber Supply Mitigation
C U R R E N T R E F O R E S T A T I O N
Planning Unit (TSA/District/TFL) | Delivery Agent | Spring / Summer Planting | Fall Sowing Targets | Admin / Implem4 | % of Operational $ 7 | Access6 | Overview Planning | Surveys5 | [5 empty] | Site Preparation |  |  | Stand Maintenance Brushing 3 |  |  | Planting 2 |  |  | Current Reforestation Total
|  | SPAR | (Estimate) |  |  |  |  | Backlo NSR (RESULTSR004 ) |  |  | Surveys All (MPB/WF)
|  | (trees) | (trees) | ($) | % Total | ($) | ($) | goals(ha) | ($) | $/ha | goals(ha) | ($) | $/ha | goals(ha) | ($) | $/ha | goals(ha) | ($) | $/ha | goals (tree) | ($) | $/ tree | ($)
Region | [6 empty] | 359000
District A | BCTS | 1200200 | 2000000 | 50000 | 7.121% | 15000 |  |  |  |  | 3500 | 57750 | 16.5 | 50 | 25000 | 500 | 50 | 25000 | 500 | 1239315 | 529444 | 0.42721 | 702194
| Dist/Reg | 1076000 | 1000000 | 10000 | 2.717% |  |  | 800 | 13000 | 16.25 | 4000 | 45000 | 11.25 | 313 | 150000 | 479.2332 | 313 | 150000 | 479.2332 |  |  |  | 368000
| Recipient |  |  |  | 0% |  | 10000 | [15 empty] | 10000
TFL
District B | BCTS | 282300 | 500000 | 15000 | 9.615% | 35000 |  |  |  |  | 4000 | 66000 | 16.5 | 200 | 20000 | 100 | 200 | 20000 | 100 |  |  |  | 156000
| Dist/Reg | 165800 | 3000000 | 12000 | 4.157% |  | 30000 | 3000 | 90000 | 30 | 6333.3333 | 156660 | 24.7358 | [9 empty] | 288660
| Recipient |  |  | 2000 | 16.67% |  | 10000 | [15 empty] | 12000
TFL
District C | BCTS | 274900 | 1006000 | 15000 | 4.403% | [5 empty] | 1304 | 22200 | 17.0245 | 124 | 85200 | 687.0968 | 124 | 85200 | 687.0968 | 429200 | 133052 | 0.31 | 340652
| Dist/Reg | 609600 | 700000 | 5000 | 2.32% | 15000 | 25000 | 1800 | 63000 | 35 | 5400 | 107500 | 19.9074 | [6 empty] | 0 |  |  | 215500
Recipient
| TFL |  |  | 2000 | 9.091% |  | 20000 | [15 empty] | 22000
Sub totals | BCTS | 1757400 | 3506000 | 80000 |  | 50000 | 0 | 0 | 0 |  | 8804 | 145950 |  | 374 | 130200 |  | 374 | 130200 |  | 1668515 | 662496 |  | 1198846
| Dist/Reg | 1851400 | 4700000 | 27000 |  | 15000 | 55000 | 5600 | 166000 | 29.6429 | 15733.3333 | 309160 |  | 313 | 150000 |  | 313 | 150000 |  | 0 | 0 |  | 872160
| Recipient | 0 | 0 | 2000 |  | 0 | 20000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 22000
| TFL | 0 | 0 | 2000 |  | 0 | 20000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 22000
Grand Total |  | 3608800 | 8206000 |  |  |  | 95000 | 5600 | 166000 |  | 24537.3333 | 455110 |  | 687 | 280200 |  | 687 | 280200 |  | 1668515 | 662496 |  | 2115006
Current Reforestation Assumptions:
1 - Forecasts may change if targeted fall sowing numbers change.
2 - Spring/summer planting numbers includign reefer and storage (may not include possible stock purchases)
3 - Brushing forecast as per project approval forecast or IM estimate.
4 - Administration / Implementation is determine by Delivery Agent as per LBIS Delivery Document
5 - Includes NSR and other regular surveys such as post planting and ITSL eligibility. Survey costs are assumed to include Surveys, Prescriptions, ROI, Layout, RESULTS and forward planning
6 -Access to capture district engineering costs associated with road repairs, upgrades, snow plowing and user fees.
7- CR and TSM % Operational dollrs is based on the total value of the works and shoudl follow the LBIS Delivery Guidebook
T I M B E R S U P L Y M I T I G A T I O N
Planning Unit (TSA/District/TFL) | Delivery Agent |  |  | Admin / Implem3 | % of Operational $ 7 | Surveys2 |  |  |  |  | Impeded Brushing / Cleaning |  |  | Spacing |  |  | Fertilization |  |  | Pruning |  |  | Timber Supply Mitigation Total
[11 empty] | Treatments1 |  |  | Treatments1 |  |  | Treatments1 |  |  | Treatments1
|  |  |  | ($) | % Total | goals (ha) | ($) | $/ha |  |  | goals (ha) | ($) | $/ha | goals (ha) | ($) | $/ha | goals (ha) | ($) | $/ha | goals (ha) | ($) |  | ($)
Region | [22 empty] | 0
District A | BCTS | [21 empty] | 0
| Dist/Reg |  |  |  |  | 3500 | 57750 | 16.5 | [14 empty] | 57750
| Recipient |  |  | 50000 | 100% | 4000 | 45000 | 11.25 | [14 empty] | 95000
| TFL | [21 empty] | 0
District B | BCTS | [21 empty] | 0
| Dist/Reg |  |  |  |  | 4000 | 66000 | 16.5 | [14 empty] | 66000
| Recipient |  |  | 250000 | 100% | 3174.0667 | 156660 | 49.3562 |  |  | 0 | 20000 |  | 0 | 20000 | [7 empty] | 446660
| TFL | [21 empty] | 0
District C | BCTS | [21 empty] | 0
| Dist/Reg |  |  |  |  | 1304 | 22200 | 17.0245 | [14 empty] | 22200
| Recipient |  |  |  |  | 5400 | 107500 | 19.9074 | [14 empty] | 107500
| TFL |  |  | 8000 | 100% | [17 empty] | 8000
Sub totals | BCTS |  |  | 0 |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
| Dist/Reg |  |  | 0 |  | 8804 | 145950 |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 145950
| Recipient |  |  | 308000 |  | 7174.0667 | 201660 |  |  |  | 0 | 20000 |  | 0 | 20000 |  | 0 | 0 |  | 0 | 0 |  | 549660
| TFL |  |  | 8000 |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 8000
Grand Total |  |  |  | 316000 |  | 15978.0667 | 347610 |  |  |  | 0 | 20000 |  | 0 | 20000 |  | 0 | 0 |  | 0 | 0 |  | 703610
PROGRAM TOTAL |  |  |  | 316000 |  | 15978.0667 | 442610 |  |  |  | 166000 | 20000 |  | 455110 | 20000 |  | 280200 | 0 |  | 280200 | 0 |  | 1366106
Timber Supply Mitigation Assumptions:
1 - Treatment costs are assumed to be all found (access, logistics etc)
2 - Survey costs are assumed to include Surveys, Prescriptions, ROI, Layout, RESULTS and forward planning
3 - Administration / Implementation is determine by Delivery Agent as per LBIS Delivery Document

## All found Costs
DRAFT - Activity Cost Benchmarks Template LINKED into UNIT COSTS | [5 empty] | Prepared By:
Activity | Coast Average Cost | Interior Average Cost | Min | Max | Comments/Definitions
Current Reforestation
Surveys (Backlog NSR ) | 30 | 30
Surveys and Overview Planning | 55 | 55
Site Preparation | 550 | 350
Brushing | 762 | 762
Planting (Seedlings) | 0.57 | 0.57
Timber Supply Mitigation
Surveys and Overview Planning | 30 | 30
Brushing / Cleaning | 1000 | 800
Spacing | 1760 | 1500
Fertilizer | 248 | 220
Additional Costs / Activities
Sowing / Seed Purchase
Fertilizer Purchase

## Detailed Costs
DRAFT - Activity Cost Benchmarks 2011/12 - Operations | [6 empty] | Prepared By:
Project Submission Activity Category | Billing Units | Target Maximum Costs | Variance + 20% | Min | Max | Comments/Definitions
1.0 Administration | [5 empty] | One Per Investment Schedule _ Allowed
1.1 General Administration | % I_S | 1.5% | 1.8% | 5% | 50% | Includes General Administration, MU Budget Planning, RAH required Meetings
1.2 First Nations Capacity Building | % I_S
$ / Project
$ / Project
$ / Project
$ / Project
$ / Project
2.0 Strategic Resource Planning | [5 empty] | Only one Phase per IS for all activities unless approval given by IM.
2.1 Overview Planning | $ / ha | 1.5% | 1.5% | 0.46 | 6.44 | One Per I-S for all Overhead Related Activities
2.2 Access Mgmt Planning and Inspections | $ / km | 25 | 30 | 3 | 206
2.2 Access Mgmt Treatments | $ / km | 1601 | 1921.2 | 285 | 6179
3.0 Stand Estab. \ Treatment - All Areas | [5 empty] | Survey Projects should be separated when cost are greater the 10% (MPB vs. WF). If a Recipients is performing multiple phase (Surveys, and treatments plans) then the total costs should not be more that the combined allowable for each phases and should be indicated in the Project level descriptions or MU Budget comment section.
Surveys Recce Level | $ / ha | 22 | 26.4 | 25 | 92 | Includes Recce field work summaries and REULTS entry (if Applicable)
Surveys (MPB/WF) Full Plot | $ / ha | 50 | 60 | 25 | 92 | Includes Field Assessment and RESULTS Entry Total cost for Surveys and Site Treatment Plans is $65/ha
Site Treatment Plans (MPB/WF) Full Scope | $ / ha | 15 | 18 | 25 | 92 | Includes Treatments Prescription / ROI Analysis Total costs Surveys and Site Treatment Plans is $65/ha
Surveys (ITLS) | $ / ha | 30 | 36 | 35 | 65 | Includes Field Assessment / ROI )
Surveys RG_FG (on FFT stands) | $ / ha | 25 | 30 | 19 | 51 | Includes Field Assessment / RESULTS Entry
Multi Year Planning, contract Prep etc. (DTA, PL, BR, MSP) | $ / ha | 2 | 2.4 | 20 | 350 | Contract prep, planning, viewing etc not related to planting year
Layout (PL, BR, MSP, including ITLSL works) | $ / ha | 60 | 72 | 19 | 244 | Layout for areas should only be completed once per opening (MSP, then PL)
Danger Tree Assessment (MPB) | $ / ha | 29 | 34.8 | 19 | 43 | Includes assessment MPB often included with planting contracts
Danger Tree Assessment / Felling (WF) | $ / ha | 150 | 180 | 101 | 948 | Includes assessment and/or falling WF
Brushing (Site Prep or Maintenance) | $ / ha | 762 | 914.4 | 151 | 1411 | includes Field Boundary / Brushing Treatment / RESULTS entry
Site Preparation _ Buncher/Knockdown Pile and Burn | $ / ha | 927 | 1112.4 | 492 | 2682
Site Preparation _ Disk Trench/Mounding | $ / ha | 340 | 408 | 383 | 1139
Site Preparation _ Knockdown Mulching | $ / ha | 650 | 780 | 1673 | 1386 | Includes Field Boundary / Treatment / RESULTS entry
Planting | $ / seedling | 0.57 | 0.684 | 0.25 | 2.14 | Includes stock allocation / Plantwizard admin / planting / RESULTS entry
FltC
FltC Planning | $ / Strategy | 275 | 330 | 208 | 931 | Includes Cruising and Layout as well (Benchmarks below)
Cruising | $ / ha |  |  |  |  | Included in above project
Layout | $ / ha |  |  |  |  | Included in above project
FltC Treatment and Processing | $ / ha | 650 | 780 | 899 | 1169
Stand Estab. \ Treatment -Backlog Impeded Stands
File Review | $ / ha | 2.57 | 3.084 | 0.12 | 27.14
Field Review | $ / ha | 32 | 38.4 | 19 | 51 | Includes Field Assessment / Prescription / ROI / Field Boundary / RESULTS Entry
Brushing | $ / ha | 762 | 914.4 | 151 | 1411 | includes Field Boundary / Brushing Treatment / RESULTS entry
Stand Estab. \ Treatment - Enhancement
Fertilization | $ / ha |  |  |  |  | Includes up front planning costs / treatments and RESULTS entry
Spacing repressed stands | $ / ha |  |  |  |  | Includes up front planning costs / treatments and RESULTS entry
Cone collection | $ hl
RESULTS entry | $/ha |  |  |  |  | Stand alone cost for RESULTS entry
Stand Tending Treatments
Fertilization Application - Coast | $ / ha | 248 |  |  |  | Assumption that MFR will purchase fertilizer. Treatment cost includes: application, one monitoring plot per 500 ha ; implementation and monitoring contractor; does not include additional costs for access, fertilizer additives, or remeasurements of existing monitoring plots
Fertilization Application -NIFR | $ / ha | 206 |  |  |  | see above;
Fertilization Application - SIFR | $ / ha | 237 |  |  |  | Based on feedback from SIFR and additional funding for monitoring;
Spacing - Coast | $ / ha | 1760 |  |  |  | Includes all costs for prescription, implementation and layout costs and treatment cost as well as delivery allowance
Spacing - NIFR | $ / ha | 1769 |  |  |  | see above;
Spacing - SIFR | $ / ha | 1434 |  |  |  | see above;
Pre 87, Cleaning/ Brushing - Coast | $ / ha | 1105 |  |  |  | Includes all costs for prescription, implementation and layout costs and treatment cost
Pre 87, Cleaning/ Brushing - NIFR | $ / ha | 963 |  |  |  | see above;
Pre 87, Cleaning/ Brushing - SIFR | $ / ha | 923 |  |  |  | see above;
Pruning - Coast | $ / ha | 1686 |  |  |  | Includes all costs for prescription, implementation and layout costs and treatment cost
Punning - NIFR | $ / ha | 1732
Pruning - SIFR | $ / ha | 1258 |  |  |  | see above;

## Definitions
Definitions;
Total Eligible: This is the total estimated area which will be examined over the next 5 years. These estimates will be based on the most recent available data as outlined in the Reference Documents above.
Total and Annual Achievable: These are the proportion of the total eligible activity (defined above) that is forecast to be completed every year and cumulatively over the next five years. The first two years of achievable goals will be driven by sowing levels and current status of prescriptions.
Current Reforestation
Backlog NSR – This is the total estimated area that will be surveyed . These numbers come from RESULTS and Silviculture Strategies(2015 throne speech commitment).
Surveys – This is the total estimated area to be surveyed . This includes all forecasted surveys based on estimates of eligible ground from MPB, Catastrophic WF, unfunded NRFLs . In the comment section the estimated percent Wildfire vs. MPB vs. NRFL.
Site Preparation – This is the total estimated area to under go site preparation including danger tree assessment, mechanical site preparation and potential FLTCs. It is linked to the sowing targets.
Stand Maintenance Brushing – This is the total estimated area to be brushed . This includes both brushing pre-planting brushing, brushing to maintain FFT stands. This does not include impeded stand brushing.
Planting – This is the total estimated trees to be planted. This includes both planting and fill planting.
Sowing - This is the total estimated trees that will be sown . This number is linked to the survey number and assumptions around the relationship of ground surveyed to ground identified as eligible to be planted (NS, ROI >2%, access etc)
Timber Supply Mitigation
Backlog Impeded surveys – This is the estimated area that the file review will require surveying. These numbers come from RESULTS and Silviculture Strategies.
Brushing / Cleaning – This is an estimate of the area eligible for brushing as estimated from the Silviculture Strategy or Fertilization Strategy .
Spacing – This is an estimate of the area eligible for spacing as estimated from the Silviculture Strategy or recent opportunity reports.
Fertilization – This is an estimate of the area eligible for fertilization as estimated from the Silviculture Strategy or Fertilization Strategy.
Spacing – This is an estimate of the area eligible for spacing as estimated from the Silviculture Strategy or recent opportunity reports.
Pruning – This is an estimate of the area eligible for pruning as estimated from the Silviculture Strategy or recent opportunity reports.
Additional Activities
Infrastructure – this is an estimate of the forecasted costs/km of roads required to meet goals.
Cone Collection – This is an estimate of the hectolitres of cones required for the planting program based on provincial wide seed needs analysis.
Other s
Unit Costs – These are unit cost averages from the all found costs spreadsheet . If estimated costs are significantly different than posted in this spreadsheet then make the change and colour red with comment as to why the difference. These costs are linked to the $$ table located on the right hand side of the sheet – no filling out is required for the $$ sheet. It is only a rough planning tool as well, final allocation will not be tied to the break out from the plan as information and locations will always change.
Comment Column – Provide factors used to build estimates (egg. Brushing 2% of forecasted planting) and for site preparation include a percentage breakdown estimate for and Mechanical, Danger Tree and FLTC.
Summary Cell (bottom of spreadsheet) - Written summary of the assumptions (and sources) used during the net down process. See Business Case for example.