## Sheet1
INSTALLATION SUMMARY REPORT
EP # _703_82 Dewdney West | December 2018
CREW | Jake, Justin
EQUIPMENT USED | Vertex, iPad
1. access (roads, trails, paths between plots) | 30 minute drive from Hope, 20 minute walk in, you must cross an across actively ravelling slope that is a little dicey.
2. weather conditions | Fine, but cold to -10C, no wind. I wouldn't try December here most years
3. % slope & direction | Plot 1 10-15% SW, The rest to 35%SW
4. vegetation (major species, abundance) | Mostly mossy, little understory, scattered falsebox
5. TP markers | Fine, trees repainted
6. corners (markers, labels) | Aluminum posts,
7. center posts (presence, condition, identification tag) | Cedar 4X4's in typically rough but servicable shape
8. maintenance work done | Tagged, painted trees, painted trails
9. ingrowth (presence, species) | Patchy HW, mostly in plot 1&4, see note in plot condition
10. tags (nails, straps) | Mostly too small nails, all need to be pulled, blue brittle tags many replaced
11. height visibility | Good
12. plot condition | Poor growth, the HW ingress almost all top dead and dying downwards, particularly in the higher rockier blocks. I believe this may be due to drought.
13. ambiguities | Not enough trees in the Crown class 3, means many on this high elevation slow growing site will not meet EP703 class 2 growth validation. Many trees misclassified as cc 1 we changed many.
We found ingress from 436 to 485 in plot 1 not on file, this ingress was added in to file but not stem mapped due to time constraints. Plot 1 is a disorganized mess, the most time consuming plot due to the HW ingress
14. other information | Mountain Beaver caches and warrens throughout both Dewdney sites