## work plan & timing
ISSC Review of Max Densty, Work Plan
PROJECT DETAILS
DATE | MILESTONE | POSITION | BASELINE | WHO | Notes
2017-02-07 | Issue brought forward to ISSC | -20 | 1 | Kori | 2003 Fires in Okanagan and Kootenays with resulting high density regeneration and high cost of spacing reinvigorated max density debate
2017-04-05 | Repression Density and Decision Key Presentation to TOSSWG | -10 | 1 | Ed Collen and Eleanor McWilliams | Repression Density Presentation to TOSSWG, including background of Decision Key
2017-06-01 | Max Density Field Trip, Kelowna Weyerhaueser | 10 | 1 | Trenna MacLeod Weyerhaeuser | Reviewed several treatments and high density stands. FFT participated and discussed guidance document. We have speakers notes.
2017-08-01 | Kori presented paper to ISSC | -5 | 1 | Kori | Discuees paper and asked for comments
2017-09-01 | Update Discussion Paper with feedback | -20 | 1 | ISSC members | review Discussion paper and provide feedback
|  | 20 | 1
|  | 15 | 1
|  | -15 | 1
|  | -5 | 1
|  | -10 | 1
|  | 20 | 1
2017-12-31 | Submit recommendations to OIFs | 10 | 1
1
1

## max density issues
Theme | Identified Issue | Discussion | ISSC Working Group Comments | Actions Required | Final Outcome
Definition | In current FRPA legislation, maximum density is equal to repression density. | Could this be followed up with opportunity to pre-commercial thin? | clarify by changing wording to repression density
Post Spacing Density | Reference to post spacing treatment density is not specified in FRPA and could be removed from stocking standards.
Countable Conifer Definition | Does countable conifer definition reflect the threshold where natural mortality and stand differentiation occurs?
Impact of Time to Establish | Separate wildfire vs post harvest regeneration – importance here is understanding how long it takes to establish a stand and the effect this has on stand differentiation. | This also impacts interpretation of some of the research like Barnes lake. a) Barnes Lake – trees were sown in 1 day and planted in 2 days so establishment is completely at the same time. b) Wildfire – trees are all the same age but established within a few weeks or months. This difference contributes to some stand differentiation. c) Post harvest regeneration – logged and regen fills in over 1-10 years. There is large differentiation in the stand so repression is unlikely. | If max density rarely applies to any sites other than wildfires, is this very significant? Yes, it influences how research was interpreted.
Monitoring | Are adequate trials established to improve our understanding of stand density impacts on stand development? What trials are currently established and what is being monitored? Who is lead? | Have any new trials been established since 2006/2007 increase in max density threshold?
Respression Density Threshold | What new information is available to better identify the threshold maximum density that tree growth is significantly impeded. | a) Species – should max density only apply to Pli and Lw? b) Site index - repression occurs at lower densities on drier sites so is one number appropriate way to minimize risk of repression to crown? c) does forest health have any impact on decision to space for max density
FFT | Should Silviculture investment on crown land be consistent between IA obligations and FFT? | If same fire and 2 areas are adjacent, is it defendable that the licensee has to pay $3500/ha to treat max density issue but FFT will not pay that on the adjacent site? | What is FFT treating and not treating usng the Decision Key?
Decision Key | Should FFT Juvenile Spacing Review document and Decision Key apply to IA ? | a) Does the lower volume potential of low SI sites reduce the amount that is practicable to spend / ha. Does it make sense to spend $4000/ha to space a site with SI 15? b) Should we include ROI threshold for max investment on IA? c) Are there gaps or updates in the document that need to be addressed before this was possible? | FFT is considering updating decsion key with: a) Definition of site tree used to calculate max investment is critical and should be discussed – representative tree vs the largest. b) Current planned updates to report include i. a succinct survey methodology including when to survey using a 1.0m X 1.0m plot, or a 0.56m radius plot & methodology. (Rather than Silviculture Survey Procedures Manual.) ii. Correct Flow Chart changing “Top Height” to “Site Tree”. Create print off flow chart & to allow people to walk their way through it easier. Define how to pick the appropriate Site Tree. (Use existing published method.) iii. Print off appropriate break even table iv. Summarize SI data collected. (There is a need for some analysis to understand better.) v. Define Site Index determination methodology. (Use existing published method.) vi. Refine Table 2 from The Report by replacing extrapolated data with empirical or modelled data.
Appraisal | Should maximum density spacing be considered basic Silviculture? If yes, does the current funding mechanism adequately recognize the cost or are changes needed. | a) The time to space and address repression is when stand is less than 1m tall so could lose opportunity if density control isn’t considered basic Silviculture b) Appraisal only looks at treatments required for 5 years after harvest and often spacing is not identified by then. c) Unpredictable nature of max density issues make forecasting difficult. d) Could a specific appraisal allowance for wildfire salvage be applied if max density issue expected. e) Could max density spacing could be considered FFT funded activity once you prove it is required, licensee administered similar to section 108.
Survey Procedures | Standard Silviculture surveys often underestimate the density of the stand. | Post wildfire densities are highly variable and difficult to stratify which may result in an underestimate of the max density issue. Investigate potential opportunity for surveys to use imagery and automated analysis of tree counts.