## Sheet1
Interior Silviculture Sub Committee
Meeting Actions
Item No. | Action | Update and Comments | Related Topic | Responsible | Date Added | Due Date | Status | Date Complete
1 | Ask Will Mackenzie to present BEC Modelling of species selection |  | Stocking Standards | Paul Rehsler | 2017-02-07 |  | Done | 2018-10-10
2 | Update survey methodology to tally high densities. Greg Jorgenson to follow up with Steve Jones and Monty DeGregg | Ask Greg to provide update at Sept meeting | Max Density, Surveys | Paul Rehsler | 2017-08-01 |  | Done | 2018-10-10
3 | FFT program to provide strategic reforestation direction to licensees once Treasury Board approvs. Confirm amount approved by Treasuery | Ask Neil to provide summary for Sept 25 meeting | Wildfire Reforestation | Paul Rehsler | 2017-12-18 |  | Done | 2018-10-10
4 | CBST presentation to update group on seed supply and prioritizaton for Section 108/FFT | Set up for Sept 25 meeting | Seed | Paul Rehsler | 2017-12-18 |  | Done | 2018-10-10
5 | Results of seed analysis and seedling update from Brendan Brabrender |  | Wildfire Reforestation | Kori Vernier | 2018-02-06 |  | closed
6 (6&7 comb) | Set up working group to look at options to get funding applicatons into the system. Review and comment on Post Wildfire Briefing Note. Needs Caribou Section 108 Options paper presented by Josh Pressey, DM to be finalized which is currently out for comment | First need strategy and prioritization process confirmed | Wildfire Reforestation | Paul Rehsler/Grant Glessing | 2018-02-06 |  | closed
8 | Updates to Repression Density Decision Key - what are the final updates and their status. | follow up with Anne Wong (replaced Monty when he retired). Anne reports to Brendan so he might be able to provide update. | Max Density | Paul Rehsler | 2018-02-06 |  | in progress
9 | Follow up with Greg Jorgenson about using DFP in irregular shelterwood stands | Todd sent email. Present at next meeting in Greg's updates | Surveys, stocking standards | Todd Schmidt | 2018-04-03 |  | Done | 2018-10-10
10 | Support development of shared stocking standards in Mackenzie, PG and Stewart-Nechako | Paul to stay in touch with Miodrag and other Stewardship officers | Stocking Standards | Paul Rehsler | 2018-05-22 |  | in progress
11 | Talk to Shannon Pierce to get place marker for changes to legislation for stocking standards |  | Stocking Standards | Paul Rehsler | 2018-05-22 |  | Done | 2018-10-10
12 | Send copy of Caribou Enhanced Stocking standards to Paul to confirm they are consistent with guidance document. |  | Stocking Standards | Darcy Lillico, Paul Rehsler | 2018-05-22 |  | Done | 2018-10-10
13 | Share George Harpers paper on Barnes Creek research | published online | Max Density | Paul Rehsler | 2018-05-22 |  | closed
14 | Paul to present Stocking standards paper to OIFs and will share feedback/results. | NOIF Aug 1, SOIF ask to be put on agenda | Stocking Standards | Paul Rehsler | 2018-05-22 |  | in progress
15 | Set up doodle poll for in person meeting in Nov |  | ISSC Meeting | Kori Vernier | 2018-07-24 | 2018-07-30 | Done | 2018-10-10
16 | Follow up with Dan regarding FSP tracker and stocking standards IDs looking for efficiencies in how they are managed and what help is needed and options for who is available to get them entered. | Completed for Caribou, consultant used. Ministry has automated process. All Districts need to use same format. Need to distribute format to group and to District offices (Dan Turner has). | Stocking Standards | Darcy | 2018-07-24 |  | in progress
17 | Recruit the new Stewardship Forester in Cranbrook as a presenter at the Stewardship meeting in November to discuss Canfor Research in the Kootenays. | add to repression density conversation | Surveys, Wildfire Reforestation | Paul Rehsler | 2018-10-10 |  | in progress
18 | Contact Josh and check for updates on his group's work. |  | Wildfire Reforestation | Darcy Lillico | 2018-10-10 |  | N/A
19 | Combine Actions #6 and #7 on Actions Spreadsheet. |  | Wildfire Reforestation | Mari Schenkeveld | 2018-10-10 |  | Done | 2018-10-10
20 | Confirm with Shannon' replacement regarding the place marker for changes to legislation for stocking standards. | Denise Hogue is replacement. | Stocking Standards | Nina | 2018-10-10
21 | Send the link for TR115, "George Harper's Barnes Creek 34 Year Remeasurement to Kori. | https://www.for.gov.bc.ca/hfd/pubs/Docs/Tr/TR115.htm | Max Density | Greg Jorgenson | 2018-10-10 |  | complete
22 | Follow up with Nina to get a meeting room for the Face to Face Meeting in Kamloops. |  | ISSC Meeting | Paul Rehsler | 2018-10-10 |  | N/A
23 | Submit couple of key topics for the Face to Face Meeting and what you want to see accomplished at the meeting. |  | ISSC Meeting | ISSC Members | 2018-10-10 | 2018-10-19 | N/A