## Sheet1
Interior Silviculture Sub Committee
Meeting Actions - As of Feb 10, 2020
Item No. *() refers to the action # in previous Meeting Actions Sheets | Action | Update and Comments | Related Topic | Responsible | Date Added | Due Date | Status | Date Complete
1 | Ask Will Mackenzie to present BEC Modelling of species selection |  | Stocking Standards | Paul Rehsler | 2017-02-07 |  | Done | 2018-10-10
2 | Update survey methodology to tally high densities. Greg Jorgenson to follow up with Steve Jones and Monty DeGregg | Ask Greg to provide update at Sept meeting | Max Density, Surveys | Paul Rehsler | 2017-08-01 |  | Done | 2018-10-10
3 | FFT program to provide strategic reforestation direction to licensees once Treasury Board approvs. Confirm amount approved by Treasuery | Ask Neil to provide summary for Sept 25 meeting | Wildfire Reforestation | Paul Rehsler | 2017-12-18 |  | Done | 2018-10-10
#1 (4) | CBST presentation to update group on seed supply and prioritizaton for Section 108/FFT | Set up for Sept 25 meeting | Seed | Paul Rehsler | 2017-12-18 |  | closed | 2018-10-10
#2 (5) | Results of seed analysis and seedling update from Brendan Brabrender |  | Wildfire Reforestation | Kori Vernier | 2018-02-06 |  | closed
#3 (6: 6&7 comb) | Set up working group to look at options to get funding applicatons into the system. Review and comment on Post Wildfire Briefing Note. Needs Caribou Section 108 Options paper presented by Josh Pressey, DM to be finalized which is currently out for comment | First need strategy and prioritization process confirmed | Wildfire Reforestation | Paul Rehsler/Grant Glessing | 2018-02-06 |  | closed
#4 (8) | Updates to Repression Density Decision Key - what are the final updates and their status. | follow up with Anne Wong (replaced Monty when he retired). Anne reports to Brendan so he might be able to provide update. | Max Density | Paul Rehsler | 2018-02-06 |  | complete
9 | Follow up with Greg Jorgenson about using DFP in irregular shelterwood stands | Todd sent email. Present at next meeting in Greg's updates | Surveys, stocking standards | Todd Schmidt | 2018-04-03 |  | Done | 2018-10-10
#5 (10) | Support development of shared stocking standards in Mackenzie, PG and Stewart-Nechako | Omineca silv working group | Stocking Standards | Craig, Tammy | 2018-05-22 |  | in progress
11 | Talk to Shannon Pierce to get place marker for changes to legislation for stocking standards |  | Stocking Standards | Paul Rehsler | 2018-05-22 |  | Done | 2018-10-10
12 | Send copy of Caribou Enhanced Stocking standards to Paul to confirm they are consistent with guidance document. |  | Stocking Standards | Darcy Lillico, Paul Rehsler | 2018-05-22 |  | Done | 2018-10-10
#6 (13) | Share George Harpers paper on Barnes Creek research | published online | Max Density | Paul Rehsler | 2018-05-22 |  | complete
#7 (14) | Paul to present Stocking standards paper to OIFs and will share feedback/results. | NOIF Aug 1, SOIF ask to be put on agenda. | Stocking Standards | Nina Sigloch | 2018-05-22 |  | complete
15 | Set up doodle poll for in person meeting in Nov |  | ISSC Meeting | Kori Vernier | 2018-07-24 | 2018-07-30 | Done | 2018-10-10
#8 (16) | Follow up with Dan regarding FSP tracker and stocking standards IDs looking for efficiencies in how they are managed and what help is needed and options for who is available to get them entered. | Completed for Caribou, consultant used. Ministry has automated process. All Districts need to use same format. Need to distribute format to group and to District offices (Dan Turner has). April 29, 2019: Darcy to send Craig the Master spreadsheet to put on the FTP Site. | Stocking Standards | Darcy Lillico | 2018-07-24 |  | complete
#9 (17) | Recruit the new Stewardship Forester in Cranbrook as a presenter at the Stewardship meeting in November to discuss Canfor Research in the Kootenays. | Denise Hogue is replacement. | Surveys, Wildfire Reforestation | Paul Rehsler | 2018-10-10 |  | complete
#10 (18) | Contact Josh and check for updates on his group's work on Sec108. |  | Wildfire Reforestation | Darcy Lillico | 2018-10-10 |  | complete
19 | Combine Actions #6 and #7 on Actions Spreadsheet. |  | Wildfire Reforestation | Mari Schenkeveld | 2018-10-10 |  | Done | 2018-10-10
#11 (20) | Confirm with Shannon' replacement regarding the place marker for changes to legislation for stocking standards. | Denise Hogue is replacement. | Stocking Standards | Nina | 2018-10-10 |  | complete
#12 (21) | Send the link for TR115, "George Harper's Barnes Creek 34 Year Remeasurement to Kori. | https://www.for.gov.bc.ca/hfd/pubs/Docs/Tr/TR115.htm | Max Density | Greg Jorgenson | 2018-10-10 |  | complete
#13 (22) | Follow up with Nina to get a meeting room for the Face to Face Meeting in Kamloops. |  | ISSC Meeting | Paul Rehsler | 2018-10-10 |  | N/A
#14 (23) | Submit couple of key topics for the Face to Face Meeting and what you want to see accomplished at the meeting. |  | ISSC Meeting | ISSC Members | 2018-10-10 | 2018-10-19 | N/A
#15 | Resend the South OIF the meeting minutees and stocking Standards Issues Note. |  | ISSC Meeting | Nina Sigloch | 2019-02-02 |  | complete
#16 | Leave all required documents on the FTP site. |  | ISSC Meeting | Paul Rehsler | 2019-02-02 |  | complete
#17 | Leave access to editable documents to Paul's replacement. |  | ISSC Meeting | Paul Rehsler | 2019-02-02 |  | complete
#18 | Update the Work Plan to show the status of all the work. |  | ISSC Meeting | Kori Vernier | 2019-02-02 |  | complete
#19 | Send Kori the Thompson Okanagan SS Variations Max Density Exemption on wildfire salvage areas. |  | ISSC Meeting | Nina Sigloch | 2019-02-02 |  | complete
#20 (includes #24) | Update the actions to close off Max Density. Write up a background and summary document about Repression Density information to follow up with the Rocky Mountain District. Circulate the updated actions and background/summary document to the ISSC for review before forwarding it to the OIF. | May 1/19: Mari has amalgamated action #24 with action #20 as per Kjori at April 29/19 meeting. Closed this action. It will be addressed with RDWG. | ISSC Meeting | Kori Vernier | 2019-06-30 |  | closed
#21 | Check into the status of the spreadsheet format for the Stocking Standards IDs import as to whether it is available for all Districts. |  | ISSC Meeting | Darcy Lillico | 2019-02-02 |  | complete
#22 | Obtain SOIF meeting schedule. |  | ISSC Meeting | Nina Sigloch | 2019-02-02 |  | complete
#23 | Send out meeting list and schedules to group. | Kori will send proposed meeting dates to the ISSC members (from meeting minutes: 12-Mar-19). | ISSC Meeting | Kori Vernier | 2019-02-02 |  | complete
#25 | Summarize a list of top priorities and their background, and forward to the ISSC members to review and select priorities for ISSC to work on. |  | ISSC Meeting | Kori Vernier | 2019-03-12 |  | complete
#26 | Review the list of top priorities from Kori, and select the top three priorities that ISSC should work on. |  | ISSC Meeting | ISSC Members | 2019-03-12 |  | complete
#27 | Book the next meeting. |  | ISSC Meeting | Kori Vernier | 2019-03-12 |  | complete
#28 | Add to June 's Agenda: ISSC members to discuss the initial phase of the Fast Track process and discuss. |  | ISSC Meeting | Craig Wickland Kori Venier | 2019-06-20 |  | complete
#29 | Craig to track the status of the guidance memo for Enhanced Basic Silviculture. |  | ISSC Meeting | Craig Wickland | 2019-06-20 |  | complete
#30 | Craig to get a speaker to do a presentation on Silviculture Research for "Face to Face" meeting or for the next conference call meeting. | Craig has talked to the researchers, want to tie into a specific topic that we are working on. Lorraine McGlauclan drought research. Catherine presented at Dec5, 2019 meeting and sent links to research info. Will reach out on specific topics and issues as they arise. | ISSC Meeting | Craig Wickland | 2019-06-20 |  | complete
#31 | Craig to invite Greg to talk about the North and South FG monitoring and provide updates on the Silviculture Surveys Manual to facilitate discussions at the Face to Face meeting or a conference call meeting |  | ISSC Meeting | Craig Wickland | 2019-06-20 |  | complete
#32 | Craig to forward the Coastal group discussion paper to the ISSC members. |  | ISSC Meeting | Craig Wickland | 2019-06-20 |  | complete
#33 | Craig to set up a doodle poll for “Face to Face” meeting around late August/early September as to the date/timing l and location (Kamloops or Prince George). |  | ISSC Meeting | Craig Wickland | 2019-06-20 |  | complete
#34 | A meeting request will be sent out once a meeting room is located in Kamloops or Prince George. |  | ISSC Meeting | Kori Vernier Nina Sigloch Craig Wickland | 2019-06-20 |  | complete
#35 | Revisit the wording in the TO Regional Stocking Standards regarding the decision key with the Silviculture Standards working group and clarify that it is worded sufficiently to imply fire salvage only |  | ISSC Meeting | Nina Sigloch Todd Schmidt | 2019-06-20 |  | closed
#36 | The Max Density subgroup will continue to work on the Max Density issue and review current scientific information by meeting with researchers. They will do a presentation to the main ISSC group at the September “Face to Face” meeting for endorsement to move this topic forward. |  | ISSC Meeting | Max Density Subgroup | 2019-06-20 |  | complete
#37 | Forward the latest minutes from the last Section 108 group meeting. |  | Section108 | Darcy Lillico | 2019-06-20 |  | complete
#38 | Send out a summary called "SOIFs June 20th Updates on Priorities" to the ISSC members to review. |  | ISSC Meeting | Nina Sigloch | 2019-06-20 |  | complete
#39 | Post Nina's summary, "SOIFs June 20th Updates on Priorities" and the final minutes on the FTP site. |  | ISSC Meeting | Craig Wickland | 2019-06-20 |  | complete
#40 | Send out a meeting request for August 8, 2019. |  | ISSC Meeting | Craig Wickland | 2019-06-20 |  | complete
#41 | Craig to circulate the hardwood management strategy developed by the Coast for mix-wood and broadleaf management in the Coast to the group. |  | ISSC Meeting | Craig Wickland | 2019-08-08 |  | complete
#42 | Craig to check with Greg when he returns on the 21st as to the information that he can provide for the group regarding the deciduous topic, and also to contact Darcy to touch basis regarding information from the Cariboo researcher. |  | ISSC Meeting | Craig Wickland | 2019-08-08 |  | complete
#43 | Kori to include the related items to herbicides from the SOIF’s list to the deciduous topic on the agenda. |  | ISSC Meeting | Kori Vernier | 2019-08-08 |  | complete
#44 | Kori to follow up with Brendan regarding updates from his sub-committee on reforestation costs, lack of seedlings and nursery capacity. |  | ISSC Meeting | Kori Vernier | 2019-08-08 |  | complete
45 | Distribute issues note on post wildfire and post-harvest regenerated by Monday to the RDWG members. Comments back to Greg and the sub-committee by Sept. 30. | add appendix describing the scope of the issue. Intent is to wrap up max density by Dec31, 2019 | Max Density | Greg Jorgenson | 2019-09-05 | 2019-09-30 | complete
46 | Max Density sub-committee to revise issues note and develop a decision note to be reviewed by ISSC at Feb 10 meeting and to be presentted to both N and S OIFs. | for presentation to North and South OIFs at their fall meeting, notify Coastal OIF | Max Density | Greg Jorgenson | 2019-09-05 | 2019-11-01 | in progress
47 | Confirm non deleterious deciduous sub-committe membership | George Harper, Richard Kabczens, Neil Spendiff, Lorree Lucas to be contacted to confirm participation in subcommittee | Deciduous | Greg Jorgenson/Kori Vernier | 2019-09-05 | 2020-02-28 | in progress
48 | Non deleterious deciduous sub-committe to determine scope of "administrative" brushing treatments, literature review, inform Timber IO of research gaps/needs, develop a couple options (straw dogs) to model in TASS | research papers posted on FTP site for everyone to review. FAIB presentation TBD regarding timber supply impacts once options developed | Deciduous | Greg Jorgenson/Kori Vernier | 2019-09-05 | 2020-07-01 | in progress
49 | Send Kari FTP site and any relevant documents. Kari needs to test to verify. Craig currently posting everything. | Craig continuing to update | ISSC Meeting | Craig Wickland | 2019-09-05 | 2019-09-16 | complete
50 | Develop format for 2017 and 2018 drought impacts report and to group for comment | Working with Dan Turner to calculate 5 year avg and then will test with Tolko data to give comparison. Survey results and planting udpates into results still in progress so will need to be updated. | Drought | Craig Wickland (take over from Grant Glessing) | 2019-09-05 | next mtg date | in progress
51 | Send out request for 2017/2018 drought impacts to be reported by licensees and districts and roll up impacts by district to determine scope (% THLB, $ impact and value) |  | Drought |  | 2019-09-05
52 | Develop Issue Note with scope of 2017/2018 Drought and possible criteria that would define drought as an eligible S108 event to present to Resource and Tenures Stewardhsip Committee | also determine if there is potential to define alternate mechanism if replanting doesn't make sense | Drought | Possibly Drought Working Group | 2019-09-05
53 | Determine what other forestry working groups or committees exist at a district or regional level throughout the province and get copies of their TOR | intention to identify where gaps exist and potential for improving communications between various stakeholder groups i.e. Wildlife Biologists and Foresters for GAR development and recommend a reporting framework for groups to OIFs | ISSC Meeting | Darcy Lillico/Kari Doyle | 2019-09-05 | 2019-10-21 | in progress
54 | Obtain S OIF meeting minutes and schedule | Last meeting was in June, next mtg in Dec but might be cancelled. In contact with OIFs but they are in flux. | ISSC Meeting | Todd/Nina | 2019-09-05 | 2019-10-21 | closed
55 | Propose ISSC has a seat on North and South OIFs (like on Coast) | NOIF said | ISSC Meeting | Craig Wickland | 2019-09-05 |  | complete
56 | Distribute the results of the FG monitoring reports to group |  | ISSC Meeting | Greg Jorgenson | 2019-09-05 | 2020-02-10
57 | Information session by FAIB to show how survey data is used and inputs into TSR. | Mack TSR group provided to group FAIB presentation with Greg for jan 2020 mtg (30 min) | TSR | Craig Wickland | 2019-09-05 | 2019-12-31
58 | GAR order issues - how do we action solution identified in meeting mintues? Put together issues note and sumarize a couple of examples? | review at next meeting | Stocking Standards | Kori Vernier/ Bill Laing/ Nina | 2019-09-05 | 2019-12-05
59 | post deciduous literature on FTP site |  | deciduous | craig | 2019-10-21 | 30 day | complete
60 | schedule Paul ABCFP as standing agenda item for update n PGA for next meeting |  | ISSC Meeting | paul | 2019-10-21 |  | complete
61 | provide upate on research priorities at next meeting | Franchesco to provide broad discussion for highlevel overview | research | Catherine / Craig | 2019-10-21 |  | complete
62 | section 108 added a standing agenda item |  |  |  | 2019-10-21 | 2019-12-01 | complete
63 | ISSC members to review RDWG Max Density Desition Note and Appendices | provide feedback to Greg J. and Trenna M. via email | Max Density | All | 2020-02-10 | 2020-02-16
64 | Present RDWG Max Density Decision Note to North, South, Coastal OIF | present before developing the policy for the Chief Forester to sign off | Max Density | Craig Wickland, Kori Vernier, Trenna MacLeod, Greg Jorgenson | 2020-02-10 | Next OIF meetings
65 | Find representatives for Deciduous WG from northern silviculture community | Tammy/Miodrag to be contacted, a rep from the Northeast region as well | Deciduous | Kori Vernier | 2020-02-10 | 2020-04-02
66 | Arrange presentation on RPB's dry Fdi research and best management practices | contact John Hopper for presentation | Drought | Craig Wickland | 2020-02-10 | 2020-09-15
67 | Secure replacement ISSC member for Darcy Lillico | Darci to confirm with his replacement, Shelley Barlow on her ISSC membership | Membership | Darcy Lillico | 2020-02-10 | 2020-04-02
68