SILVICULTURE CONTRACT COORDINATOR CHECKLIST

FOR BCTS and DISTRICT USE

| Contract File # | Contract Name | Contract Term – Start Date |
| --- | --- | --- |
| Contract Coordinator (CC) | Expense Authority (EA) | Contract Term – End Date |

Orange highlighted items: BCTS Forms Directory from Contract Quality Management System (CQMS)

Green highlighted items: FLNRO Forms Index

Blue highlighted items: CSNR Procurement Forms Website

Employment Standards bulletins: BCTS Policy & Legislation (public facing page)

BCTS BA EMS: Safety Forms and Checklists website

BCTS Silviculture Tender Package Guidance document: Business Administrator Sharepoint – or use local BA admin guidance – Business Administrator access only

Lime highlighted: BCTS Contractor Planting Rating System! Sharepoint BCTS Contractor Planting Rating System! Sharepoint

Other important links for contract management BCTS-Contract-Help@gov.bc.ca Core Policy & Procedures Manual - Province of British Columbia (gov.bc.ca)

| PRE-AWARD Planning and Monitoring Documents (iNTERNAl DOCS) |  | Date Done |
| --- | --- | --- |
| Obtain Contract # | - Contract number should include the fiscal year (example: PL23TII101 is a planting contract where the planting will occur in 2022 but it is in fiscal year 2023) - Must indicate if it is an Option to Renew (OTR) contract (see page 4 for further OTR instructions) |  |
| Set up contract folders and documents | - Create contract folder: - Set up folders: 01 Planning Pre-Award 02 BC Bid 03 Award 04 Modifications 3. Create an operational folder in G drive - used only by contract coordinator and set up folders: BCTS 05 Communication 06 Invoices 07 EMS / Safety 08 Completion |  |
| Ministry Cost Estimate (MCE) | Formulate MCE with rationale, date, and sign/seal. Ensure it is clear, detailed and reflects Tender Offer Form info. Must be a separate spreadsheet to the BCTS 1198. |  |
| BCTS 1198- Planning Procurement Checklist | https://intranet.gov.bc.ca/for/bcts/finance-procurement/cqms/forms - Document under Contract Forms planning - The new fillable PDF form in the BCTS Forms Directory can be digitally signed by the EA and CC - Guidance document on the CQMS website under “General guidance and directives” |  |
| Safety BCTS 19-1 | Contract Planning Safety Checklist https://intranet.gov.bc.ca/flnrord/bcts/safety under BCTS Safety Certification then Appendices |  |
| Safety BCTS 23-1 | Access Assessment Checklist - required when there are known safety access concerns – same as above |  |
| BCTS EMS Project Risk Rating | BCTS Project Risk Rating Form on the CQMS website under “Contract forms > Planning” https://intranet.gov.bc.ca/flnrord/bcts/finance-procurement/cqms/forms |  |

| Contract/Project - Risk Rating - Monitoring Plan |  |  | - Project Risk Rating for Monitoring - Contract Monitoring Plan (save to Communications folder) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CONTRACT AND TENDER DOCUMENTS (for 02 BC Bid folder) |  |  |  |  |  |  |  |  |  |
| Table of Contents |  |  |  |  |  | The NRS1000-ToC-Checklist TOC or Planting specific |  |  |  |
| NRS1295 – Sample Invitation to tender – delete pages 1 to 5 (including sample table of contents) |  |  |  |  |  | Rename the document “Information to Bidders”. It will be posted as a separate document from the Table of Contents on BC Bid. |  |  |  |
| Conditions of Tender (Services) |  |  |  |  |  | Conditions of Tender for Service Contracts |  |  |  |
| NRS 629 |  |  |  |  |  | Tender Offer Form |  |  |  |
| NRS 423 |  |  |  |  |  | Tender Envelope – delete file link in footer |  |  |  |
| NRS 1000 |  |  |  |  |  | Operational Services Contract |  |  |  |
| BRUSH | PLANT | SURVEYS |  |  | SPACE |  |  |  |  |
| FS717a | FS767a | FS925a |  |  | FS751a | Operational Services – legal document which should not be changed. | Schedule A |  |  |
| FS 1-b | FS 1-b | FS 1-b |  |  | FS 1-b | Payment – The FS 1-b is the base document. Add the subsidiary payment schedule table (FS717b, FS925b, FS751b) into the FS 1-b. The FS 1-b has specific clauses (holdback, invoice submission info). | Schedule B |  |  |
| FS717b See BR21TII105 contract | See Planting Contract Folder | FS925b |  |  | FS751b See BR20TII103 contract |  |  |  |  |
| FS 787 | FS 787 | FS 787 |  |  | FS 787 | Other Conditions – Normally developed by TSO specific to the activity. If applicable it identifies it as Schedule C. BA’s can add specifics if required, ie: plot intensity for surveys, planting microsites, etc. | Schedule C |  |  |
| NRS 1-D (CGL required for all contracts) |  |  |  |  |  | Insurance Schedule (NRS1289 is guide) | Schedule D |  |  |
| FS11- BCTS |  |  |  |  |  | EMS schedule – new schedule – important guidance located in EMS Schedule Local Table and Guidance | Schedule E |  |  |
| NRS 1313 (required for all contracts) |  |  |  |  |  | Safety Conditions | Schedule F |  |  |
| NRS 1315 |  |  |  |  |  | SAFE Certification Requirements | Schedule G |  |  |
| NRS 1-H Tax Verification |  |  |  |  |  | For contracts >$100,000 | Schedule H |  |  |
| NRS 776 Camp Standards |  |  |  |  |  | Include if potential for camp to be established | Schedule I |  |  |
| NRS 999 Subcontracting Schedule |  |  |  |  |  | Subcontracting Schedule | Schedule J |  |  |
| POTENTIAL ADDITIONAL SCHEDULES TO INCLUDE (Surveys) - All Located in RESOURCE_TSK\Contract Prep Package\!SILVICULTURE\Surveys |  |  |  |  |  |  |  |  |  |
| BA specific |  |  |  | GIS Standards (if applicable list as sch C - #) |  |  |  | Schedule __ |  |
| BA specific |  |  |  | GPS Standards (if applicable list as sch C - # ) |  |  |  | Schedule __ |  |
| BA specific |  |  |  | Cold Storage etc. |  |  |  | Schedule __ |  |
| BA specific |  |  |  | Traverse & Layout (if applicable list as sch C - # ) |  |  |  | Schedule __ |  |

| APPENDICES (Contract dependent) Silviculture Operations only are PL, BR, JS |  |  |  |  |
| --- | --- | --- | --- | --- |
| Specimen NRS 1354 Prime Contractor |  | Must be included in every contract as it is not necessarily executed at the time of contract award make as a separate document for execution when required |  |  |
| Tax Verification Appendix |  | Attach to support the Tax Verification Schedule |  |  |
| ESA Advisory Bulletin March 23, 2011 ICS Advisory Bulletin March 22, 2011 |  | Employment Standards Act (ESA) and Industrial Camp Standards (ICS) - Advisory bulletins Located on our policy webpage https://www2.gov.bc.ca/gov/content/industry/forestry/bc-timber-sales/policy-legislation Include the above link in the Information to Bidders document |  |  |
| NRS776a_ CS_Inspection |  | Camp Standards Inspection Form (for PL, BR, JS Ops) |  |  |
| NRS791B |  | Work Progress Plan (or integrate into Schedule C) |  |  |
| Planting Risk Matrix |  | Planting only – form on CQMS website under “planting contracts”: https://intranet.gov.bc.ca/flnrord/bcts/finance-procurement/cqms/forms |  |  |
| NRS 1235 |  | Copyright Assignment (for receiving deliverables – i.e. survey contracts) |  |  |
| NRS 1235a |  | Waiver of Moral Rights (for receiving deliverables – i.e. survey contracts) |  |  |
| ATTACHMENTS |  |  |  |  |
| Maps |  | Project map (current status, detailed access) and Overview maps |  |  |
| KMZ files |  | Google map block locations |  |  |
| Prescriptions |  | Signed prescriptions |  |  |
| Photos |  | Recommended to put into a pdf format - then compress |  |  |
| Report templates |  | Example reports and maps |  |  |
| Block List (optional) |  | Block details - create a spreadsheet with the list of blocks in the contract. Add comments, access notes, location, hectares, etc. |  |  |
| Business Administrator generated: |  |  |  |  |
| Feedback Form | Tender Quality Feedback Form (HQ) |  |  |  |
| WP0037B | Tenders Received Log |  |  |  |
| WP0010B | Invitation Letters (selection invitation contracts only) |  |  |  |
| !FS280 | Contract Opening Record |  |  |  |
| Planting Contracts only: | Continuous Bid Deposit Declaration Form |  |  |  |
| Planting Contracts only: | BCTS Planting Contractor Rating System - FAQ 2020 |  |  |  |
| Planting Contracts only: | BCTS Planting Contractor Value Added Evaluation form |  |  |  |
| Planting Contracts only: | BCTS Planting Contractor Rating Solicitation Directive |  |  |  |
| EVALUATION |  |  |  |  |
|  | Admin follows the ONE FLOWSHEET for Tender opening processes then forwards contract file to the CC |  |  |  |
| NRS 1305 – Reference Checks – Sample Qs | Reference Check / Statement of Experience Contractor Evaluation Sharepoint site |  |  |  |
| POST AWARD |  |  |  |  |
| BCTS- EMS CHK-004 | Silviculture Pre-work (for EMS/Safety file) EMS Certification website |  |  |  |
| BCTS- EMS CHK-008 | Silviculture Inspections (for EMS/Safety file) |  |  |  |
| FS775a_WorkerInspec | Inspection Form – Compliance with Employment Standards / Silviculture Worker (for PL, BR, JS Ops) |  |  |  |
| FS775b_ContractorInspec | Inspection Form – Compliance with Employment Standards Branch (Silviculture Contractor) (for PL, BR, JS Ops) |  |  |  |

| CONTRACT CLOSURE |  |  |  |
| --- | --- | --- | --- |
| NRS 687 | Contract Completion Certificate (part of completion checklist) |  |  |
| NRS 688 | Contract/Contractor Evaluation Form (part of completion checklist) - Signed by Contract manager (QR) & program manager (EA) then sent to Contractor |  |  |
| BCTS Planting only | BCTS Planting Contractor Rating System Evaluation Form - CC completes, countersigned by contractor, then sent to contractor & share-point BCTS Contractor Planting Rating System! Sharepoint |  |  |

Further Information:

Option to Renew Contract?  For Year 2 or greater you will need:

- Review the CSNR website for policy information.

- At Year 2 or 3: Contract Modification Agreement NRS 600 – (include clauses, OTR dates, schedules being replaced) and Contract Amendment Rationale NRS 1353, including Cost Estimate and Rationale

- Schedule B replacement, maps

- Other relevant changes that came into effect (e.g. Insurance requirements)

Direct Award Contract you will need:

- A completed and approved NRS 1353 and potentially a Notice of Intent to Direct Award.  Research further if this is a large value contract or repeat direct award for similar work

- All of the above Checklist Information except for the following:

- Invitation to Tender, Conditions of Tender, Tender offer form & envelope

- Tender Received Log, Invitation Letters, Contract Opening Record

Other Schedules/Appendices

Loan Agreement for Digital Map Products required?  Note: When BCTS/GOV shares internal digital data or some Provincial digital data that is required to complete contract work (eg. LiDAR, specialized sat images, provincial First Nations data). If yes, include this document.  Generally not an issue with silviculture contracts

Other Resources

- Contract Procurement CSNR

- BC Procurement Resources

Definitions

CC  contract coordinator

EA  expense authority

HQ  headquarters

Prepared by:  Ellery Tetz and Val Parr for Skeena TSO

Revised by: Liz Wass (April 5th, 2022)

Province Revision by Tanja Armstrong- Whitworth, Forest Investment and Reporting Branch