
	[image: H:\BC_FLNR_H_CMYK_sanBPOE_pos.jpg]
	Schedule C
Supplementary Specifications


File:  10005-40/PL
Attachment to the Agreement with                       . for Tree Planting 
Project Logistics
[bookmark: _Hlk79740433]	Spring planting is expected to start early spring under snow-free conditions and must be completed by June 21, 2021.
1. The Ministry Representative reserves the right to limit the amount of blocks open at one time in line with the following guidelines, unless otherwise authorized in writing:
	
crew size under 20 persons	

	
      1 block (+/- 60 ha’s)

	
crew size 21-40 persons
	
       2 blocks (+/- 120 ha’s)


	
crew size 41-60 persons   

	     
       3 blocks (+/- 180 ha’s)


	
crew size 61+ persons	
	
       4 blocks (+/- 220 ha’s)	



GENERAL ACCESS INFORMATION
1.02	It is the responsibility of the Contractor to provide appropriate access for trees, equipment, and personnel.  This may include the use of helicopter transport, ATV, or walking into units. It may also include the building of quad bridges or ditch and stream traversing devices.
1.03	Access within the planting site shall be the responsibility of the Contractor.  Any modifications made by the Contractor to mitigate poor access must be restored to its original state after planting completion.
[bookmark: _Hlk79742237]3.	Daily production numbers are to be communicated daily to the Implementation Contractor.  Phone or e-mail communication is acceptable.	
4.	When developing the work progress plan, some blocks will be required to be planted at a specific time.  Failure to complete the planting of any one block will result in a $5,000.00 fine subject to each individual instance.	
5.	Danger tree assessment
· Danger trees must be assessed prior to planting each unit.
· Assessments must be done as per approved Wildlife Danger Tree assessment procedures and by a certified assessor.
· A tree assessed as dangerous must be felled prior to planting.	
· A No Work zone may be utilized for the following conditions:
· 	it is unsafe to fall the tree: and/or
·  high value wildlife trees.
· Danger trees must be felled by a certified faller and must be accompanied by a qualified falling supervisor.  A copy of the Faller Certificate and the BCFSC Falling Supervisor Certificate is required.
· A copy of the assessment must be submitted to the Implementation Contractor after planting is completed.
[bookmark: _Hlk79745872]6.	Where a field camp is used to provide accommodation for workers on Crown land, proposed locations must be provided twenty one (21) days in advance to the Ministry Representative to support the time it takes to status land and consult with stakeholders.  Short term Water permits are the sole responsibility of the contract holder and must be applied for through Front Counter BC.
Planting Specifications
7.	Prescription details located on the final contract maps are to be followed by the Contractor. These maps will be delivered to the Contractor prior to planting startup and thus making all other previous viewing versions void.  It is the Contractor’s responsibility to ensure they refer to the appropriate maps for planting activities.


Excess charges – when determining an excess tree, M+1 will be used to calculate and record excess trees.  Example:  Planting prescription 1400 M=7.  An Excess tree will be calculated when a plot exceeds M+1=8.  The Excess tree will be the 9th tree in this example.


8.	Minimum Acceptable Density 
	Target Density
	Minimum Acceptable Density

	2000 well spaced per hectare
	1800 well spaced per hectare

	1800 well spaced per hectare
	1600 well spaced per hectare

	1600 well spaced per hectare
	1400 well spaced per hectare


 	Areas with lower than minimum densities will be subject to Article 5.5 of the Schedule A.
9.	Acceptable crop trees 
	Heights
· Minimum height for existing trees to be recognized is fifteen centimetres (15 cm).
· Unless otherwise described in the planting prescription.
Appearance
· good color and vigor, with a dominant leader; as described on site;
· greater than fifty percent (50%) live crown;
· no visible damage, pest or disease whatsoever;
· scarred and bent trees due to logging damage are not acceptable;
· germinates that have just surpassed five centimetre (5 cm) in height and have not yet expressed a dominant leader are considered acceptable; and
· the Silviculture Surveys manual damage criteria may be used in the determination of an acceptable crop tree.


10.	Preferred planting microsites in order of preference are:
· within twenty centimetres (20 cm) of any stump or large obstacle; obstacles such as logs and rocks must be twenty centimetres (20 cm) in height to be considered a preferred microsite;
· undisturbed natural high spots;
· mineral soil or an acceptable mixture of mineral soil and organic matter; and
· where the site is prepared by mounding or disc trenching, planting in between the site preparation may be required to ensure target densities are met.

Note:  When a preferred microsite is available at the prescribed spacing but is not used, a planting fault may result.  For example, if a stump is available to plant beside but the seedling is planted greater than twenty centimetres (>20 cm) from the stump in mineral soil, a planting fault may result.
Unacceptable planting microsites further to Section 3.5 of the Schedule “A” are:
· cutbanks, roadside fill, loose humps or soil, gravel or debris subject to drought; and
· within one and a half metres (1.5 m) either side from the centre-line of fences, or as stated in the SP.
11.	Mixed Bag Planting: The Contractor may be required to plant a mixture of species in certain locations specified in planting prescription as per operational maps.
12.		Silvacool liners must be used by all planters and they must be in all bags including the draw bag.
12B.     Plastic ribbon cannot be used where it is not tied a minimum of one point three meters (1.3m) from the ground with a double knot. 

Cold Storage and Thawing
14.		The Contractor is responsible for thawing notices submitted to Williams Lake Cold Storage and/or Quesnel Cold Storage. 
[bookmark: _Hlk79743157]15.		From the day that the trees are scheduled for pick up upon completion of thaw, the planting contractor has seven (7) days to have the trees planted.  Trees not planted within the seven (7) days will be considered wasted trees as per 5.8 of the Schedule A. Unless otherwise approved in writing by the Ministry Representative.
16. Further to Schedule "A", Section 2.10, the Contractor must supply refrigerated storage for the storing of trees.
17.		Seedling cartons are to be returned to Williams Lake Cold Storage in the following manner:
· cartons are to be emptied and flattened and put on specific pallets that will be left outside of the Williams Lake Cold Storage building;
· cartons are to be stacked 100/pallet;
· plastic lining is to be taken out and put into one liner and tied; and
· plastic lining is to be disposed of in an appropriate recycling or waste site.
18.	The Contractor must adhere to the Williams Lake Cold Storage, “Cold Storage Guidelines” as set out in Schedule G.
Deliverables
19.		List of deliverables to be handed in to the Implementation contractor within forty-eight 
(48) hours of the completion of each unit, late submissions may be assessed at $100.00 per day, per block:
· map showing request key & Seedlot information, number of trees planted;
· area planted, area not planted;
· wildlife danger tree assessment (signed);
· safety reports and any incidents; 
· EMS documents; 
· deliverables must be of high quality, clean, and legible to be acceptable for being placed on our BCTS files; and
· balanced and complete total trees planted spreadsheet.
· Failure to deliver in a timely manner, may result in an assessment of five hundred dollars ($500.00) per day for each day that the report is not submitted to the Implementation Contractor. 
Final invoice must include a Balance Spreadsheet of total trees planted per Planting Unit (PU) for the entire project.   
Access and road maintenance

21. 		Helicopter Use:  The operating cost of helicopter access will be the responsibility of the Contractor.
22.	Damage to Roads
The Contractor must ensure their use of forest roads does not affect the structural integrity of the roads and does not result in a harmful impact to the environment.


	It is the responsibility of the Planting Contractor to report to the contract officer(s) by email/written/verbal any road damage noticed on routes to and from the worksite. Pre-existing road damage should be identified, photographed and reported prior to use.
If the contractor perceives that damage to a road is a “Safety concern”, the contractor shall
· submit a report of the safety concern with a 15-1 incident report form (provided during the prework), including photos of the road issue, to the Ministry Representative; and
· also mark or delineate the road damage or safety concern in the field via the use of appropriate flagging, ribbon, or other means to warn other traffic.
1.05	The Contractor must report any road damage caused by planting vehicles that may require road repair with the same methods as above. 
Planting Contractors who cause damage to forestry roads or road structures may be responsible 
for the associated repair costs.  Any anticipated road damage should be discussed with the 
Ministry Representative prior to road use to explore alternate blocks or mitigation measures, and to limit charges to the Contractor.
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