FFESC final report Oct 2011:

Soil and Ecological Baseline Data: Improvement and Delivery
 consisting of two interrelated components:

Part a (Soil):  Soil / terrain database & map

Part b (Ecology): Ecological baseline data delivery

- MFR project leader:

Chuck Bulmer

Research Branch, BC Ministry of Forests and Range

3401 Reservoir Rd

Vernon BC V1B 2C7

Phone 250-260-4765

Email chuck.bulmer@gov.bc.ca

- Recipient of FFESC grant (contractor) and contact information:

  - ($40,000) various

  - ($20,000) Russell Klassen 1351 Moncton Road Smithers, BC  V0J 2N4, 250-847-1764 russk@bulkley.net

- Project title:

Soil and Ecological Baseline Data: Improvement and Delivery

- Geographic focus:

Provincial

- Purpose of project:

  - Improve the accessibility of existing soil survey information and explore the use of predictive techniques to generate new information for soils throughout BC

  - Provide access to the provincial ecosystem plot database, create tools for common data summaries, and undertake specialized data summaries as required for FFESC projects

- Short description of how the project achieves FFEI objectives

  - Soil: Millions of dollars have been invested over several decades in collecting and organizing information on BC’s forest and range landscapes and soils. Much of this information consists of soil survey data that was collected before the widespread application of digital mapping technologies. Significant amounts have also been spent mapping British Columbia’s geological resources, terrain, and ecosystems. Despite this, limited budgets have slowed the incorporation of this information into readily accessible spatial databases that are needed to perform modeling of climate change effects throughout the diverse landscapes of British Columbia. At the same time, new technologies and the development of improved techniques for using computer based mapping methods provide the opportunity to economically create a provincial scale map of edaphic units. This portion of the project will take advantage of this large amount of existing information, and use automated methods and other approaches to make it more available to scientists and land managers developing strategies for adapting to climate change.

  - Ecology: The provincial ecosystem plot database is the most comprehensive data source for ecosystems and species distribution in British Columbia. This is important baseline information for understanding the functional constraints for key species and ecological processes and forecasting and monitoring ecosystem changes. This information is also being used to forecast how a range of climate change scenarios might alter key species and ecological processes over time.

- Summary of progress towards key deliverables:

  - Soil component:

    - Work with terrain / soil specialists at MoE to improve soil and terrain datasets, and facilitate access to digital data as improvements are made. (completed Oct 2011).

    - Evaluate models for classifying landscapes as a precursor to predictive soil and terrain mapping, produce a detailed landscape classification for the Okanagan Basin and a first approximation of a landscape classification for the entire province at 1 ha resolution (completed see Appendix 1,2).

    - Evaluate the SOLIM software package for predictive soil mapping on a pilot area (Okanagan Basin) (completed Oct 2011).

  - Ecology component (all aspects completed):

    - Data additions: incorporate new data into provincial database delivered by FFESC projects

    - Update existing soils and terrain data in Ecosystem database

    - Create data summary tool: Soils and Terrain data summary tool

    - Create mensuration and stand alone FS882 data entry modules

    - Populate mensuration data tables with existing digital data.

    - Create export function to CruiseComp

    - Provide technical support in the use of VPRO07 and the provincial ecosystem plot data set

    - Update programming to ensure proper function

- Discussion of progress

  - Soils component

  - Research process: A number of approaches were followed to achieve the project goals, but the most common activity involved manipulation of spatial data in a geographic information system to carry out the following:
(1) Over the course of our first year, several approaches to landscape classification were evaluated and a considerable amount of time was spent gaining familiarity with the various software packages that are available to carry out landscape classification. Much of this work was carried out at Simon Fraser University.
(2) At the same time, other members of the project team worked to better understand the role of a landscape classification in digital soil mapping and how to incorporate a landscape classification into a digital soil map, some of this work which was made possible by funds received through the former Ministry of Forests Research program. Two field trips were undertaken to northwestern BC to gain familiarity with soils in that remote part of the province where very little detailed soil information is available.
(3) In the second year, Brandon Heung began studies towards his MSc under the supervision of Dr Margaret Schmidt. Brandon’s work involves carrying out inference modeling of soil conditions as they are affected by topography and other factors at three locations in southern BC, and assigning soil attribute information to the resulting maps. In the Okanagan, field programs were carried out in the Winfield area and at Pennask Lake during 2011, and Brandon also made preliminary evaluations of soil conditions in the Mission area of the Fraser Valley.
(4) Finally, some geoprocessing work was carried out to make improvements to digital soil datasets which are the responsibility of the BC Ministry of Environment, and for which there is ongoing demand from the modeling community . 

The project team held regular meetings and was also able to collaborate through the use of the AgriForum online collaboration environment available at Agriculture and AgrFood Canada. As a result of these efforts, significant progress was made towards the overall goal of matching the knowledge of soil scientists with the power of geographic information systems and towards the ultimate goal of producing high quality spatial information on the soils of BC. 

Research progress: Progress involves key accomplishments in several areas, including;

    - Evaluate various approaches to landscape classification.. With assistance from Bob MacMillan, a simple landscape classification method was tested and calculations were made for all areas of the province. The relative hydrologic slope position describes the hydrologic position of a cell within its local flow path and is determined by dividing the cell’s catchment area into the total catchment area for both the upslope and downslope local flow paths. This simple value provides information on the cell’s position in the landscape and is being used as an input in our digital soil maps. More information and a detailed workflow  is provided in Appendix 1. An evaluation of the LandMapR output was carried out at SFU, and results are presented in Appendix 2. In early 2011, we uploaded two topographic datasets to hectares bc (www.habc.org):  The relative hydrologic slope position (rhsp) and  multiresolution index of valley bottom flatness (mrvbf: Gallant and Dowling 2003).

    - Evaluate the SOLIM package for digital soil mapping.. Early on in our work, we learned that an ArcGIS extension called ArcSIE was complementary software to SOLIM and implemented all of the functionality of SOLIM within the ArcGIS software environment. From that point on we used ArcSIE exclusively for implementing soil inference in our digital soil map. The project team has become familiar with the use of ArcSIE to create a digital soil map, and a first approximation was prepared of a detailed soil map of the Okanagan basin. This work was the subject of the presentation to the DSM 2010 meeting in Rome Italy, and is described in Appendix 3 (Rome). Inference modeling was also used by Brandon Heung to generate a soil attribute map for the Winfield area, and this work was described in a poster session by B Heung et al. (October 2011; included in this report as Appendix 4a).

    - Improving existing datasets.. As a result of discussions within the project team, a project was devised and (external) funding was approved to develop a vector format soils dataset of ‘best available’ information from soil surveys that have been conducted in BC since the 1960’s. This dataset will be made available and will provide a single summary of soils information for the entire province. Funding was arranged within the (former) Ministry of Forests Research program. The work was completed under contract in March 2011, and the “soil prototype” dataset is still undergoing improvement. While the initial effort was  not supported directly by FFESC funds, in year two we allocated a small amount of project funds towards improvements to the BC portion of the Soil Landscapes of Canada (v2r2 and 3r2) datasets, and to the BCSIS soil dataset which contains information from more than 25000 individual soil pits. Geoprocessing results for the BCSIS dataset are presented in Appendix 5. These examples provide evidence of how the funding received from FFESC has been leveraged to create results far beyond what was initially planned.

  - Collaboration: Our team worked in a collaborative environment within our group as well as externally. At the outset of the project we became aware of several groups carrying out similar work in British Columbia and Canada. These include people working for the Canadian Forest Service (B Titus, B Amichev), Agriculture and AgriFood Canada (B Daneshfar) and others. At our project update meeting in October 2010, several of these people participated via conference call. These collaborations continued in 2011 and resulted in a joint presentation (made by Scott Smith) to the Soil Science Society of America annual meeting in San Antonio TX (Appendix 4b).

  - Communication: The following presentations were made (selected summaries are included in Appendix 3);

    - Feb 2010: presentation to Research Branch Seminar Series (C Bulmer)

    - March 2010: Presentation to Canadian Forest Service researchers (S Smith and C Bulmer)

    - March 2010: meeting with digital soil mappers in Morgantown West Virginia (S Smith and E Flager)

    - June 2010: DSM 2010 (Rome Italy) S Smith and C Bulmer

    - Oct 2010: Global soil map.net update meeting Ottawa (E Flager, C Bulmer, S Smith)

    - Aug 2011: Team meeting with Ag Canada scientists at Summerland (B Heung, C Bulmer)

    - Oct 2011: Field Presentation to PRSSS soil scientists (C Bulmer)

    - Oct 2011: Poster presentation to SSSA annual meeting San Antonio TX (B Heung, M Schmidt, C Bulmer, S Smith)

    - Oct 2011: Oral presentation to SSSA meeting San Antonio TX (S Smith, C Bulmer)

  - Deviations from project plan: There were no significant deviations from the project plan

  - Research Outcomes: Detailed discussion of the results can be found in the Appendices. To summarize, we have gained significant ability to generate digital soil maps from spatial data. Validation of the map outputs is a significant challenge that will require ongoing field work. We are confident that our methods will form the basis for improved soil mapping in British Columbia.

  - Recommendations: The following activities should be carried out..

    - Continue to explore methods for predictive soil mapping

    - Continue to improve digital datasets that are the responsibility of the BC Government. These datasets are an important foundation for all predictive soil mapping in BC.

    - Work to integrate soil datasets with  information in other terrestrial datasets (BEC, PEM, TEM).

    - Develop interpretive soil maps for attributes such as C, texture, and forest floor depth.

    - Field checking of maps using protocols similar to those used in predictive ecosystem mapping.

  - Extension of Research outcomes: These are described under “Communication”

  - Utility of FFESC research program: The FFESC research program provided an important contribution to improving existing soil datasets, and for developing new soil information in British Columbia. Since our initial funding was approved almost 2.5 years ago, there has been renewed interest in the work to improve soil mapping, and much of this renewal was built on the credibility given to the initiative when we received funding from FFESC. The project team appreciates that early support, and we believe it will represent  an important legacy of the FFESC program.

8.2 Ecology component

- Research process: This work aimed to provide access to the provincial ecosystem plot database, create tools for common data summaries, and undertake specialized data summaries as required for FFESC projects

- Research outcomes:  (completed October 31 2010):

  - Data additions: incorporate new data into provincial database delivered by FFESC projects. 
..  500 new ecosystem plots added to provincial repository

  - Update existing soils and terrain data in provincial ecosystem plot database.
.. Soils and terrain data for 50,000 ecosystem plots were reviewed and updated to contemporary data standards

  - Create data summary tool: Soils and Terrain data summary tool
.. Tool to extract and summarize soils horizon data for FFESC project to develop a stand-level climate change risk assessment and decision support tool to assist forest managers in evaluating options for minimizing tree-mortality risk, and making strategic forest investments in response to a rapidly changing climate (Craig Delong – Lead)

  - Create mensuration and stand alone FS882 data entry modules
..  Stand-alone database tool created for mensuration data (V-Trees)
.. Stand-alone database tool created for coarse woody debris data (V-CWD)
.. Tools are currently posted for download at http://vuser.ca/

  - Populate mensuration data tables with existing digital data.
.. Forest mensuration data for 3370 ecosystem plots was acquired and compiled into V-Trees format
.. Mensuration data summaries were not created. Awaiting guidance from silviculturalists

  - Provide technical support in the use of VPRO07 and the provincial ecosystem plot data set
.. Technical support for Vpro07 supplied to provincial and federal government users.
.. Technical support for Vpro07 supplied to industry and consultants users

- Recommendations: The provincial database of ecosystem plot information has been mined extensively for research and management projects requiring information on  species and ecosystems distribution. Newly compiled information on soils and stand structure extend the possible uses of this dataset to baseline ecosystem condition for management and modeling.

- Extension of research outcomes: We are awaiting government terminal server system upgrades for release of new tools programming.

- Project budget:

  - Soil: $40,000 – $40,000 = $0 balance

  - Ecology: $20,000 – $20,000 = $0 balance

Appendix 1:

Relative Hydrologic Slope Position

Purpose: This dataset is used for terrain analysis as an input to landscape classification and predictive mapping of soils and ecosystems.

Characteristics: Relative hydrologic slope position (RHSP) is a measure of flow accumulation (catchment area) relative to a pixel’s nearest peak and pit. A value of zero indicates the cell has no catchment area i.e. it is a local peak or ridge top. A value of 1 means the pixel is located adjacent to a stream channel. Stream channels are defined as having a catchment area of more than 2,000,000 cells in the current version of the dataset, although this value can be changed. No evaluation has been carried out of the effects on RHSP of varying the stream channel threshold. Because it is based on the normal and inverted DEMs, RHSP defines both a pixel’s wetness relative to its neighbours that flow to the same pit, as well as its ‘dryness’ relative to neighbours that share a (notional)  flow path to the same peak.

Calculation: RHSP is determined as the ratio of a pixel’s catchment area and the sum of the catchment areas for the normal and inverted dems. All calculations were performed in SAGA on the HABCbs grid after using ArcGIS to ‘burn in’ the drainage network and then  applying 3 successive mean filters (3x3, 3x3, 5x5), then finally burning in the drainage network again.

Workflow:

- Burn and smooth DEM (ArcGIS):

  - Input HaBC dem (www.habc.org)

    - Reclassify all values <1m to zero

  - Input 	BC’s streamnetwork shape file

  - select all segments 3rd order and higher, and create a new layer

  - Feature to raster, and create a raster layer with stream pixels as 1, all others as 0

  - Raster calculator: subtract stream layer from DEM

  - Spatial analyst tools>Neighbourhood>Focal statistics>mean 3x3, 3x3. 5x5

  - Raster calculator: subtract stream layer from DEM

  - OutputHaBCbs (burn smooth)

- Prepare overlapping sub - grids (SAGA)

  - Input  HaBCbs burned smoothed provincial DEM

    - Module Import/Export – Grids Import Esri Arc/Info Grid

  - Clip grid to 8 overlapping  ‘chunks’ to allow small computer to process

    - Module Grid – Tools – Cutting interactive

  - Output SAGA grids  a_HaBCbs; b_HaBCbs; etc

- Calculate RHSP on subgrids (SAGA)

  - Input  a_HaBCbs

    - File – Load grid – a_HaBCbs

  - Prepare inverse DEM

    - Module Grid Tools – Grid Orientation – Method Invert

    - Output  a_inv_HaBCbs

  - Determine catchment area for a_HaBSba and s_inv_HaBCbs

    - Module Terrain Analysis – Hydrology – Parallel Processing – Catchment Area

    - Output  a_Catcharea_HaBCbs; a_inv_catcharea_HaBCbs

  - Truncate a_catcharea_HaBCbs at 2,000,000 cell threshold

    - Module Grid – Calculus – Grid Calculator:  [gt(a,2000000)]… Output b

    - Module Grid – Calculus – Grid Calculator: [a +(b*(2000000)-a))]… Output  a_trunc_catch_HaBCbs

  - Calculate RHSP

    - Load grid a: a_ trunc_catch_HaBCbs

    - Load grid b: a_inv_ trunc_catch_HaBCbs

    - Module Grid – Calculus – Grid Calculator: [a/(a+b)]… Output  a_RHSP

    - Repeat for all other sub-grids

  - Merge sub-grids

    - Input  a_RHSP; bRHSP; etc etc

    - Module Grid tools – Merging

    - Output  BC_rhsp_combined

Appendix 2:

pdf file “Appendix 2 DSM-reports on Landscape Classification” was submitted with Interim report

Appendix 3:

pdf files “Appendix 3 Presentation1,2,3” were submited with interim report

Appendix 4:

See attached pdf files “Appendix 4 Data history journals”

Appendix 5:

See attached pdf files “Appendix 5 SSSA poster”

Gallant, JC and TI Dowling 2003. A multiresolution index of valley bottom flatness for mapping depositional areas. Water Res. Res. 39:1347-1359.