## owssvr(1)
ID | REMEDY # | PTWeb | Priority | Description | Release: | Type | Item Status | Action Status | Reported By | Application | Category | Created | Created By | Users Notified | Assignee | Screen ID | Item Type | Path
182 | 118618 |  | Critical | Processing error on job server | Not yet scheduled | Bug | Open | Approved for Implementation | Winter, Ralph FOR:EX | RESULTS;#RESULTS Reports | Reports | 2010-10-27 10:58 | Akerley, Scott C FOR:EX | FALSE | Yee, Ricky FOR:EX | N/A | Item | results/Lists/BugsEnhancements
181 | 118483 |  | Medium | An Opening can be created with out a CUT_BLOCK_OPEN_ADMIN record | Not yet scheduled | Bug | Open | Reported | Yee, Ricky FOR:EX | RESULTS | Opening | 2010-10-20 14:23 | Yee, Ricky FOR:EX | FALSE | Yee, Ricky FOR:EX | RESULTS302 - Add New Opening | Item | results/Lists/BugsEnhancements
180 | 118528 |  | Low | Veglots are not displayed on the RESULTS317 - Maintain Activity Detail screen | Not yet scheduled | Bug | Open | Reported | Yee, Ricky FOR:EX | RESULTS | Activities | 2010-10-19 13:29 | Yee, Ricky FOR:EX | FALSE | Yee, Ricky FOR:EX | RESULTS317 - Maintain Activity Detail screen | Item | results/Lists/BugsEnhancements
179 | 118354 |  | Medium | Expired Reserve Codes caused by IMM Polygon Inventroy layer with no Total Stems | Not yet scheduled | Bug | Open | Reported | Yee, Ricky FOR:EX | RESULTS | Forest Cover | 2010-10-18 10:40 | Yee, Ricky FOR:EX | FALSE | Yee, Ricky FOR:EX | RESULTS328 - Forest Cover Edit | Item | results/Lists/BugsEnhancements
178 | 00118495 |  | High | New Method Code for Forest Health: SDM – Stand Development Monitoring | Not yet scheduled | Enhancement | Open | Reported | MacLeod, Caroline FOR:EX | RESULTS;#ESF | Activities | 2010-10-15 09:54 | Akerley, Scott C FOR:EX | FALSE | Tsoi, Mei-Ching FOR:EX | RESULTS315 - Activities | Item | results/Lists/BugsEnhancements
177 |  |  | Medium | Field not easy to interpret and new field needed | Not yet scheduled | Enhancement | Closed | Reported | Howden, Brian (BHOWDE_P) | RESULTS;#LRDW;#RESULTS Reports | Reports | 2010-10-07 14:05 | Akerley, Scott C FOR:EX | FALSE | Yee, Ricky FOR:EX | Information from RESULTS 317 - Main activity details | Item | results/Lists/BugsEnhancements
176 | 116872 |  | Medium | Request for adhoc report | Not yet scheduled | Enhancement | Closed | Reported | Tsoi, Mei-Ching FOR:EX | RESULTS Reports | Reports | 2010-09-29 17:20 | Yee, Ricky FOR:EX | FALSE |  | N/A | Item | results/Lists/BugsEnhancements
175 | 116801 |  | Medium | Report - query for Forest Cover entry time stamp. | Not yet scheduled | Bug | Open | Reported | Yee, Ricky FOR:EX | RESULTS Reports | Forest Cover | 2010-09-29 17:18 | Yee, Ricky FOR:EX | FALSE |  | RESULTS320 - Forest Cover Summary | Item | results/Lists/BugsEnhancements
174 | 111924 |  | Medium | Dates are processed wrong | Not yet scheduled | Bug | Closed | Reported | Yee, Ricky FOR:EX | RESULTS Reports | Reports | 2010-09-16 12:33 | Yee, Ricky FOR:EX | FALSE |  | reports | Item | results/Lists/BugsEnhancements
173 | 00117984 |  | High | Submitting opening definition with Max soil then goes blank in RESULTS. | Not yet scheduled | Bug | Open | Approved for Scheduling | IDIR\FVARGA | RESULTS;#ESF | Standard Units | 2010-08-27 14:08 | Akerley, Scott C FOR:EX | FALSE | Yee, Ricky FOR:EX | RESULTS310 - Stocking Standards | Item | results/Lists/BugsEnhancements
172 | 111035 |  | Critical | Make SSID's optional for Woodlots | Not yet scheduled | Datafix | Closed | Business Analysis Complete | Barron, Patricia FOR:EX | RESULTS;#ESF | SSID | 2010-08-16 15:31 | Akerley, Scott C FOR:EX | FALSE | MacLeod, Caroline FOR:EX | RESULTS310 - Stocking Standards | Item | results/Lists/BugsEnhancements
171 |  |  | Low | Area/Length missing - future spatial view enhancment for Business Views | Not yet scheduled | Enhancement | Open | Reported | McClung, Melinda | RESULTS;#LRDW;#RESULTS Reports | Reports | 2010-08-16 12:58 | Akerley, Scott C FOR:EX | FALSE | MacLeod, Caroline FOR:EX | OPENING_SVW & FOREST_COVER_INV_SVW | Item | results/Lists/BugsEnhancements
170 | 00117865 |  | High | Tech spec update needed for SP Exempt button meaning | Not yet scheduled | Maintenance | Open | Reported | Pawlak, Magda FOR:EX | RESULTS | Opening | 2010-08-12 16:41 | Akerley, Scott C FOR:EX | FALSE | MacLeod, Caroline FOR:EX | RESULTS301 - Opening Inquiry | Item | results/Lists/BugsEnhancements
169 | 00117512 |  | High | NSR Report including retired opening information. | Not yet scheduled | Enhancement | Open | Submitted for Business Analysis | Tsoi, Mei-Ching FOR:EX | RESULTS;#RESULTS Reports | Reports | 2010-07-22 16:28 | Akerley, Scott C FOR:EX | FALSE | Yee, Ricky FOR:EX | N/A | Item | results/Lists/BugsEnhancements
168 | 112104 |  | Medium | FFT block was split into two SU's when it was in FG status. | Not yet scheduled | Bug | Open | Reported | Godin, Tracey | RESULTS | Standard Units | 2010-07-16 14:09 | Akerley, Scott C FOR:EX | FALSE | MacLeod, Caroline FOR:EX | RESULTS310 - Stocking Standards | Item | results/Lists/BugsEnhancements
167 |  |  | High | Cannot enter amendment if SSID has expired. | Rel 4.02 | Bug | Open | Reported | Yee, Ricky FOR:EX | RESULTS | Function | 2010-07-14 16:17 | Akerley, Scott C FOR:EX | FALSE |  | RESULTS312 - Stocking Standard Amendment Request | Item | results/Lists/BugsEnhancements
166 | 115868, 115187 and 116003 |  | Medium | Data from amalgamations seem to be lost or placed in incorrect areas | Rel 4.02 | Bug | Open | Reported | Tsoi, Mei-Ching FOR:EX | RESULTS | Function | 2010-07-14 15:54 | Akerley, Scott C FOR:EX | FALSE | Yee, Ricky FOR:EX | RESULTS345 - Opening Amalgamation | Item | results/Lists/BugsEnhancements
165 | 117222, 117238, 117549, 117845 |  | Low | Results wanting spatial data for amendments on blocks that never had spatial data before on amendments to LFG | Not yet scheduled | Datafix | Open | Business Analysis Complete | Jack.Sweeten | RESULTS | Function | 2010-07-08 13:27 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 310 | Item | results/Lists/BugsEnhancements
164 | 00117525 , 116335 |  | High | Have batch job run to catch bad geometry submitted | Not yet scheduled | Enhancement | Closed | Implemented | Gallimore, John FOR:EX | RESULTS;#ESF;#LRDW | Function | 2010-07-06 15:49 | Akerley, Scott C FOR:EX | FALSE |  | N/A | Item | results/Lists/BugsEnhancements
163 | 112887 |  | Medium | add the opening status to the RDD011 report | Not yet scheduled | Enhancement | Closed | Reported | Minor, Carmen | RESULTS Reports | Reports | 2010-06-28 10:50 | Scott, Sharon FOR:EX | FALSE | Yee, Ricky FOR:EX | 300 | Item | results/Lists/BugsEnhancements
162 | 116800 |  | High | Possible report for Woodlots : RSLTRPT_REC_SIL_ACC.xls | Not yet scheduled | Enhancement | Open | Reported | Mooney, Stephanie J FOR:EX | RESULTS;#RESULTS Reports | Reports | 2010-06-23 13:38 | Scott, Sharon FOR:EX | FALSE | Johnson, Jeff FOR:EX | 300 | Item | results/Lists/BugsEnhancements
161 | 114940 |  | Medium | Crystal Reporting - Statistics for RESULTS | Not yet scheduled | Enhancement | Closed | Reported | Tsoi, Mei-Ching FOR:EX | RESULTS;#RESULTS Reports | Reports | 2010-06-23 13:25 | Scott, Sharon FOR:EX | FALSE | Yee, Ricky FOR:EX | 300 | Item | results/Lists/BugsEnhancements
160 | 112890 |  | High | code for calculating the Regen and Free Growing over due needs to be changed to match the changes to the screen. | Not yet scheduled | Enhancement | Closed | Reported | Deveau, Lauri K FOR:EX | RESULTS Reports | Reports | 2010-06-23 12:41 | Scott, Sharon FOR:EX | FALSE | Yee, Ricky FOR:EX | 300 | Item | results/Lists/BugsEnhancements
159 | 112300 |  | Medium | report not showing max prefer species as per results 310 screen | Not yet scheduled | Enhancement | Open | Reported | Deveau, Lauri K FOR:EX | RESULTS;#RESULTS Reports | Reports | 2010-06-23 10:50 | Scott, Sharon FOR:EX | FALSE | Yee, Ricky FOR:EX | 310 | Item | results/Lists/BugsEnhancements
158 | 112227 |  | Medium | Deveolpe business use reports for forest health users | Not yet scheduled | Enhancement | Open | Reported | Misener, Rebecca FOR:EX | RESULTS;#RESULTS Reports | Reports | 2010-06-23 10:37 | Scott, Sharon FOR:EX | FALSE | Yee, Ricky FOR:EX | 300 | Item | results/Lists/BugsEnhancements
157 |  |  | High | BEC code tables now on DBQ01 with latest changes | Not yet scheduled | Maintenance | Open | Reported | Gallimore, John FOR:EX | RESULTS | Admin | 2010-06-21 08:56 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 300 | Item | results/Lists/BugsEnhancements
156 | 117297 |  | High | RESULTS-removing Tree Species Code from Tech Spec, Help and the application | Not yet scheduled | Admin Fix | Open | Reported | MacLeod, Caroline FOR:EX | RESULTS | Admin | 2010-06-16 10:40 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 320 | Item | results/Lists/BugsEnhancements
155 | 117293 |  | Low | add an intermediary caution button to the attachment deletion toggle | Not yet scheduled | Enhancement | Open | Reported | Sacenieks, Kristine G FOR:EX | RESULTS | Function | 2010-06-16 08:20 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 401 | Item | results/Lists/BugsEnhancements
154 | 117233 |  | High | Major Amendment Spatial Problem | Not yet scheduled | Bug | Open | Reported | Yee, Ricky FOR:EX | RESULTS | Function | 2010-06-10 12:46 | Scott, Sharon FOR:EX | FALSE | Yee, Ricky FOR:EX | 201 | Item | results/Lists/BugsEnhancements
153 | 116923 |  | Low | enhancement suggestion to make Cenge/results interface better by populating the location field on the opening inquiry screen in RESULTS from a different field in Resources | Not yet scheduled | Enhancement | Open | Reported | Waines, Andy C FOR:EX | RESULTS | Function | 2010-05-18 09:35 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 301 | Item | results/Lists/BugsEnhancements
152 | 00116871 |  | High | Amendment sent in to combine SU's but did not combine all. | Not yet scheduled | Bug | Closed | Submitted for Vendor Technical Analysis | Akerley, Scott C FOR:EX | RESULTS;#ESF | Standard Units | 2010-05-14 14:44 | Akerley, Scott C FOR:EX | FALSE | Yee, Ricky FOR:EX | RESULTS312 - Stocking Standard Amendment Request | Item | results/Lists/BugsEnhancements
151 |  |  | Medium | defaults ssid causing both FDP and non-FTML FRPA obligated openigns to show as FRPA blocks | Not yet scheduled | Business Issue | Open | *Submitted for Vendor Technical Analysis | MacLeod, Caroline FOR:EX | RESULTS | Function | 2010-05-06 16:33 | MacLeod, Caroline FOR:EX | FALSE |  | Tombstone, Stocking standards | Item | results/Lists/BugsEnhancements
150 | 116967 |  | Low | Clocks starts ticking as soon as DN activity reported and should be user specified | Not yet scheduled | Enhancement | Open | *Submitted for Vendor Technical Analysis | MacLeod, Caroline FOR:EX | RESULTS | Milestones | 2010-05-06 16:25 | MacLeod, Caroline FOR:EX | FALSE |  | Activity | Item | results/Lists/BugsEnhancements
149 |  |  | Medium | Requested by the OIF group: review of current data requirement under regen delay reporting and streamlining process | Not yet scheduled | Business Issue | Open | Submitted for MFR Technical Analysis | MacLeod, Caroline FOR:EX | RESULTS | Forest Cover | 2010-05-06 16:19 | MacLeod, Caroline FOR:EX | FALSE | MacLeod, Caroline FOR:EX | forest cover | Item | results/Lists/BugsEnhancements
148 | 116755 |  | Low | RESULTS- problem approving amalgamations. glitch causes auto approvals. | Not yet scheduled | Bug | Open | Reported | Grainger, Mike FOR:EX | RESULTS | Function | 2010-05-05 11:44 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 201 | Item | results/Lists/BugsEnhancements
147 | 00116541 |  | Medium | Cannot view FC when confirmed it exists | Not yet scheduled | Bug | Closed | Reported | IDIR\PEBROCHE | RESULTS | Forest Cover | 2010-05-04 16:58 | Akerley, Scott C FOR:EX | FALSE | Gallimore, John FOR:EX | RESULTS336 - Forest Cover Map | Item | results/Lists/BugsEnhancements
146 | 116163 |  | Medium | Contractor has been entering NSR PL polygons as Reserves | Not yet scheduled | Datafix | Open | Submitted for MFR Technical Analysis | Barolet, Paul L FOR:EX | RESULTS | Forest Cover | 2010-04-23 16:38 | Akerley, Scott C FOR:EX | FALSE | MacLeod, Caroline FOR:EX | RESULTS320 - Forest Cover Summary | Item | results/Lists/BugsEnhancements
145 |  |  | Low | Summary report not working | Rel 4.02 | Maintenance | Open | Reported | Tsoi, Mei-Ching FOR:EX | RESULTS;#RESULTS Reports | Reports | 2010-04-21 10:21 | Akerley, Scott C FOR:EX | FALSE | Gallimore, John FOR:EX | RESULTS301 - Opening Inquiry | Item | results/Lists/BugsEnhancements
144 | 116539 |  | High | SP Exempt button active again. Prevents Woodlot owners from entering SU's | Rel 4.02 | Bug | Closed | Reported | Akerley, Scott C FOR:EX | RESULTS | Opening | 2010-04-16 17:05 | Akerley, Scott C FOR:EX | FALSE | MacLeod, Caroline FOR:EX | RESULTS301 - Opening Inquiry | Item | results/Lists/BugsEnhancements
143 | 116399 |  | High | NDFS block (beetle disturbance) FC submitted but not showing | Rel 4.01 | Bug | Closed | Reported | Scott, Sharon FOR:EX | RESULTS | Forest Cover | 2010-04-12 08:31 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 313 | Item | results/Lists/BugsEnhancements
142 | 116457 |  | High | report request that would enable us to enter either an individual woodlot licence number or select all woodlots in a district | Not yet scheduled | Enhancement | Closed | Reported | Mooney, Stephanie J FOR:EX | RESULTS Reports | Reports | 2010-04-07 08:20 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 300 | Item | results/Lists/BugsEnhancements
141 | 116335 |  | Critical | Spatial data submitted to the Layer is incorrectly configured | Not yet scheduled | Datafix | Closed | Implemented | Lanktree, Terry ILMB:EX | RESULTS;#ESF;#LRDW | Activities | 2010-03-30 09:27 | Akerley, Scott C FOR:EX | FALSE | Edwards, Cheryl FOR:EX | N/A LRDW Layer in Mapview | Item | results/Lists/BugsEnhancements
140 | 00116302 |  | Medium | When opening status changed to REMOVED, it is not totally locked down | Not yet scheduled | Bug | Open | *Submitted for Vendor Technical Analysis | Lester, Mary FOR:IN | RESULTS | Opening | 2010-03-26 14:43 | Akerley, Scott C FOR:EX | FALSE | Gallimore, John FOR:EX | RESULTS301 - Opening Inquiry | Item | results/Lists/BugsEnhancements
139 | 116274 |  | Medium | retire schema 3 | Not yet scheduled | Business Issue | Open | Reported | Bonar, Darren | RESULTS;#ESF | Function | 2010-03-22 09:03 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 311 | Item | results/Lists/BugsEnhancements
138 | 115443, 115818, 115884, 00117973 |  | High | Submitted SP amendments not showing up in the District In-Box | Rel 4.02 | Bug | Open | Approved for Scheduling | Jack.Sweeten | RESULTS | Function | 2010-03-16 12:02 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 311 | Item | results/Lists/BugsEnhancements
137 | 115930 |  | High | FRPA 197 new validation that will check if the current SSID in the SU is associated with ANY FSPs | Rel 4.02 | Enhancement | Closed | Submitted for Vendor Technical Analysis | Tsoi, Mei-Ching FOR:EX | RESULTS | Function | 2010-03-11 14:08 | Scott, Sharon FOR:EX | FALSE | Gillan, Stacey FOR:IN | 311 | Item | results/Lists/BugsEnhancements
136 | 115807 |  | High | Change in the Tech specs and online help for FRPA197 | Rel 4.02 | Admin Fix | Closed | Submitted for MFR Technical Analysis | MacLeod, Caroline FOR:EX | RESULTS | Admin | 2010-03-11 13:52 | Scott, Sharon FOR:EX | FALSE | Gillan, Stacey FOR:IN | 311 | Item | results/Lists/BugsEnhancements
135 | 113618 |  | High | Plan Amendment - Offsets not rippled upon addition of SS | Rel 4.02 | Bug | Closed | Submitted for Vendor Technical Analysis | Tsoi, Mei-Ching FOR:EX | RESULTS | SSID | 2010-03-11 11:10 | Scott, Sharon FOR:EX | FALSE | IDIR\SKILLAM | 311 | Item | results/Lists/BugsEnhancements
134 | 116167 |  | Low | RESULTS not checking against Silviculture system. | Not yet scheduled | Business Issue | Open | Reported | Akerley, Scott C FOR:EX | RESULTS | Activities | 2010-03-11 10:38 | Akerley, Scott C FOR:EX | FALSE | MacLeod, Caroline FOR:EX | RESULTS315 - Activities | Item | results/Lists/BugsEnhancements
133 | 115028 |  | High | SU scrolling navigation on RESULTS311 | Rel 4.02 | Bug | Closed | Submitted for Vendor Technical Analysis | Gillan, Stacey FOR:IN | RESULTS | Function | 2010-03-11 08:43 | Scott, Sharon FOR:EX | FALSE | IDIR\SKILLAM | 311 | Item | results/Lists/BugsEnhancements
132 | 115029 |  | High | SU's with multiple FSPs can have any FSp with FRPA197 election | Rel 4.02 | Bug | Closed | Submitted for Vendor Technical Analysis | Gillan, Stacey FOR:IN | RESULTS | Function | 2010-03-11 08:34 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 312 | Item | results/Lists/BugsEnhancements
131 | 116147 |  | Medium | rendered image bug with SP map rendering when ESF amendment submissions | Rel 4.01 | Bug | Closed | Reported | MacLeod, Caroline FOR:EX | RESULTS | Standard Units | 2010-03-11 08:18 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 312 | Item | results/Lists/BugsEnhancements
130 | 115965 |  | High | RESULTS CRS Reports make global access | Rel 4.01 | Unknown | Closed | Submitted for MFR Technical Analysis | Tsoi, Mei-Ching FOR:EX | RESULTS Reports | Reports | 2010-03-10 13:46 | Scott, Sharon FOR:EX | FALSE | Will, Mark R FOR:EX | 300 | Item | results/Lists/BugsEnhancements
129 | 115998 |  | Low | Request to enhance search function | Not yet scheduled | Enhancement | Open | Reported | Salzl, Mark FOR:EX | RESULTS | Function | 2010-03-01 13:21 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | Sil56 | Item | results/Lists/BugsEnhancements
128 | 115980 |  | Medium | edit raising the max planting densities from 3000 to 5000 | Not yet scheduled | Enhancement | Closed | Reported | MacLeod, Caroline FOR:EX | RESULTS | Activities | 2010-03-01 08:20 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 317 | Item | results/Lists/BugsEnhancements
127 | 115391 |  | High | problem with RESULTS / MAPVIEW data layer | Not yet scheduled | Maintenance | Open | Reported | Tsoi, Mei-Ching FOR:EX | RESULTS | Function | 2010-02-08 15:21 | Scott, Sharon FOR:EX | FALSE | Tsoi, Mei-Ching FOR:EX | 300 | Item | results/Lists/BugsEnhancements
126 | 115674 and 116009 |  | High | RESULTS -_ CRS Reporting Issue RDD011 giving different name and number for client vs results screen | Not yet scheduled | Bug | Open | Reported | Deveau, Lauri K FOR:EX | RESULTS Reports | Reports | 2010-02-08 08:46 | Scott, Sharon FOR:EX | FALSE | Yee, Ricky FOR:EX | 300 | Item | results/Lists/BugsEnhancements
125 | 115715 |  | High | The validation check incorrectly throws an error if the Post Harvest or Regen Milestone is declared | Rel 4.02 | Bug | Closed | Submitted for Vendor Technical Analysis | IDIR\SKILLAM | RESULTS | SSID | 2010-02-05 14:30 | Akerley, Scott C FOR:EX | FALSE | IDIR\SKILLAM | RESULTS 312 | Item | results/Lists/BugsEnhancements
124 | 115628 |  | Low | PAS Report including NP UNN & also "C" & "U" stocking status - issue with Land Status Table processing | Rel 4.01 | Maintenance | Open | *Submitted for Vendor Technical Analysis | Tsoi, Mei-Ching FOR:EX | RESULTS Reports | Reports | 2010-02-04 09:09 | Scott, Sharon FOR:EX | FALSE | MacLeod, Caroline FOR:EX | 300 | Item | results/Lists/BugsEnhancements
123 | 00115554 |  | Medium | Submission stuck in progress but all data seems to have migrated | Not yet scheduled | Unknown | Open | *Submitted for Vendor Technical Analysis | Akerley, Scott C FOR:EX | RESULTS;#ESF | Forest Cover | 2010-02-04 09:06 | Akerley, Scott C FOR:EX | FALSE |  | N/A | Item | results/Lists/BugsEnhancements
122 | 00115649 |  | Low | Update code table specifications to include new opening categories | Rel 4.02 | Maintenance | Closed | Submitted for Vendor Technical Analysis | Gallimore, John FOR:EX | RESULTS | Admin | 2010-02-02 09:54 | Akerley, Scott C FOR:EX | FALSE | Gillan, Stacey FOR:IN | Help link on all screens | Item | results/Lists/BugsEnhancements
121 | 115637 |  | High | need to align CRS, Business Views and VRIMS with new reporting Coding for treed Retention | Not yet scheduled | Maintenance | Open | Business Analysis Complete | MacLeod, Caroline FOR:EX | RESULTS | Function | 2010-02-01 15:02 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 300 | Item | results/Lists/BugsEnhancements
120 | 114896 |  | High | system allows an opening to be changed to non-primary when there is only one licence present. | Rel 4.01 | Bug | Open | Submitted for Vendor Technical Analysis | Rockley, Scott FOR:EX | RESULTS | Function | 2010-01-28 08:29 | Scott, Sharon FOR:EX | FALSE | Yee, Ricky FOR:EX | 301 | Item | results/Lists/BugsEnhancements
119 | 115498 |  | Low | No comment area specific to Amalgamations | Not yet scheduled | Enhancement | Open | Reported | Akerley, Scott C FOR:EX | RESULTS;#ESF | Standard Units | 2010-01-22 14:49 | Akerley, Scott C FOR:EX | FALSE |  | RESULTS130 - Comment Summary | Item | results/Lists/BugsEnhancements
118 | 115437 |  | High | RESULTS Attribute&Spatial Data - Recipients/Contractors working for FFT/FIA can access data themselves | Rel 4.01 | Business Issue | Closed | Reported | Tsoi, Mei-Ching FOR:EX | RESULTS;#RESULTS Reports | Reports | 2010-01-19 13:16 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 300 | Item | results/Lists/BugsEnhancements
117 | 115402 & 115705 |  | High | max soil disturbance error with minor amendment | Rel 4.02 | Bug | Closed | Submitted for Vendor Technical Analysis | Scott, Don A. PENC:EX | RESULTS | Standard Units | 2010-01-18 11:18 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 310 | Item | results/Lists/BugsEnhancements
116 | 115370 |  | High | need to align the reports (CRS) and business views with new coding (expired reserve codes) for reserve type code and new procedures. | Not yet scheduled | Enhancement | Open | Submitted for MFR Technical Analysis | MacLeod, Caroline FOR:EX | RESULTS | Reports | 2010-01-13 15:48 | Scott, Sharon FOR:EX | FALSE | Yee, Ricky FOR:EX | 300 | Item | results/Lists/BugsEnhancements
115 | 115250 |  | Medium | amendment of SU get error asking for stocking layer code | Rel 4.01 | Bug | Open | *Submitted for Vendor Technical Analysis | Rockley, Scott FOR:EX | RESULTS | Standard Units | 2010-01-06 10:28 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 310 | Item | results/Lists/BugsEnhancements
114 | 115168 |  | High | FC spatial only submission gets 316 action code missing | Rel 4.01 | Bug | Closed | Reported | Bonar, Darren | RESULTS;#ESF | Forest Cover | 2010-01-06 08:51 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 300 | Item | results/Lists/BugsEnhancements
113 | 115217 |  | High | RESULTS custom report function is MIA | Not yet scheduled | Query Request | Closed | Submitted for Vendor Technical Analysis | Tsoi, Mei-Ching FOR:EX | RESULTS;#RESULTS Reports | Reports | 2010-01-05 11:13 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 300 | Item | results/Lists/BugsEnhancements
112 | 115218 |  | Critical | previous FC submitted with all information but does not show the details in the FC or in the History | Rel 4.01 | Bug | Closed | Implemented | Akerley, Scott C FOR:EX | RESULTS;#ESF | Forest Cover | 2010-01-04 14:46 | Akerley, Scott C FOR:EX | FALSE | Gallimore, John FOR:EX | RESULTS321 - Forest Cover Detail | Item | results/Lists/BugsEnhancements
111 | 114893 |  | High | Delete 82K098-1401, 1402 and 82N007-1401, 1402 | Rel 4.01 | Datafix | Closed | Reported | Thomae, Oliver | RESULTS | Admin | 2010-01-04 10:29 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 300 | Item | results/Lists/BugsEnhancements
110 | 115187 116003 |  | High | Amalgamation approval results in ORA-02292: integrity constraint (THE.FCMI_OLS_FK) violated - child record found | Rel 4.01 | Bug | Closed | Implemented | IDIR\MCFEAGAN | RESULTS | Function | 2009-12-23 10:20 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 201 | Item | results/Lists/BugsEnhancements
109 | 111626 |  | Low | Add Opening Status Code to RDD008 | Not yet scheduled | Enhancement | Open | Reported | Yee, Ricky FOR:EX | RESULTS Reports | Reports | 2009-12-22 15:29 | Scott, Sharon FOR:EX | FALSE | Yee, Ricky FOR:EX | 310 | Item | results/Lists/BugsEnhancements
108 | 115134 |  | Low | Site plan amendment in test does not change all the data in the database | Not yet scheduled | Bug | Open | Reported | Gillan, Stacey FOR:IN | RESULTS | Function | 2009-12-17 08:17 | Scott, Sharon FOR:EX | FALSE | Tsoi, Mei-Ching FOR:EX | 311 | Item | results/Lists/BugsEnhancements
107 | 114871, 113924, 116097 |  | Critical | Cannot view historical Forest Cover for FRPA 108 application approval | Rel 4.01 | Bug | Closed | Implemented | Keith.Boyes | RESULTS | Forest Cover | 2009-12-16 11:34 | Akerley, Scott C FOR:EX | FALSE | Gallimore, John FOR:EX | RESULTS108 - FRPA Application | Item | results/Lists/BugsEnhancements
106 | 114979, 116487 |  | Medium | wrong error message-316 | Rel 4.01 | Bug | Open | Submitted for MFR Technical Analysis | Storla, Richelle | RESULTS;#ESF | Function | 2009-12-16 10:28 | Scott, Sharon FOR:EX | FALSE | Yee, Ricky FOR:EX | 300 | Item | results/Lists/BugsEnhancements
105 | 115107 |  | Low | Clean up activity sorting in RESULTS | Not yet scheduled | Bug | Open | Reported | Lucas, Lorree J FOR:EX | RESULTS | Activities | 2009-12-15 14:09 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 315 | Item | results/Lists/BugsEnhancements
104 | 115053 and 109095 |  | High | broken RDD006 “Results Indicator” parameter field | RESULTSRPT 3.04. | Bug | Closed | Approved for Scheduling | Tsoi, Mei-Ching FOR:EX | RESULTS | Reports | 2009-12-10 10:15 | Scott, Sharon FOR:EX | FALSE | Johnson, Jeff FOR:EX | 300 | Item | results/Lists/BugsEnhancements
103 | 115047 |  | Medium | system error using details button on 320 screen | Not yet scheduled | Bug | Closed | Reported | Holoboff, Warren FOR:EX | RESULTS | Forest Cover | 2009-12-10 08:58 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 320 | Item | results/Lists/BugsEnhancements
102 | 114986 |  | Critical | procedure that saves audit messages for regime changes is currently broken | Rel 4.02 | Bug | Closed | Submitted for Vendor Technical Analysis | Gillan, Stacey FOR:IN | RESULTS | Function | 2009-12-07 09:54 | Scott, Sharon FOR:EX | FALSE | Gillan, Stacey FOR:IN | 300 | Item | results/Lists/BugsEnhancements
101 | 114944 |  | High | Making Inter agency mandatory | Not yet scheduled | Bug | Closed | Reported | Thomae, Oliver | RESULTS | Function | 2009-12-03 08:27 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 312 | Item | results/Lists/BugsEnhancements
100 | 114943 |  | Critical | Dealing with the Report Recipient issue | Not yet scheduled | Business Issue | Closed | Submitted for MFR Technical Analysis | Thomae, Oliver | RESULTS | Reports | 2009-12-03 08:21 | Scott, Sharon FOR:EX | FALSE | Will, Mark R FOR:EX | 300 | Item | results/Lists/BugsEnhancements
99 | 114939, 118095 |  | High | tech specs updates required for reserve type codes | Rel 4.02 | Maintenance | Open | Submitted for Vendor Technical Analysis | MacLeod, Caroline FOR:EX | RESULTS | Admin | 2009-12-02 15:22 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 300 | Item | results/Lists/BugsEnhancements
98 | 114897 |  | Critical | Forest Cover - IMM (with no reserves) submitted on or after 2005 missing Ht & Age | Not yet scheduled | Bug | Open | Submitted for MFR Technical Analysis | Gallimore, John FOR:EX | RESULTS | Forest Cover | 2009-12-01 08:26 | Scott, Sharon FOR:EX | FALSE | Yee, Ricky FOR:EX | 312 | Item | results/Lists/BugsEnhancements
97 | 114888 |  | Critical | Can't include FFT FTM code as get message inter-agency # mandatory | Not yet scheduled | Bug | Closed | Implemented | Bonar, Darren | RESULTS | Activities | 2009-11-30 15:44 | Scott, Sharon FOR:EX | FALSE | MacLeod, Caroline FOR:EX | 317 | Item | results/Lists/BugsEnhancements
96 | 113036 |  | High | a FG SU should have validation waived (or not even need to be submitted) | Not yet scheduled | Bug | Closed | Reported | Rockley, Scott FOR:EX | RESULTS | Standard Units | 2009-11-25 14:58 | Scott, Sharon FOR:EX | FALSE | MacLeod, Caroline FOR:EX | 312 | Item | results/Lists/BugsEnhancements
95 | 114772 |  | Low | SU number goes blank when editing FC online. | Not yet scheduled | Bug | Open | Reported | Akerley, Scott C FOR:EX | RESULTS | Forest Cover | 2009-11-19 13:40 | Akerley, Scott C FOR:EX | FALSE |  | RESULTS328 - Forest Cover Edit | Item | results/Lists/BugsEnhancements
94 | 114674 |  | Medium | edit rule loosening on planned area in FTA | Not yet scheduled | Admin Fix | Closed | Reported | MacLeod, Caroline FOR:EX | RESULTS | Admin | 2009-11-10 14:15 | Scott, Sharon FOR:EX | FALSE | MacLeod, Caroline FOR:EX | 310 | Item | results/Lists/BugsEnhancements
93 | 114446 |  | High | User created opening manually but submission fails as record not found | RESULTS 4.00 | Bug | Closed | Reported | Viszlai-Beale, Mary FOR:EX | RESULTS | Opening | 2009-11-10 09:00 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 300 | Item | results/Lists/BugsEnhancements
92 | 114489 |  | High | Link isaak SSID's to MaMook | RESULTS 4.00 | Datafix | Closed | Approved for Implementation | Dunn, Heather L FOR:EX | RESULTS | SSID | 2009-11-10 08:55 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 310 | Item | results/Lists/BugsEnhancements
91 | 114504 |  | High | Datafix opening to silviculture prescription | RESULTS 4.00 | Datafix | Closed | Approved for Implementation | Powell, Roger J FOR:EX | RESULTS | Admin | 2009-11-10 08:52 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 310 | Item | results/Lists/BugsEnhancements
90 | 114585 |  | High | prob with amendment on BEC, layers and species | RESULTS 4.00 | Bug | Closed | Submitted for MFR Technical Analysis | Scott, Sharon FOR:EX | RESULTS | Standard Units | 2009-11-10 08:49 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 310 | Item | results/Lists/BugsEnhancements
89 | 114617 |  | High | spatial replication error | RESULTS 4.00 | Unknown | Closed | Submitted for Business Analysis | Scott, Sharon FOR:EX | RESULTS | Function | 2009-11-10 08:45 | Scott, Sharon FOR:EX | FALSE | Bell, Bruce R FOR:EX | none | Item | results/Lists/BugsEnhancements
88 | 114640 |  | High | Add ICHxw o2 to code tables | RESULTS 4.00 | Datafix | Closed | Submitted for Business Analysis | Scott, Sharon FOR:EX | RESULTS | Standard Units | 2009-11-10 08:39 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 310 | Item | results/Lists/BugsEnhancements
87 | 114446 |  | High | User manually created opening but ESF sub. says not found | Not yet scheduled | Unknown | Closed | Reported | Viszlai-Beale, Mary FOR:EX | RESULTS;#ESF | Opening | 2009-11-06 10:58 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 310 | Item | results/Lists/BugsEnhancements
86 | 112410 |  | Medium | Can't delete SU if FC polygon associated with it. | RESULTS 4.00 | Enhancement | Open | *Submitted for Vendor Technical Analysis | MacLeod, Caroline FOR:EX | RESULTS | Forest Cover | 2009-10-26 09:15 | Scott, Sharon FOR:EX | FALSE | XT:Killam, Scott HLTH:IN | 312 | Item | results/Lists/BugsEnhancements
85 | 00114470 |  | Low | DN activities CB information blank. | RESULTS 4.00 | Enhancement | Open | Submitted for Business Analysis | Dolynchuk, Gary FOR:EX | RESULTS | Activities | 2009-10-23 09:54 | Akerley, Scott C FOR:EX | FALSE | MacLeod, Caroline FOR:EX | RESULTS316 - Disturbance Results | Item | results/Lists/BugsEnhancements
84 | 110876 |  | Low | BCEIDs get an error message when clicking the Opening Details Report in RESULTS | Not yet scheduled | Enhancement | Open | Reported | Scott, Sharon FOR:EX | RESULTS | Reports | 2009-10-22 10:54 | Scott, Sharon FOR:EX | FALSE |  | 301 | Item | results/Lists/BugsEnhancements
83 | 114403 |  | Critical | Edit rule for previous species for opening definition not enforced | Not yet scheduled | Bug | Closed | Implemented | Tsoi, Mei-Ching FOR:EX | RESULTS;#ESF | Opening | 2009-10-16 14:20 | Akerley, Scott C FOR:EX | FALSE |  | RESULTS301 - Opening Inquiry | Item | results/Lists/BugsEnhancements
82 | 111679 |  | Low | The RESULTS Report RDD012 needs a P_MOF_DEFAULT_STANDARD_IND parameter. | RESULTS 4.00 | Enhancement | Open | Reported | Yee, Ricky FOR:EX | RESULTS Reports | Reports | 2009-10-15 16:29 | Akerley, Scott C FOR:EX | FALSE | Yee, Ricky FOR:EX | Corporate Reporting system | Item | results/Lists/BugsEnhancements
81 | 114328 |  | High | new forwarder coding and no rules regarding requiring species of NSR areas for even-aged polygons | RESULTS 4.00 | Enhancement | Closed | Implemented | Scott, Sharon FOR:EX | RESULTS | Forest Cover | 2009-10-09 13:27 | Scott, Sharon FOR:EX | FALSE |  | 320 | Item | results/Lists/BugsEnhancements
80 | 114281 |  | Medium | Mislabelled openings in Mapview | RESULTS 4.00 | Unknown | Closed | Reported | MacLeod, Caroline FOR:EX | RESULTS | Function | 2009-10-05 13:55 | Scott, Sharon FOR:EX | FALSE | MacLeod, Caroline FOR:EX | 301 | Item | results/Lists/BugsEnhancements
79 |  |  | High | Text depicting attachment size limits | Not yet scheduled | Enhancement | Closed | Reported | Gallimore, John FOR:EX | RESULTS | Opening | 2009-09-28 11:39 | Gallimore, John FOR:EX | FALSE |  | RESULTS301/302 - Opening Inquirey/Add New Opening | Item | results/Lists/BugsEnhancements
78 | 114124 |  | Low | problem with the “RESULTS201 - Inbox Search” screen | Not yet scheduled | Enhancement | Closed | Reported | Yee, Ricky FOR:EX | RESULTS | Function | 2009-09-22 12:59 | Scott, Sharon FOR:EX | FALSE | Yee, Ricky FOR:EX | 201 | Item | results/Lists/BugsEnhancements
77 | 114082 |  | Medium | Allowing submission to change only primary block to none primary. | Not yet scheduled | Business Issue | Open | Submitted for Vendor Technical Analysis | Waines, Andy C FOR:EX | RESULTS;#ESF | Opening | 2009-09-16 16:11 | Akerley, Scott C FOR:EX | FALSE |  | RESULTS305 - Multi-Tenure | Item | results/Lists/BugsEnhancements
76 |  |  | High | RESULTS not recognizing BCTS as "O" client | Not yet scheduled | Bug | Closed | Reported | Akerley, Scott C FOR:EX | RESULTS | Standard Units | 2009-09-15 10:59 | Akerley, Scott C FOR:EX | TRUE | Yee, Ricky FOR:EX | RESULTS 311 , 312 | Item | results/Lists/BugsEnhancements
75 | 113493 |  | Critical | Date ranges causing report to fail RDDxxx (All RDD reports) | Rel 4.02 | Bug | Closed | Approved for Implementation | Scott, Mel FOR:EX | RESULTS;#RESULTS Reports | Reports | 2009-07-22 11:36 | Akerley, Scott C FOR:EX | FALSE | Johnson, Jeff FOR:EX | RDD006-Activity Report | Item | results/Lists/BugsEnhancements
74 | 00113474 |  | Low | Add comment box for approvals of amendments | Not yet scheduled | Enhancement | Open | Reported | Kukulies, Brian FOR:EX | RESULTS | Admin | 2009-07-22 11:26 | Akerley, Scott C FOR:EX | FALSE |  | RESULTS201 - Inbox Search | Item | results/Lists/BugsEnhancements
73 | 113472 |  | Low | revised species reports | Not yet scheduled | Maintenance | Open | Submitted for MFR Technical Analysis | MacLeod, Caroline FOR:EX | RESULTS | Reports | 2009-07-21 09:26 | Scott, Sharon FOR:EX | FALSE | Yee, Ricky FOR:EX | Reports | Item | results/Lists/BugsEnhancements
72 | 113116, 115970 |  | Critical | Site plan amendment deletes data but does not add new | Rel 4.02 | Unknown | Closed | Implemented | tina.tmp.co | RESULTS | Standard Units | 2009-07-17 14:27 | Scott, Sharon FOR:EX | FALSE | Yee, Ricky FOR:EX | S310 | Item | results/Lists/BugsEnhancements
71 | 113273 |  | Critical | S313 Event Dates being overwritten by approval date | Rel 4.02 | Bug | Closed | Implemented | MacLeod, Caroline FOR:EX | RESULTS | Standard Units | 2009-07-13 08:17 | Scott, Sharon FOR:EX | FALSE | Yee, Ricky FOR:EX | S313 | Item | results/Lists/BugsEnhancements
70 | 00112 |  | Medium | RESERVE type "O" other showing as a WTP. | Not yet scheduled | Bug | Closed | Reported | Konowalyk, Lyn FOR:EX | RESULTS;#LRDW | Forest Cover | 2009-07-10 11:43 | Akerley, Scott C FOR:EX | FALSE |  | RESULTS321 - Forest Cover Detail | Item | results/Lists/BugsEnhancements
69 | 113243 |  | Critical | FRPA197 regen lockdown | Rel 4.01 | Business Issue | Closed | Submitted for Vendor Technical Analysis | Barolet, Paul L FOR:EX | RESULTS | Function | 2009-07-08 08:17 | Scott, Sharon FOR:EX | FALSE | MacLeod, Caroline FOR:EX | S310 | Item | results/Lists/BugsEnhancements
68 | 112356 |  | High | Regenerate the thr rendered images RE: Western audit report | Not yet scheduled | Datafix | Closed | Submitted for Vendor Technical Analysis | Scott, Sharon FOR:EX | ESF | Activities | 2009-06-29 10:47 | Gallimore, John FOR:EX | FALSE | Yee, Ricky FOR:EX | RESULTS315 - Activities | Item | results/Lists/BugsEnhancements
67 |  |  | Medium | Transfer of obligations under 29.1 | Not yet scheduled | Business Issue | Closed | Reported | MacLeod, Caroline FOR:EX | RESULTS | Standard Units | 2009-06-29 10:03 | Gallimore, John FOR:EX | FALSE | MacLeod, Caroline FOR:EX | RESULTS310 - Stocking Standards | Item | results/Lists/BugsEnhancements
66 |  |  | High | Determine how much the C and E reports are for next release | Rel 4.02 | Enhancement | Closed | Business Analysis Complete | MacLeod, Caroline FOR:EX | RESULTS Reports | Reports | 2009-06-29 09:57 | Gallimore, John FOR:EX | FALSE | MacLeod, Caroline FOR:EX | RDD | Item | results/Lists/BugsEnhancements
65 | 00113191 |  | Medium | ESF opening definition submission E-mail not saying if accepted or rejected. | Not yet scheduled | Enhancement | Closed | Reported | Scott King | RESULTS;#ESF | Opening | 2009-06-24 15:52 | Akerley, Scott C FOR:EX | FALSE | MacLeod, Caroline FOR:EX | N/A | Item | results/Lists/BugsEnhancements
64 | 113079 |  | Low | RESULTS Stocking Standards 4 species limitation | RESULTS 4.00 | Enhancement | Open | Submitted for MFR Technical Analysis | tina.tmp.co | RESULTS | Standard Units | 2009-06-16 13:05 | Scott, Sharon FOR:EX | FALSE | Gallimore, John FOR:EX | 310 | Item | results/Lists/BugsEnhancements
63 | 110953 |  | Medium | FFT openings require disturbance for FC reporting | Not yet scheduled | Maintenance | Closed | Deferred | Bonar, Darren | RESULTS | Function | 2009-06-09 14:31 | MacLeod, Caroline FOR:EX | FALSE | MacLeod, Caroline FOR:EX | Activities | Item | results/Lists/BugsEnhancements
62 |  |  | Low | Validate RESULTS spatial against FTA cleared exhibit A | Not yet scheduled | Enhancement | Open | Reported | Tsoi, Mei-Ching FOR:EX | RESULTS | Function | 2009-06-09 14:21 | MacLeod, Caroline FOR:EX | FALSE | MacLeod, Caroline FOR:EX | Spatial - ESF | Item | results/Lists/BugsEnhancements
61 |  |  | Low | % pest incidence | Not yet scheduled | Enhancement | Open | Reported | Weaver, David W FOR:EX | RESULTS | Forest Cover | 2009-06-09 14:19 | MacLeod, Caroline FOR:EX |  | MacLeod, Caroline FOR:EX | Forest Cover | Item | results/Lists/BugsEnhancements
60 |  |  | Low | Tree Spp Monitoring Reports - Minister Bell's Newsletter | Not yet scheduled | Communication | Open | Reported | Winter, Ralph FOR:EX | RESULTS Reports | Reports | 2009-06-08 08:48 | Gallimore, John FOR:EX | FALSE | MacLeod, Caroline FOR:EX | RDD | Item | results/Lists/BugsEnhancements
59 |  |  | Low | Create event history for FRPA 108 | Not yet scheduled | Enhancement | Open | Reported | MacLeod, Caroline FOR:EX | RESULTS | Admin | 2009-06-05 16:38 | MacLeod, Caroline FOR:EX |  | MacLeod, Caroline FOR:EX | RESULTS 108/610 | Item | results/Lists/BugsEnhancements
58 |  |  | Low | Openings with no tenure in FTA | Not yet scheduled | Enhancement | Open | Reported | MacLeod, Caroline FOR:EX | RESULTS | Function | 2009-06-05 16:36 | MacLeod, Caroline FOR:EX | FALSE | IDIR\SKILLAM | multi tenure, opening | Item | results/Lists/BugsEnhancements
57 | 00115648 |  | Medium | Opening category code update request | Not yet scheduled | Maintenance | Open | Reported | Dominy, Richard FOR:EX | RESULTS | Opening | 2009-06-05 16:32 | MacLeod, Caroline FOR:EX | FALSE | Gallimore, John FOR:EX | Opening Inquiry | Item | results/Lists/BugsEnhancements
56 |  |  | Low | Pre-harvest stand label for non FT openings | Not yet scheduled | Business Issue | Open | Reported | Tsoi, Mei-Ching FOR:EX | RESULTS | Opening | 2009-06-05 16:30 | MacLeod, Caroline FOR:EX |  | MacLeod, Caroline FOR:EX | Opening Inquiry | Item | results/Lists/BugsEnhancements
55 |  |  | Low | FG declaration and FC info confirmation | Not yet scheduled | Enhancement | Open | Reported | MacLeod, Caroline FOR:EX | RESULTS | Reports | 2009-06-05 16:28 | MacLeod, Caroline FOR:EX |  | MacLeod, Caroline FOR:EX | Forest Cover | Item | results/Lists/BugsEnhancements
54 |  |  | Low | Cutblock status triggered by RESULTS submissions | Not yet scheduled | Enhancement | Open | Reported | MacLeod, Caroline FOR:EX | RESULTS | Milestones | 2009-06-05 16:27 | MacLeod, Caroline FOR:EX | FALSE | MacLeod, Caroline FOR:EX | Milestones | Item | results/Lists/BugsEnhancements
53 |  |  | Low | Datestamps for attachements | Not yet scheduled | Maintenance | Open | Reported | Moss, Duncan E FOR:EX | RESULTS | Function | 2009-06-05 16:25 | MacLeod, Caroline FOR:EX |  | IDIR\SKILLAM | Attachment | Item | results/Lists/BugsEnhancements
52 | 107698, 00107779 |  | Low | SP & FC Maps Rendering missing labels | Not yet scheduled | Enhancement | Open | Reported | Tsoi, Mei-Ching FOR:EX | RESULTS | Forest Cover | 2009-06-05 16:23 | MacLeod, Caroline FOR:EX | FALSE | Yee, Ricky FOR:EX | SP and FC rendered maps | Item | results/Lists/BugsEnhancements
51 | 106492 |  | Medium | RESULTS ACCEPTS PL AND FD IN FOREST COVER EDITS | Not yet scheduled | Bug | Open | Submitted for MFR Technical Analysis | Fraser, Andrew FOR:EX | RESULTS | Forest Cover | 2009-06-05 14:12 | MacLeod, Caroline FOR:EX | FALSE | Holland, Bill FOR:EX | Activities, foorest cover | Item | results/Lists/BugsEnhancements
50 | 103276 |  | Low | Tracking Research Installations | Not yet scheduled | Enhancement | Open | Reported | MacLeod, Caroline FOR:EX | RESULTS | Function | 2009-06-05 14:09 | MacLeod, Caroline FOR:EX | FALSE | MacLeod, Caroline FOR:EX | Forest Cover | Item | results/Lists/BugsEnhancements
49 |  |  | Low | Allow opening search with CB id only | Not yet scheduled | Enhancement | Open | Reported | MacLeod, Caroline FOR:EX | RESULTS | Function | 2009-06-05 14:06 | MacLeod, Caroline FOR:EX |  | Gallimore, John FOR:EX | SIL 56 - RESULTS 105 | Item | results/Lists/BugsEnhancements
48 |  |  | Low | FSP ID in ATU Search | Not yet scheduled | Enhancement | Open | Reported | MacLeod, Caroline FOR:EX | RESULTS | Function | 2009-06-05 14:04 | MacLeod, Caroline FOR:EX |  | Gallimore, John FOR:EX | SIL 56 - RESULTS 105 | Item | results/Lists/BugsEnhancements
47 |  |  | Low | Fertilizer related issues | Not yet scheduled | Enhancement | Open | Reported | Fougere, Blake FOR:EX | RESULTS | Query Tools | 2009-06-05 14:01 | MacLeod, Caroline FOR:EX |  | Gallimore, John FOR:EX | Reports, Activities, Projects | Item | results/Lists/BugsEnhancements
46 |  |  | Low | Recipient Accomplishment Report | Not yet scheduled | Maintenance | Open | Submitted for MFR Technical Analysis | MacLeod, Caroline FOR:EX | RESULTS | Reports | 2009-06-05 13:58 | MacLeod, Caroline FOR:EX | FALSE | Yee, Ricky FOR:EX | Reports - RESULTSRDD011 | Item | results/Lists/BugsEnhancements
45 |  |  | Low | open view all to public - security | Not yet scheduled | Enhancement | Open | Reported | Gallimore, John FOR:EX | RESULTS | Authorities | 2009-06-05 13:46 | MacLeod, Caroline FOR:EX |  | MacLeod, Caroline FOR:EX | All except projects | Item | results/Lists/BugsEnhancements
44 | 109380 |  | Medium | Pre-Harvest stand label on viewable and FTWL | Not yet scheduled | Business Issue | Closed | Reported | MacLeod, Caroline FOR:EX | RESULTS | Forest Cover | 2009-06-05 13:42 | MacLeod, Caroline FOR:EX | FALSE | MacLeod, Caroline FOR:EX | Opening Inquiry | Item | results/Lists/BugsEnhancements
43 |  |  | Low | Ability to export opening search results to excel | Not yet scheduled | Enhancement | Open | Reported | Gallimore, John FOR:EX | RESULTS | Reports | 2009-06-05 13:39 | MacLeod, Caroline FOR:EX |  | MacLeod, Caroline FOR:EX | SIL 56 | Item | results/Lists/BugsEnhancements
42 |  |  | Low | FSP Results and Stategies checklist | Not yet scheduled | Enhancement | Open | Reported | MacLeod, Caroline FOR:EX | RESULTS | Function | 2009-06-05 13:29 | MacLeod, Caroline FOR:EX |  | MacLeod, Caroline FOR:EX | Opening Inquiry? Reports? | Item | results/Lists/BugsEnhancements
41 | 00108929 | 41864 | Low | Duplicate opening numbers allowed in ESF submissions | Not yet scheduled | Bug | Open | Reported | Tsoi, Mei-Ching FOR:EX | RESULTS | Opening | 2009-06-05 13:24 | MacLeod, Caroline FOR:EX |  | IDIR\SKILLAM | Opening Inquiry | Item | results/Lists/BugsEnhancements
40 |  |  | High | Creating new Reporting View for Easier FPC/FSP referencing - Draft Decision Tree | Not yet scheduled | Business Issue | Closed | Business Analysis Complete | Winter, Ralph FOR:EX | RESULTS;#RESULTS Reports | Standard Units | 2009-06-02 15:57 | Gallimore, John FOR:EX | FALSE | MacLeod, Caroline FOR:EX | RESULTS_310_Stocking Standards | Item | results/Lists/BugsEnhancements
39 |  |  | Low | Cutblock status rationalisation for FTA/RESULTS | Not yet scheduled | Business Issue | Open | Reported | Rockley, Scott FOR:EX | RESULTS | Activities | 2009-06-02 15:48 | Gallimore, John FOR:EX | FALSE | MacLeod, Caroline FOR:EX | RESULTS315 | Item | results/Lists/BugsEnhancements
38 |  |  | Low | Minutes of "No Regen" Milestone Meeting(march 2008) | Not yet scheduled | Business Issue | Open | Reported | Winter, Ralph FOR:EX | RESULTS | Milestones | 2009-06-02 15:10 | Gallimore, John FOR:EX | FALSE | MacLeod, Caroline FOR:EX | milestone | Item | results/Lists/BugsEnhancements
37 |  |  | Medium | System-derived spatial errors | Not yet scheduled | Business Issue | Closed | Reported | Sapinsky, Linda FOR:EX | RESULTS;#LRDW | Opening | 2009-06-02 13:56 | Gallimore, John FOR:EX | FALSE | MacLeod, Caroline FOR:EX | Opening | Item | results/Lists/BugsEnhancements
36 |  |  | Medium | Various derived fields for C & E | Not yet scheduled | Enhancement | Closed | Reported | Fougere, Blake FOR:EX | RESULTS | Reports | 2009-06-02 13:51 | Gallimore, John FOR:EX | FALSE | MacLeod, Caroline FOR:EX | Opening | Item | results/Lists/BugsEnhancements
35 |  |  | High | Various derived fields for C & E | Not yet scheduled | Enhancement | Closed | Submitted for Business Analysis | Fougere, Blake FOR:EX | RESULTS | Reports | 2009-06-02 13:51 | Gallimore, John FOR:EX | FALSE | MacLeod, Caroline FOR:EX | Opening | Item | results/Lists/BugsEnhancements
34 | 111935 |  | Medium | a process to retire old sec108 applications in the system | Not yet scheduled | Business Issue | Closed | Implemented | Winter, Ralph FOR:EX | RESULTS | Forest Cover | 2009-06-02 11:50 | Gallimore, John FOR:EX | FALSE | MacLeod, Caroline FOR:EX | sec108 | Item | results/Lists/BugsEnhancements
33 | 00112815, 00113621 |  | Low | History Record for SU not showing all information changed | Not yet scheduled | Bug | Open | Reported | Salokannel, Susan E FOR:EX | RESULTS;#ESF | Standard Units | 2009-05-27 15:14 | Akerley, Scott C FOR:EX | FALSE |  | RESULTS313 - Stocking Standards History | Item | results/Lists/BugsEnhancements
32 | 112757 |  | Medium | RDD011 Milestone report -Filter not working | Not yet scheduled | Bug | Open | Submitted for MFR Technical Analysis | Tsoi, Mei-Ching FOR:EX | RESULTS Reports | Reports | 2009-05-26 15:07 | Gallimore, John FOR:EX | FALSE | Yee, Ricky FOR:EX | RDD011 | Item | results/Lists/BugsEnhancements
30 |  |  | High | Data Cleanup report | Not yet scheduled | Business Issue | Closed | Reported | MacLeod, Caroline FOR:EX | RESULTS | Admin | 2009-05-26 14:54 | Gallimore, John FOR:EX | FALSE | MacLeod, Caroline FOR:EX | All | Item | results/Lists/BugsEnhancements
29 |  |  | Low | TASS/TYPSY modification to accept Retention procedures | Not yet scheduled | Business Issue | Open | Reported | Winter, Ralph FOR:EX | RESULTS | Admin | 2009-05-26 09:49 | Gallimore, John FOR:EX |  | MacLeod, Caroline FOR:EX | Forest Cover | Item | results/Lists/BugsEnhancements
28 |  |  | Low | Query determining how many BA obligations within SU | Not yet scheduled | Query Request | Closed | Reported | Tsoi, Mei-Ching FOR:EX | RESULTS | Query Tools | 2009-05-26 09:43 | Gallimore, John FOR:EX | FALSE | Tsoi, Mei-Ching FOR:EX | Forest Cover | Item | results/Lists/BugsEnhancements
27 |  |  | Medium | Precision standards in RISS | Not yet scheduled | Business Issue | Closed | Deferred | Wickland, Craig M FOR:EX | RESULTS | Admin | 2009-05-26 09:38 | Gallimore, John FOR:EX | FALSE | MacLeod, Caroline FOR:EX | All | Item | results/Lists/BugsEnhancements
26 |  |  | Medium | Numerous RISS updates | Not yet scheduled | Business Issue | Closed | Deferred | MacLeod, Caroline FOR:EX | RESULTS | Admin | 2009-05-26 09:36 | Gallimore, John FOR:EX | FALSE | MacLeod, Caroline FOR:EX | All | Item | results/Lists/BugsEnhancements
25 |  |  | Medium | Article for the ABCFP Magazine | Not yet scheduled | Communication | Closed | Deferred | Gallimore, John FOR:EX | RESULTS | Admin | 2009-05-26 09:14 | Gallimore, John FOR:EX | FALSE | Gallimore, John FOR:EX | All | Item | results/Lists/BugsEnhancements
24 |  |  | Low | Self serve User Access Web page | Not yet scheduled | Business Issue | Open | Submitted for Business Analysis | MacLeod, Caroline FOR:EX | RESULTS;#ESF | Admin | 2009-05-26 09:09 | Gallimore, John FOR:EX | FALSE | Tyler Waters (Sharepoint Admin) | ESF;All RESULTS Pages | Item | results/Lists/BugsEnhancements
23 |  |  | Low | Develop CRS reports for Compliance | Not yet scheduled | Enhancement | Open | Submitted for Prioritization | Winter, Ralph FOR:EX | RESULTS Reports | Reports | 2009-05-26 09:02 | Gallimore, John FOR:EX | FALSE | MacLeod, Caroline FOR:EX | CRS | Item | results/Lists/BugsEnhancements
22 |  |  | Low | Discuss how to streamline RESULTS data with FAIB | Rel 4.02 | Business Issue | Open | Reported | Winter, Ralph FOR:EX | RESULTS | Forest Cover | 2009-05-25 15:54 | Gallimore, John FOR:EX |  | MacLeod, Caroline FOR:EX | Forest Cover | Item | results/Lists/BugsEnhancements
21 |  | 30959/32489 | Critical | Updates to Reserve Type and Objective codes | Not yet scheduled | Maintenance | Closed | Submitted for Business Analysis | MacLeod, Caroline FOR:EX | RESULTS | Forest Cover | 2009-05-25 15:38 | Gallimore, John FOR:EX | FALSE | MacLeod, Caroline FOR:EX | Forest Cover | Item | results/Lists/BugsEnhancements
20 |  |  | Medium | Linking RESULTS with Prognosis | Not yet scheduled | Enhancement | Closed | Deferred | Winter, Ralph FOR:EX | RESULTS | Query Tools | 2009-05-25 15:05 | Gallimore, John FOR:EX | FALSE | MacLeod, Caroline FOR:EX | Opening | Item | results/Lists/BugsEnhancements
19 |  |  | High | SP Exempt Indicator | Not yet scheduled | Business Issue | Open | Submitted for Business Analysis | MacLeod, Caroline FOR:EX | RESULTS | Opening | 2009-05-25 15:02 | Gallimore, John FOR:EX | FALSE | MacLeod, Caroline FOR:EX | Opening | Item | results/Lists/BugsEnhancements
18 |  |  | Medium | Consolidate the RESULTS work for 2009/2010 | Not yet scheduled | Business Issue | Closed | Business Analysis Complete | Gallimore, John FOR:EX | RESULTS | Admin | 2009-05-25 14:54 | Gallimore, John FOR:EX | FALSE | Gallimore, John FOR:EX | All | Item | results/Lists/BugsEnhancements
17 |  |  | High | Number of unapproved FSP stocking standards amendments Report | Not yet scheduled | Query Request | Closed | Reported | Winter, Ralph FOR:EX | RESULTS | Standard Units | 2009-05-25 14:48 | Gallimore, John FOR:EX | FALSE | Winter, Ralph FOR:EX | RESULTS 310 | Item | results/Lists/BugsEnhancements
16 | 00112746 |  | Medium | Review and correction of wording for minor amendment legislation | Not yet scheduled | Maintenance | Closed | Business Analysis Complete | Randy Waterous | RESULTS | Standard Units | 2009-05-22 14:05 | Akerley, Scott C FOR:EX | FALSE | MacLeod, Caroline FOR:EX | RESULTS310- Stocking Standards | Item | results/Lists/BugsEnhancements
15 | 00110953 |  | Medium | Change DN activity requirements for FC on FFT openings | Not yet scheduled | Enhancement | Closed | Declined | Bonar, Darren | RESULTS | Forest Cover | 2009-05-21 10:16 | Akerley, Scott C FOR:EX |  | MacLeod, Caroline FOR:EX | RESULTS320-Forest Cover Summary | Item | results/Lists/BugsEnhancements
14 | 00109808 |  | Low | When adding burn as denudation activity the area doubles | RESULTS 4.00 | Enhancement | Open | Deferred | Konowalyk, Lyn FOR:EX | RESULTS | Activities | 2009-05-21 08:40 | Akerley, Scott C FOR:EX |  | MacLeod, Caroline FOR:EX | Displayed on RESULTS301-Opening Inquiry | Item | results/Lists/BugsEnhancements
13 | 112681 |  | Low | ignoring the Client Number for ESF subs | Not yet scheduled | Bug | Open | Submitted for MFR Technical Analysis | Yee, Ricky FOR:EX | ESF | Opening | 2009-05-19 08:45 | Gallimore, John FOR:EX |  | Yee, Ricky FOR:EX | ESF Schemas and RESULTSVC | Item | results/Lists/BugsEnhancements
12 | NO |  | Medium | Forest Cover Archiving not working as it should | Not yet scheduled | Bug | Closed | Submitted for Prioritization | Tsoi, Mei-Ching FOR:EX | RESULTS | Forest Cover | 2009-05-12 15:45 | MacLeod, Caroline FOR:EX | FALSE | Akerley, Scott C FOR:EX | Forest Cover | Item | results/Lists/BugsEnhancements
11 | 112428 |  | Medium | Reports showing which are FDP or FSP openings | Not yet scheduled | Enhancement | Closed | Duplicate | Sacenieks, Kristine G FOR:EX | RESULTS | Reports | 2009-05-05 08:17 | Gallimore, John FOR:EX | FALSE |  | CRS | Item | results/Lists/BugsEnhancements
10 | 112246 |  | Critical | Major amendments being saved in RESULTS without being approved | Rel 4.01 | Bug | Closed | Approved for Implementation | Waterer, Fred FOR:EX | RESULTS | Opening | 2009-05-01 13:09 | Akerley, Scott C FOR:EX | FALSE | Yee, Ricky FOR:EX | RESULTS312 - Stocking Standard Amendment Request | Item | results/Lists/BugsEnhancements
9 | 118962 TESTING; Prod-114929 | 44863 | Critical | Hitting back button from Stocking comment area causes system error | Not yet scheduled | Bug | Open | Approved for Implementation | Akerley, Scott C FOR:EX | RESULTS | Standard Units | 2009-04-08 14:12 | Akerley, Scott C FOR:EX | FALSE | XT:Killam, Scott HLTH:IN | RESULTS131 - Comment List | Item | results/Lists/BugsEnhancements
8 | 00108468 |  | Low | Species added to Biological Regeneration report | Not yet scheduled | Enhancement | Open | Reported | Dymond, Caren FOR:EX | RESULTS | Reports | 2009-04-08 13:29 | Akerley, Scott C FOR:EX |  |  | CRS Silviculture reports | Item | results/Lists/BugsEnhancements
7 | 00112088 |  | Low | Phoenix xml generator used and SS information not going through | Not yet scheduled | Unknown | Open | Submitted for MFR Technical Analysis | Howse, Kerri L FOR:EX | RESULTS;#ESF | SSID | 2009-04-03 08:40 | Akerley, Scott C FOR:EX | FALSE | Yee, Ricky FOR:EX | RESULTS312 - Stocking Standard Amendment Request | Item | results/Lists/BugsEnhancements
6 | 00107681 |  | Low | RDD005 report showing nulls when specific license choosen | RESULTS 4.00 | Bug | Open | Reported | Howse, Kerri L FOR:EX | RESULTS | Reports | 2009-03-26 16:50 | Akerley, Scott C FOR:EX |  | Yee, Ricky FOR:EX | CRS RDD005 - Disturbance Report | Item | results/Lists/BugsEnhancements
5 | 00111947 |  | Low | Data saved but no showing in RESULTS after save. | RESULTS 4.00 | Bug | Open | Submitted for MFR Technical Analysis | Porteous, Jaime | RESULTS | SSID | 2009-03-24 14:53 | Akerley, Scott C FOR:EX | FALSE | Yee, Ricky FOR:EX | RESULTS311 - Stocking Standard Correction | Item | results/Lists/BugsEnhancements
4 | 00107656 | 41316 | Low | Report DAT001 reading 0 as null. | RESULTS 4.00 | Bug | Open | Reported | Akerley, Scott C FOR:EX | RESULTS | Reports | 2009-03-12 14:30 | Akerley, Scott C FOR:EX |  |  | CRS RESULTS Silviculture Reports | Item | results/Lists/BugsEnhancements
3 | 00106917 |  | Low | Opening tenure search only giving area for primary block. | RESULTS 4.00 | Enhancement | Open | Deferred | Akerley, Scott C FOR:EX | RESULTS | Function | 2009-03-12 14:03 | Akerley, Scott C FOR:EX |  | Kepmen Lee | SIL56 - Opening Tenure Search | Item | results/Lists/BugsEnhancements
2 | 00111768 |  | Medium | Approval required notice not disappearing when approved | RESULTS 4.00 | Bug | Closed | Deferred | Derow, Kevin FOR:EX | RESULTS | Admin | 2009-03-12 12:03 | Akerley, Scott C FOR:EX | FALSE | Akerley, Scott C FOR:EX | RESULTS201 | Item | results/Lists/BugsEnhancements
1 | 00110997 |  | Low | ESF submission not changing acc species to preferred | Not yet scheduled | Bug | Closed | Submitted for MFR Technical Analysis | Akerley, Scott C FOR:EX | RESULTS | Standard Units | 2009-01-25 11:18 | Akerley, Scott C FOR:EX | FALSE | Yee, Ricky FOR:EX | RESULTS312 - Stocking standards amendment request | Item | results/Lists/BugsEnhancements