Dec 07, 2011
Coastal Fire Centre 2012 Forest Service Centennial Activities
CoFC Theme : 100 Years of Forest Fire Suppression on Coastal BC
1. Coastal Fire Centre Open House:
Scheduled Date:  June 7, 2012 - must ensure date selected integrates with other activities
Fire Centre Plan: 
· CLT is June 6 allowing CLT members the option to participate
· invite local NRO offices to attend; invite local politicians including First Nations
· special presentation planned for dignitaries
· general open house for public 1000 am to 1500 pm
· Displays: 	
· Historic fires of note:
· Tay 1967; Port Neville 1925; Bloedel (Sayward) 1938; Manning Park 1945/46
· Modern fires of note: 
· Squamish 1990; Galiano 2006; Dean River 2010; Bella Coola 2009
· F/F Equipment: Fire Zone modern equipment, old equipment (Alberni Historical Society?)
· Aviation – hover exit demo, helicopter tours
· Fire Smart trail
· Partners: local fire departments, local forest companies, fire wardens, former employees, local politicians and First Nations
· Target Audience:  invited dignitaries, former staff and general public; not [schools as there can be participation in classroom presentations]
· Refreshments: coffee, tea, juice, snacks, cookies, hot dogs between 1100 and 1300
· Logistics: Plan requires that a dedicated logistics contact is in place by February 2012 to begin organization of event.  Identified items to arrange are
· Ranger tents for displays
· port-a-potties
· janitorial support
· shuttle for staff parking
· sound system (Greg Brown)
· tables and chairs
· flat screen display
· projector
· additional BBQ & misc supplies



2. Zone Plans
Zones are expected to support the BCFS 100 year event at local levels by integrating with other NRO functions, local community events, school visits, fire department initiatives etc.  Traditional fire prevention events can expand to include a focus on this being our 100 year anniversary.  Zones will be supported with an information kit that builds upon our regular Prevention messaging and activities.  The Zone Info Kit will include:
· table top static display for posters, pictures etc
· table runner with Coastal Fire Centre and WMB oval
· DVD with fires of interest
· booklets, general Prevention supplies etc

3. Crew Leader Bootcamp
March 26-30 @ Mesachie Lake.  Interaction with crew leaders about the background and ideas behind our planned Centenary events; possible guest speaker (suggestion: John Flanagan)

4. Draft Budget
	Lapel pins BCFS 100 year
	1000 pins
	2200
	2200

	BCFS 100 Yearbook
	25 copies @ $40/copy (available Sept 2012)
	1000
	?

	Additional Smokey Suit
	One at $3300 + shipping
	3500
	0

	Advertising; print
	Info Bulletins + tag in with BCFS 100 promotions
	0
	

	Banners & signs
	Outdoor suitable banner, grommets 8 @ $64 + shipping
	550
	

	
	BCFS 100 signs printed in-house: ink set 4 x $175 + paper $40
	740
	

	Open House
	Food
	1000
	1000

	
	Parking shuttle
	250
	250

	
	Additional Janitorial support
	200
	200

	
	BBQ rental, cooking equipment
	200
	200

	
	Other misc supplies
	TBD
	TBD

	Zone Kits
	Static display, tabletop, Velcro attachment, 6 @ 185 + shipping
	1200
	*

	
	Table top runners, 56”: 8 @ $64 + shipping
	550
	*

	
	DVD’s with historic photos, 6, in-house: costs for DVDs
	20
	*

	
	Misc supplies
	100
	*

	Additional Travel Expenses 
	for staff for Centenary events
	2000
	

	Total estimated costs
(for PID proposal)
	(estimates in red)
	$13,510
	$3850

	
	Pay items identified with * and * out of Prevention budget
	
	


5. Action Items
· review projected costs and develop PID for funding approval
· solicit feedback and input from ZFPO’s (must have)
· identify date of open house for the BCFS100 calendar
· consult CoFC Prevention WG to take on the responsibility of integrating the centenary events with other prevention activities schedule next meeting of fire centre committee in mid January for a CLT discussion Feb 1, 2012
