Apr 19, 2012

Coastal Fire Centre 2012 Forest Service Centennial Activities

CoFC Theme : 100 Years of Forest Fire Suppression on Coastal BC

- Coastal Fire Centre Open House:

Scheduled Date:  June 7, 2012 - must ensure date selected integrates with other activities

Fire Centre Plan:

  - CLT is June 6 allowing CLT members the option to participate

  - general open house for public 1000 am to 1500 pm; no public advertising planned

  - target audience: current and retired WMB staff; retired Wildfire TEAMS staff; interested FLNRO staff

  - invitees: 
- WMB Director; Deputy Minister; Asst DM; BCFS100 board of directors including WMB rep, John Flanagan (Phil do you want a semi-formal email style invitation form?)
- South & West Coast RMT members; BCTS Business Area Managers (Seward/Tlasta/Strait of Georgia/Chinook)
- Forest Industry: TimberWest, Island Timberlands, Western Forest Products, Interfor, (Teal Jones??)
- District 69 Fire Chiefs (Rob T to propose draft list of fire chiefs to invite)
- MLA’s: fire centre located in riding of Parksville/Qualicum, Ron Cantelon (Lib), MLA ; Scott Fraser (NDP), MLA, Alberni/Pacific Rim (formerly Alberni/Qualicum) lives in Qualicum Beach (Has this been dropped?)

Displays:

- Historic fires of note: audio/visual

    - Tay 1967; Port Neville 1925; Bloedel (Sayward) 1938

    - Modern fires of note: audio/visual

      - Squamish 1990; Galiano 2006; Dean River 2010; Bella Coola 2009

    - F/F Equipment: Staff parking lot
Fire Zone modern equipment, old equipment (Alberni Historical Society?)

    - Aviation – hover exit demo, static helicopter tours, Air tanker demo

    - Fire Smart Trail v- self guided tour

Refreshments: coffee, tea, juice, snacks, cookies, hot dogs between 1100 and 1300
		Question: could drop hot dog idea for guests and go with coffee and cake only

- Draft Budget

| Lapel pins BCFS 100 year | 1500 pins – 230 mailed to staff; 125/fire zone; 520 fire centre cache |  | bought |
| --- | --- | --- | --- |
| Additional Smokey Suit | Back ordered from last fiscal | 2100 |  |
| Advertising; print | Info Bulletins + tag in with BCFS 100 promotions | 0 |  |
|  | BCFS 100 signs printed in-house: ink set 2 x $175 + paper $40 | 390 |  |
| Open House | Food | 1000 | 1000 |
|  | Parking shuttle | 250 | 250 |
|  | Additional Janitorial support | 200 | 200 |
|  | BBQ rental, cooking equipment | 200 | 200 |
|  | Other misc supplies | 200 | TBD |
| Zone Kits | Static display, tabletop, Velcro attachment, 6 @ 185 + shipping |  | bought |
|  | Table top runners, 56”: 8 @ $64 + shipping |  | bought |
|  | DVD’s with historic photos, 6, in-house: costs for DVDs |  | * |
| Total estimated costs | (estimates in red) | $3590 [$1490 w/o Smokey] | $2500 |
|  | Pay items identified with * and * out of Prevention budget |  |  |

Action Items

- Design Plan for Open House (attached)

- Develop ICS org structure (attached)

- Plan for follow up meeting April 19

Smokey purchase not completed last fiscal due to manufacturer issues