May 08, 2012
Coastal Fire Centre 2012 Forest Service Centennial Activities
CoFC Theme : 100 Years of Forest Fire Suppression on Coastal BC
Coastal Fire Centre Open House: June 7, 2012 

Fire Centre Plan: 
· general open house for public 1000 am to 1500 pm; no public advertising planned
· Mid Island Zone to supply rain shelter for entrance area
· hold cake cutting ceremony at 1230
· target audience: current and retired WMB staff; retired Wildfire TEAMS staff; interested FLNRO staff
· plan attendance for 80 guests for 1230 cake cutting and fire centre manager speech; 120 guests throughout day
Invitations:
1. Fire Info will design an electronic invitation for Phil to send out, RSVP’s and list of invitees attending to be managed by Penny
2. John Flanagan will bring BCFS100 society members up from Victoria for business meeting and fire centre event
3. Electronic Invitations to be distributed to:
- WMB Director; Gary Townsend, Asst DM, Integrated Resource Operations, Craig Sutherland, Asst DM, Regional operations Division; South & West Coast RMT members; BCTS Business Area Managers (Seward/Tlasta/Strait of Georgia/Chinook); South and West Coast Region CEB managers; Paul Tatayrn, Regional Mgr, Recreation Sites & Trails; Gino Fournier, Engineering Group Leader (both West & South Coast Regions)
- Forest Industry: TimberWest, Island Timberlands, Western Forest Products, Interfor, (Teal Jones??)
- District 69 Fire Chiefs (Rob T to propose draft list of fire chiefs to invite)
Displays:
1. AV Display: (Fire Info) Lookout photos
2. Memorabilia display (Fire Info) – main meeting room, Admin trailer
3. Historic fires of note: (Fire Info) Tay 1967; Port Neville 1925; Bloedel (Sayward) 1938
4. Modern fires of note: (Fire Info) Galiano 2006, Dean River 2010, Bella Coola 2009
5. F/F Demo/FireSmart Trail – (Mid Island Zone)
6. F/F Equipment Demo – Mid Island Zone equipment bay
7. Aviation – (Rob F) hover exit demo, static helicopter tours
8. Cardboard Lookout (see John Flanagan)

Logistics Support
1. Develop parking plan with assistance from Mid Island Zone
current public parking and main staff parking lot to be made available for public parking
2. Refreshment Order ($1000 initial budget)
- coffee, tea, water, cookies, hot dogs and cake
- condiments
- plates, forks, napkins etc.
3. Consider need for Port-a-potties
4. Contact janitor about cleaning offices Thursday versus Friday or hire for one additional day
Smokey Bear
	Mid Island Zone to wear one of the Smokey suits during the event day
Hosts (Doug)
Develop a list of staff including FCM and DFCM to engage attendees in informal discussions and/or modified tour of centre facilities
