Nov 22, 2011

Coastal Fire Centre 2012 Forest Service Centennial Activities

CoFC Theme : 100 Years of Forest Fire Suppression on Coastal BC

- Coastal Fire Centre Open House:

Scheduled Date:  June 7, 2012 - must ensure date selected integrates with other activities

Fire Centre Plan:

  - CLT is June 6 allowing CLT members the option to participate

  - invite local NRO offices to attend; invite local politicians including First Nations

  - special presentation planned for dignitaries

  - general open house for public 1000 am to 1500 pm

  - Displays:

    - Historic fires of note:

      - Tay 1967; Port Neville 1925; Bloedel (Sayward) 1938; Manning Park 1945/46

    - Modern fires of note:

      - Squamish 1990; Galiano 2006; Dean River 2010; Bella Coola 2009

    - F/F Equipment: Fire Zone modern equipment, old equipment (Alberni Historical Society?)

    - Aviation – hover exit demo, helicopter tours

        - Fire Smart trail

    - Partners: local fire departments, local forest companies, fire wardens, former employees, local politicians and First Nations

    - Target Audience:  invited dignitaries, former staff and general public; not [schools as there can be participation in classroom presentations]

    - Refreshments: coffee, tea, juice, snacks, cookies, hot dogs between 1100 and 1300

    - Logistics: Plan requires that a dedicated logistics contact is in place by February 2012 to begin organization of event.  Identified items to arrange are

        - Ranger tents for displays

        - port-a-potties

        - janitorial support

        - shuttle for staff parking

        - sound system (Greg Brown)

        - tables and chairs

        - flat screen display

        - projector

        - additional BBQ & misc supplies

- Zone Plans
Zones are expected to support the BCFS 100 year event at local levels by integrating with other NRO functions, local community events, school visits, fire department initiatives etc.  Traditional fire prevention events can expand to include a focus on this being our 100 year anniversary.  Zones will be supported with an information kit that builds upon our regular Prevention messaging and activities.  The Zone Info Kit will include:

    - table top static display for posters, pictures etc

    - table runner with Coastal Fire Centre and WMB oval

    - DVD with fires of interest

    - booklets, general Prevention supplies etc

- Crew Leader Bootcamp
March 26-30 @ Mesachie Lake.  Interaction with crew leaders about the background and ideas behind our planned Centenary events; possible guest speaker (suggestion: John Flanagan)

- Draft Budget

| Lapel pins BCFS 100 year | 1000 pins | 2200 |
| --- | --- | --- |
| BCFS 100 Yearbook | 25 copies @ $25/copy | 500 |
| Additional Smokey Suit | One at $3300 + shipping | 3500 |
| Advertising; print | Info Bulletins + tag in with BCFS 100 promotions | 0 |
| Banners & signs | Outdoor suitable banner, grommets 8 @ $64 + shipping | 550 |
|  | BCFS 100 signs printed in-house: ink set 4 x $175 + paper $40 | 740 |
| Open House | Food | 1000 |
|  | Parking shuttle | 250 |
|  | Additional Janitorial support | 200 |
|  | BBQ rental, cooking equipment | 200 |
|  | Other misc supplies | TBD |
| Zone Kits | Static display, tabletop, Velcro attachment, 6 @ 185 + shipping | 1200 |
|  | Table top runners, 56”: 8 @ $64 + shipping | 550 |
|  | DVD’s with historic photos, 6, in-house: costs for DVDs | 20 |
|  | Misc supplies | 100 |
| Additional Travel Expenses | for staff for Centenary events | 2000 |
| Total estimated costs (for PID proposal) | (estimates in red) | $13,010 |

- Action Items

    - review projected costs and develop PID for funding approval

    - solicit feedback and input from ZFPO’s (must have)

    - identify date of open house for the BCFS100 calendar

    - consult CoFC Prevention WG to take on the responsibility of integrating the centenary events with other prevention activities

    - schedule next meeting of fire centre committee in mid January for a CLT discussion Feb 1, 2012