## REcon and establishment
AMAT test site recon/establishment report
Site name | Deep Creek
Date planted | May 2009
Planting Crew names | VB, MF, NU, MC, JF, et al.
Report by | Greg/Mary
Site history | harvested July 2008 Lots of slash left on site Site prepped with excavator Fall 2008
Native tree species (% composition) | Pl>abies, Sx
Native non-tree species (% cover)
Soil type (clayey silt, sandy loam, etc) | Sandy loam
Slope (%), Slope position (crest, upper, mid, lower) | 2%
Aspect (e.g., NW) | NE
Coarse fragment content
Stock condition | good
Soil moisture | good
Weather
Soil condition (e.g., compacted, fluffy)
Labels | good
Slash | very little removed with site prep
Vegetation control req'd? | no
Deer/elk/cattle control req'd? | YES!
Surrounds planted? | yes
Weather station installed? | no
Wildlings need pulling?
Comments/problems

## site visit
Site visit reports
Site | Deep Creek
Date | October 2009
Visitor(s) | Greg, Vicky, Nick, MC
Notes by | Greg
Purpose of visit | survival survey, erect weather station
Road condition/access | good, but could be slippery if wet
Fence condition. Fence needed? | YES
Veg control needed? Describe. | no
Animal or pest damage | 20% of trees were trampled by cows. Ask rancher to move cows
Other damage (frost, human, fire) | no
Label and stake condition | good
Tree condition | very good
Wildlings need pulling?
Comments/problems?
Site | Deep Creek
Date | October 2010
Visitor(s) | VB
Notes by | Vicky
Purpose of visit | hunting in area
Road condition/access | good, went on a dryish day
Fence condition. Fence needed? | less cattle activity than in 2009 new fence being built to the east to contain animals in area so they do not go down to valley bottom. Could cause a problem for us.
Veg control needed? Describe. | Yes
Animal or pest damage? Type of control needed.
Other damage (frost, human, fire)
Label and stake condition
Tree condition
Wildlings need pulling? | completed by contractor. They had also put pin flags on some of the crop trees
Comments/problems?
Site | Deep Creek
Date | Sept 27th - October 16th 2010
Visitor(s) | Mike, Ryan, Tim
Notes by | Mike Brown
Purpose of visit | Download data from Hobo
Road condition/access | Good
Fence condition. Fence needed? | saw no new cattle damage
Veg control needed? Describe. | brushsaw done Oct 2010... Will require more in 2011 ferns, aspen and grass on site
Animal or pest damage? Type of control needed. | Nil
Other damage (frost, human, fire) | Nil
Label and stake condition | Good
Tree condition | Good
Wildlings need pulling? | brushing . Will require removal of a few wildlings in 2011
Comments/problems? | too much site prep . Site was pin flagged at all surviving trees. ~ 2200 surviving seedlings. Cw, Pw Hw all dead
Site | Deep Creek
Date | 2011-09-07
Visitor(s) | VB
Notes by | Vicky
Purpose of visit | download data from HOBO weatherstation and check site
Road condition/access | good, dusty, went on a dry day
Weatherstation condition | Good, updated named site on HOBO from 'Replacement 1 to Deep Creek', changed batteries, put hex screw in rain gauge etc.
Veg control needed? Describe. | Yes! There is alot of Pli ingress to be removed as well as very large patches of alder, willow, cottonwood, aspen etc. It would be good to maintain this site early in the year as soon as the site is accessible (end of May?). Many pinflags are missing from crop trees so this needs to be done before any snipping, clipping or pulling around crop tree. Once that is done brushing could be done between the rows. It would take 3-4 person days to do a good job of this site.
Animal or pest damage? Type of control needed. | No cattle damage in plot. Some browse by deer on birch.
Other damage (frost, human, fire) | There is some small patches of mortality in wet, compacted soil areas
Label and stake condition | Good
Tree condition | Excellent for most species. Some larch, Sx and Pli over a meter in height. Good color and no sign of recent cattle damage. Some crop trees free growing as of Sept. 2011.
Wildlings need pulling? | There is alot of Pli ingress on the site which needs to be removed along with the shrubs named above.
Comments/problems? | Good fireweed site!
Site | Deep Creek
Date | 2012-07-30
Visitor(s) | J. Cooney, D Gustafson, J Pelttari
Notes by | R. White
Purpose of visit | restart project for 2012
Road condition/access | ok
Fence condition. Fence needed? | N/A
Veg control needed? Describe. | much hardwood ingress
Animal or pest damage? Type of control needed. | no
Other damage (frost, human, fire) | no
Label and stake condition | ok
Tree condition | ok
Wildlings need pulling? | Yes, brushing
Comments/problems? | 4 days brushing in 2012, 4 more in 2013
HOBO working? Repair? | Working okay
Site | Deep Creek
Date | 09/19/2013
Visitor(s) | R. White Woods (J. Pelttari, J. Hepting)
Notes by | J. Pelttari
Purpose of Visit | HOBO download,site inspection, measurement, brushing.
Road Condition/access | Good, 2 wd. Hike in last 400 meters.
Fence Condition/needed | N/A
Veg Control Needed? | Fully brushed in 2013. Fast growing, re-assess 2014.
Animal/Pest Damage | Some browse
Other damage (frost/human/fire | No
Label and stake condition | Good
Tree Condition | Very good survival and growth - some Lw, At, Ep over 4 meters
Wildlings need pulling? | Pl & Lw ingress removed in 2013.
Comments/problems
Site | Deep Creek
Date | Sept 27th, 2013
Visitor(s) | Vicky Berger
Notes by | Vicky Berger
Purpose of visit | Check on brushing contractor from 2012 work
Road condition/access | Good, can make it through first waterbar and deactivation with quad but it only gets you a few hundred meters closer to the site.
Fence condition. Fence needed? | N/A
Veg control needed? Describe. | still to be visited in 2013. Some plots with no crop trees needed brushing. No 5 meter buffer on perimeter
Animal or pest damage? Type of control needed. | NONE
Other damage (frost, human, fire)
Label and stake condition | good
Tree condition | excellent for all but coastal sources.. Even the aspen was > 4m A couple plots at the lower portion of the trial had seepage and were wet so had mortality
Wildlings need pulling? | a few but not bad
Comments/problems?
HOBO working? Repair? | light blinking OK did not download as contractor will be there within the month
Site Name | Deep Creek
Date of visit | October 19th, 2014
Visitor(s) | D. Evans E. van Eeden & M. Brown
Notes by | Mike Brown
Purpose of visit | HOBO download & brushing
Road condition/access | Good ---quad in the last km
Fence condition. Fence needed? | no
Veg control needed? Describe | Fully brushed again in 2014
Animal or pest damage | no
Other damage (frost, human, fire) | nil
Label and stake condition | Good.
Tree condition | good
Wildlings need pulling? | Always be wildlings but they are brushed to the ground hard to kill them all—constant problem. Plot trees free to grow
Comments/problems | Work completed 2014—6 days 2015--0
HOBO working? Repairs? | All good.
Site Visit Report
Site Name | Deep Creek
Date of visit | 2015-10-01
Visitor(s) | Vicky Berger, David Hickman
Notes by | Vicky Berger
Road condition? Access notes updated? | Good when dry, can be muddy 1 1/2 km before site. Must walk or quad in last 400 meters as the road is deactivated for vehicles
Fence condition. | n/a
Vegetation - type, amount and height? Affecting seedlings? | Lots of vegetation but not affecting seedlings but we will have large decidious trees in the trial if it is not brushed again. There are 1 1/2 - 2 meter alder, birch, willow and aspen.
Animal or pest damage? | Spruce leader weevil, armillaria killing Pli and Lw
Other damage (frost, human, fire) | no, cattle on road but no sign of them in the trial
Label and stake condition | Good
Tree condition | Very good survival, (75-80%) Lw over 4 meters, nice Grand Fir
Wildlings - amount, height, species? | There is a lot of Lw and Pli ingress that should be removed. They are 0.5 - 1.5 meters tall
HOBO - working? Downloaded? Repaired? | HOBO not working. Batteries installed incorrectly. Only 2 months data from previous year. No lights blinking. Tried to read out while in the field but neither the shuttle or computer could communicate with the data logger. Relaunched data recorder in the office, reinstalled and checked in field that is was logging. All was well Oct. 2, 2015. Left a 6 foot ladder at base of weatherstation to access the data recorder and components.
What did you do at the site? Describe each task (e.g., pinned live seedlings, brushed, removed ingress, replaced centre stakes, measured, downloaded, etc.) and number of person-days spent on each task. | Took photos and downloaded the data logger.
PLAN? For each task (e.g., pin live seedlings, brush, remove ingress, replace centre stakes, measure, download, etc.) describe when it should be done and how many person-days req'd for each task. | Must remove ingress and decidous brush. It will take 4 person days with brush saws and hand pruners. Many conifers near test trees that will have to be removed with pruners.
Comments/problems?
Site Name: | Deep Creek
Date of visit | July 12-18 2016
Visitor(s) | R. White Woods - Pelttari/Hepting
Notes by | J. Pelttari
Road condition? Access notes updated? | Good, 2wd access. Last 700 m could be a walk-in but a high-clearance 4x4 can make it through
Fence condition. | N/A
Vegetation - type, amount and height? Affecting seedlings? | Thick hardwoods - willow, alder, aspen, cottonwood - some over 2.5m tall. Removed in 2016
Animal or pest damage? | Some adelgid
Other damage (frost, human, fire) | A few Ep test trees were cut during brushing the first year.
Label and stake condition | Good, PVC center posts installed.
Tree height? Survival? | Very good survival and growth. Lw doing very well, some over 6m. Aspen over 5 m, some Pli near 4m. Most Cw gone, Cy doing ok, Bg up to 1.5m.
Wildlings - amount, height, species? | Numerous Pl, Lw, Sx and some Fd coming in throughout the site, removed in 2016.
HOBO - Downloaded? Batteries changed? OK button flashing? | Yes, all good.
What did you do at the site? Describe each task (e.g., pinned live seedlings, brushed, removed ingress, replaced centre stakes, measured, downloaded, etc.) and number of person-days spent on each task. | PVC center posts installed (1 pd), Pinned/painted test trees (1.5 pd), brushed/removed ingress (9 pd), download (.2 pd)
PLAN? For each task (replace centre stakes, pin live test seedlings, remove ingress, measure, brush and download). For each task, describe when it is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Scheduled for measurement in 2018. Est 5-7 pd depending on whether or not DBH is required. Close enough to Kal for staff to download in 2017 if desired, brush could be assessed then.
Site Name: | Deep Creek
Date of visit | Aug 18 2016
Visitor(s) | Greg ONeill and Trevor Deorkson
Notes by | Greg
Road condition? Access notes updated? | Good. We parked and walked in the last 400 m.
Fence condition. | N/A
Vegetation - type, amount and height? Affecting seedlings? | A few alder 1 m tall. Site was brushed heavily 2 weeks ago.
Animal or pest damage? | Lots of armalleria on Fd and Pl; Lots of wooley gall adelgid on Sx. A bit of spruce weevil on Sx.
Other damage (frost, human, fire) | frost on soft species; no human damage
Label and stake condition | PVC in place. Labels hanging on cable; should be screwed to post
Tree height? Survival? | As per previous report.
Wildlings - amount, height, species? | A few Lw and Pl seedlings 20 cm tall. Site was brushed heavily 2 weeks ago.
HOBO - Downloaded? Batteries changed? OK button flashing? | OK button flashing. Hardwoods to the south of the Hobo will soon affect precipitation and temp recordings.
What did you do at the site? Describe each task (e.g., pinned live seedlings, brushed, removed ingress, replaced centre stakes, measured, downloaded, etc.) and number of person-days spent on each task. | Scrutinize contractor work
PLAN? For each task (replace centre stakes, pin live test seedlings, remove ingress, measure, brush and download). For each task, describe when it is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Remove hardwoods to the south of the weather station. Could be done with a swede saw or handsaw. Probably 2 p-d of brushing required in 2018. Measure in 2018 - 7 pd w dbh
Site Name: | Deep Creek
Date of visit | 2017-10-03
Visitor(s) | Greg ONeill and Aglaen Carbajal Navarro
Notes by | Greg
Road condition? Access notes updated? | road excellent; access notes updated.
Fence condition. | n/a
Vegetation - type, amount and height? Affecting seedlings? | Lots of fireweed and some rose, not affecting seedlings too badly
Animal or pest damage? | Armillaria? Appears to be disease pockets
Other damage (frost, human, fire) | no
Label and stake condition | labels should be screwed to posts instead of hanging on cables.
Tree height? Survival? | tallest trees are Lw up to 6 m. Survival varialbe by plot and species.
Wildlings - amount, height, species? | lots of short ingress < 40 cm.
HOBO - Downloaded? Batteries changed? OK button flashing? | yes. Yes. Yes.
What did you do at the site? Describe each task (e.g., pinned live seedlings, brushed, removed ingress, replaced centre stakes, measured, downloaded, etc.) and number of person-days spent on each task. | inspect ingress and test trees; downloaded; removed hardwoods from around weather station.
PLAN? For each task (replace centre stakes, pin live test seedlings, remove ingress, measure, brush and download). For each task, describe when it is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | brush ingress in 2018 (3 pd); download (ladder required); screw labels to posts if any signs of wear on labels; brush perimeter and path to site; ribbon a path to the site.
Site Visit Report ver5
Site Name | Deep Creek
Date of visit | July 5-9 , Aug 29-Sept 2 2019
Visitor(s) | J. Pelttari/J. Hepting - R. White Woods Inc.
Notes by | J. Pelttari
Road condition? Access notes updated? | Good, 2wd access right to site, road has been opened up.
Fence condition. | N/A
Vegetation - type, amount and height? Affecting seedlings? | Fast growing site - extensive resprout of willow, aspen, birch and alder, all cut back.
Animal or pest damage? | Lots of weevil and adelgid damage in Sx, some gall rust in Pl, some foliar disease in Pl and Pw. Also root disease in Pl and Lw.
Other damage (frost, human, fire) | Six Ep cut by operational brushing crew.
Label and stake condition? 5' PVC centre stakes in place? | Good. Labels removed from plastic coated wire and attaached with screws.
Tree height, survival. | Very good growth and survival. Lw doing best, some over 9m. Pl, Fdi, Pw, Bg, At, Ep doing well. Yci doing ok, good survival some over 1.5m, some Hwi doing ok, a handful of Cw surviving.
Wildlings - amount, height, species? | Numerous small Lw, Pl and Fd seedlings,up to 30 cm coming in - removed.
HOBO - Downloaded? Batteries changed? OK light flashing? | Yes, all good.
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | Measured site 7 pd; brushed 9 pd
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | brushing will lessen as trees get bigger but still needed in 2020
Comments/problems?
Site Visit Report ver5
Site Name | Deep Creek
Date of visit | May 3 2019
Visitor(s) | Amy V and Sarina M
Notes by | Sarina M
Road condition? Access notes updated? | Good, no deactivation - access notes to be updated.
Fence condition. | NA
Vegetation - type, amount and height? Affecting seedlings? | NA, Site brushed in fall
Animal or pest damage? | >1%, minor deer rub
Other damage (frost, human, fire) | snow pack damage on Ep and At - 20% of surviving trees affected
Label and stake condition? 5' PVC centre stakes in place? | good
Tree height? Survival? | see height report from 2019 - tallest = larch( 6-7m)>Pl(4-5m)>Fd(3-5m)> Bg(1-4m)>Sx(1-3)>Cw(.5-1.5) good survival (80%, minus coastal species)
Wildlings - amount, height, species? | ~5% of Pl , ranging from 0.2-0.5m - a few missed that need lopping at test tree bases.
HOBO - what did you OBSERVE on arrival? Which light was flashing? Any damage? Faceplate leaking? Precip bucket screen clean? Are the sensors working? | hobo working, ok light flashing, grounding wire loose. Faceplate ok. Precip clean. Yes.
HOBO - what did you DO? Was the data successfully downloaded? Is there data in both the temp and precip columns? Sensors or faceplate replaced? Batteries changed? Vaseline applied to faceplate? OK button pushed after changing batteries? OK light flashing on departure? | download data, added rain guage to compare other rain gauge. Good data. No,Yes, Yes,Yes,Yes
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | download Wx statio, add additional rain guage, teach Sarina about weather stations and how to download/maintenance ( 0.25pd). Scrutinize the contractors work from the fall for brushing and height measurements. ( 1pd)
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | 2020 brushing estimate - 4pd, larch plots to be pruned up - 0.5pd, Pl to be prunned up -0.5pd
Comments/problems? | no, great site
Site Visit Report ver6
Site Name | Deep Creek
Date of visit | August 13-20th, 2020
Visitor(s) | Jeff Cooney and Michel Bergeron - R. White Woods Inc.
Notes by | Jeff Cooney
Road condition? Access notes updated? | good 2WD - no updates
Fence condition. | no fence
Vegetation - type, amount and height? Affecting seedlings? | huge amount of hardwoods re-sprouts and some small conifers
Animal or pest damage? | none observed
Other damage (frost, human, fire) | none observed
Label and stake condition? 5' PVC centre stakes in place? | Good
Tree height? Survival? | trees free-to-grow in fast growing plots
Wildlings - amount, height, species? | small conifers and all hardwoods all cutdown this visit
HOBO - what did you OBSERVE on arrival? Which light was flashing? Any damage? Faceplate leaking? Precip bucket screen clean? Are the sensors working? | OK light flashing. No damage. No leaks. Bucket cleaned, sensors working
HOBO - what did you DO? Was the data successfully downloaded? Is there data in both the temp and precip columns? Sensors or faceplate replaced? Batteries changed? Vaseline applied to faceplate? OK button pushed after changing batteries? OK light flashing on departure? | Inspection, servicing, download, change batteries and dessicant. OK light flashing.
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | Used brushsaws to cut thick hardwood re-sprouts and new sprouts.
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Brushing was much more than forecast in 2018. Actual time was 16 pd. It is anticipated that 12 pd will be required in 2022 or at the next measurement when a pruning of many trees will be required also. No estimate for pruning at this time.
Comments/problems?
Site Visit Report ver6
Site Name | Deep Creek
Date of visit | 2021 October 26
Visitor(s) | Greg O and Vicky B
Notes by | Greg
Road condition? Access notes updated? | Muddy at top, but did not require 4X4. Access notes good.
Fence condition. | n/a
Vegetation - type, amount and height? Affecting seedlings? | negligible. Not affecting seedlings (but perhaps different in July?).
Animal or pest damage? | lots of moose scat, but no damage
Other damage (frost, human, fire) | evidence of recent drought damage
Label and stake condition? 5' PVC centre stakes in place? | 5' PVC stakes in place. A few knocked over by wildlife.
Tree height? Survival? | highly variable among species. Pl up to 7m? A few Cw alive
Wildlings - amount, height, species? | < 1 per plot.
HOBO - what did you OBSERVE on arrival? Which light was flashing? Any damage? Faceplate leaking? Precip bucket screen clean? Are the sensors working? What type of microstation is in place? | OK light flashing. No damage. Old style microstation.
HOBO - what did you DO? Was the data successfully downloaded? Is there data in both the temp and precip columns? Sensors or faceplate replaced? Batteries changed? Vaseline applied to faceplate? OK button pushed after changing batteries? OK light flashing on departure? | Downloaded. Changed batteries. New dessicant inserted. Pushed start button. OK light flashing when departing. Data looks good.
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | Access assessed and site inspection done. Downloaded.
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Perhaps 4 pd of brushing required in 2023.
Comments/problems? | Site looks great. Good brushing in 2020.