## Recon_establishment
AMAT test site recon/establishment report
Site name | Glenmerry
Date planted | 2010 June 8th-10th
Planting Crew names | Caroline Hallay, Jake King
Report by | Jake King
Site history | Harvested: 2007, Commercially Planted 2008
Native tree species (by %) | Se 60%; Lw 20%; Pli 10%; Bl 10%; Cwr 1%
Soil (e.g., Silty-clay, sand, etc) | silty clay
Vegetation (main herb sp) | vaccineum some fireweed
Slope%, Slope position (e.g. toe, crest) | 10%
Aspect (e.g., NW) | West
Coarse fragment content
Stock condition | good, except WEYCO FD
Soil moisture | good
Weather | well rained in
Soil condition (e.g., compacted, fluffy) | heavily tracked in a few areas particularly through rep 1
Labels | good
Slash | light
Vegetation control req'd? | will require some brushing as it was greening up quickly
Deer/elk/cattle control req'd? | maybe
Surrounds planted? | yes
Weather station installed? | yes
Wildlings need pulling? | no
Comments/problems | some quite wet areas on left side of map in rep 3

## Site visit
Site visit report
Site | Glenmerry
Date | Oct. 14, 2011
Visitor(s) | D. Gustafson, J. Cooney R. Whitewoods Inc
Notes by | D. Gustafson
Purpose of visit | Download Hobo, site assessment and inspection weeding
Road condition/access | good
Fence condition. Fence needed? | N/A
Veg control needed? Describe. | no
Animal or pest damage | vegetation being browsed in the trial
Other damage (frost, human, fire) | no
Label and stake condition | wooden stakes falling over, tags good, all there
Tree condition | good survival
Wildlings need pulling? | weeding doen, wildlilngs pulled back from test trees
Comments/problems | brushing needed in 2012
Site | Glenmerry
Date | Oct. 18, 2012
Visitor(s) | R. Whitewood's crew
Notes by | J. Pelttari
Purpose of visit | HOBO download and site inspection
Road condition/access | Good 2 WD
Fence condition. Fence needed? | N/A
Veg control needed? Describe. | Scattered willow clumps, brush 2013
Animal or pest damage | some browse
Other damage (frost, human, fire) | no
Label and stake condition | good, some fallen posts repounded
Tree condition | good survival
Wildlings need pulling? | pulled back from test trees in 2011
Comments/problems | Brush 2013
HOBO working? Repaired? | recorded from July 10, 2011 - June 26, 2012 - cables and sensors damaged by bear or elk in June 2012. Rain bucket and temp/RH replaced this is the 2nd year in a row with animal damage to weatherstation
Site | Glenmerry
Date | 08/25/2013
Visitor(s) | R.White Woods (J.Pelttari, J. Hepting)
Notes by | J. Pelttari
Purpose of Visit | HOBO download, site inspection, brushing.
Road Condition/access | Good, 2wd.
Fence Condition/needed | N/A
Veg Control Needed? | Aspen, Willow & Alder clumps removed in 2013
Animal/Pest Damage | Some browse
Other damage (frost/human/fire | No
Label and stake condition | Good, some stakes re-pounded.
Tree Condition | Good survival
Wildlings need pulling? | Conifer ingress removed in 2013
Comments/problems | HOBO running, no damage to station this year.
HOBO working? Repaired?
Site Name | Glenmerry
Date of visit | October 6th, 2014
Visitor(s) | D. Davis E. van Eeden & M. Brown
Notes by | Mike Brown
Purpose of visit | HOBO download, measurements & brushing
Road condition/access | good
Fence condition. Fence needed? | no
Veg control needed? Describe | Aspen, willow, alder and wildings brushed
Animal or pest damage | no
Other damage (frost, human, fire) | Frost
Label and stake condition | Lots of stakes repounded----wooden stakes and need to be replaced with rebar and pvc.
Tree condition | Good survival—lw nice –lots of frost codes on the fir—looks like this past winter big setback
Wildlings need pulling? | Done
Comments/problems | Stakes redo with rebar and white posts. Work completed 2014—brushing and hand pulling 1.5 days 2015—if new markers 2 days
HOBO working? Repairs? | All good.
Site Name | Glenmerry
Date of visit | Aug 20th, 2015
Visitor(s) | Greg O'Neill and Faye Klassen
Notes by | Greg
What did you do? | Assessed contractor work. Measured survival and height on 5 columns of seedlings. Downloaded HOBO. Assessed brushing and wildlings.
Road condition/access | good
Fence condition. Fence needed? | no
Veg control needed? Describe | Very few seedlings compromised by brush, but lots of ingress that will require careful removal after all test trees are painted or staked.
Animal or pest damage | About 25% of ALL seedlings heavily deformed by hares.
Other damage (frost, human, fire) | none
Label and stake condition | Site has wood stakes. About 30% fallen over. Labels OK.
Tree condition | About 70% survival. Tallest trees about 1.5 m.
Wildlings need pulling? | Lots of ingress with multiple species.
Comments/problems/PLAN | Moderately rich site. In 2016 - First - replace wood stakes with rebar and PVC (1 pd). Second - place rigid stakes at base of all small test trees and/or paint test trees with a spot (1 pd), removing any Lw or Fdi trees from the Pickle trial (these may have a blue pinflag next to them). Third - remove all wildlings (2 pd). Forth - re-measure 2014 height and survival of all test trees.(3 pd)
HOBO working? Repairs? | All good.
AMAT SITE VISIT REPORT 2015
Site | Glenmerry
Date | Oct 12-13 2015
Visitor(s) | R. White Woods - J. Pelttari / J. Hepting
Notes by | J. Pelttari
Purpose of Visit | Measurement, site inspection, install rebar & PVC center posts & tags
Road Condition/access | Good, 2wd
Fence Condition/needed | N/A
Veg Control Needed? | Yes, willow and birch clumps re-sprouting
Animal/Pest Damage | Hare damage, some browse
Other damage (frost/human/fire | Extensive damage across whole site on all species - bark splits, lesions
multiple open scars on stem and branches on west side of trees
Likely sunscald
Label and stake condition | Good, wooden center posts replaced with rebar & PVC, re-tagged.
Tree Condition | Good survival and growth on most seedlots. Sunscald damage on most
trees, see above.
Wildlings need pulling? | Yes - Sx , Bl, Pl coming in
Comments/problems
Brushing and ingress control - 2016 | 4-5 person days with brush saws is needed
Brushing and ingress control - 2017 | 2 person days with brush saws if maintained in 2016
Site Name | Glenmerry
Date of visit | Oct.12-14 2017
Visitor(s) | J.Cooney/D. Gustafson
Notes by | J. Cooney
Road condition? Access notes updated? | good
Fence condition. | N/A
Vegetation - type, amount and height? Affecting seedlings? | areas of cottonwood,aspen, willow. ingress of Sx, Fd throughout
Animal or pest damage? | browse on many test trees
Other damage (frost, human, fire) | No
Label and stake condition | tags in good condition
Tree height? Survival? | good survival of most species
Wildlings - amount, height, species?
HOBO - Downloaded? Batteries changed? OK button flashing? | Hobo downloaded, batteries changed, OK blinking
What did you do at the site? Describe each task (e.g., pinned live seedlings, brushed, removed ingress, replaced centre stakes, measured, downloaded, etc.) and number of person-days spent on each task. | site completely brushed, trees flagged with alternating colours
PLAN? For each task (replace centre stakes, pin live test seedlings, remove ingress, measure, brush and download). For each task, describe when it is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | 2 pd in 2019 to maintain site
Comments/problems?
Site Visit Report ver5
Site Name | Glenmerry
Date of visit | Aug 8-11 2019
Visitor(s) | J. Pelttari / J. Hepting - R. White Woods
Notes by | J. Pelttari
Road condition? Access notes updated? | Good, 2wd, last few kms are rough and slow. No change.
Fence condition. | N/A
Vegetation - type, amount and height? Affecting seedlings? | Much of the site has come in with tall grass, fireweed and thimbleberry. Other areas had lots of aspen and cottonwood.
Animal or pest damage? | Some weevil.
Other damage (frost, human, fire) | Some frost.
Label and stake condition | Good.
Tree height? Survival? | Some Pl and Lw >4m, some Sx, Py & Fdi >3m, Bg & Bl doing ok, good survival of Cy, some pushing 2m, Ba hanging in but small.
Wildlings - amount, height, species? | A lot of Sx, Bl, Fd, Pl ingress 15-80 cm.
HOBO - Downloaded? Batteries changed? OK button flashing? | Hobo was not running. Replaced batteries and downloaded, data looks ok. Replaced dessicants and relaunched. OK light flashing when we left.
What did you do at the site? Describe each task (e.g., pinned live seedlings, brushed, removed ingress, replaced centre stakes, measured, downloaded, etc.) and number of person-days spent on each task. | Brushed the site, 4 pd. Measured and downloaded, 4 pd.
PLAN? For each task (replace centre stakes, pin live test seedlings, remove ingress, measure, brush and download). For each task, describe when it is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Download and brush in 2021, 4 pd.
Comments/problems?
Site Visit Report ver5
Site Name | Glenmerry
Date of visit | 17 September, 2019
Visitor(s) | Rachel Reed and Marie Vance
Notes by | Rachel Reed
Road condition? Access notes updated? | Good, 2wd, last few kms are rough and slow. No change.
Fence condition. | N/A
Vegetation - type, amount and height? Affecting seedlings? | Lots of fireweed, thimbleberry. Most woody ingress is aspen. Seedlings largely unaffected
Animal or pest damage? | Animal damage on a few trees in Lw and Py. Evidence of blister rust in Pw, adelgid in Sx, and some Western gall in Lodgepole, less than ten percent of trees
Other damage (frost, human, fire) | snow press in At - growth snaking on ground
Label and stake condition | Good.
Tree height? Survival? | Most under 3m, a few Pl and Lw larger than 4m
Wildlings - amount, height, species? | A few Sx ingress - brushing job was well done
HOBO - Downloaded? Batteries changed? OK button flashing? | Hobo was running on arrival and had been recently downloaded.
What did you do at the site? Describe each task (e.g., pinned live seedlings, brushed, removed ingress, replaced centre stakes, measured, downloaded, etc.) and number of person-days spent on each task. | Scrutiny, measured 100 trees to assess contractor work
PLAN? For each task (replace centre stakes, pin live test seedlings, remove ingress, measure, brush and download). For each task, describe when it is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Download and brush in 2021, 4 pd.
Comments/problems?
Site Visit Report ver5
Site Name | Glenmerry
Date of visit | June 15-17 2021
Visitor(s) | J. Pelttari / J. Hepting - R. White Woods Inc.
Notes by | J. Pelttari
Road condition? Access notes updated? | Good, 2 wd access directly to site.
Fence condition. | N/A
Vegetation - type, amount and height? Affecting seedlings? | Willow & alder clumps < 1.3m, aspen & cottonwood < 1m
Animal or pest damage? | Some adelgid and gall rust, some browse.
Other damage (frost, human, fire) | Some frost
Label and stake condition | Good, some leaning.
Tree height? Survival? | Fd & Lw doing best some up to 5m, Pl to 4.5 some snow damage, Cy & Bg up to 2.5m some frost on Bg, aspen to 3m, Pw to 2m
Wildlings - amount, height, species? | Pl, Bl, Sx, Lw < 50cm
HOBO - Downloaded? Batteries changed? OK button flashing? | HOBO was not running, stopped Nov 2020, no damage. Changed batteries and downloaded, data looks good, replaced dessicants and relaunched. OK light blinking.
What did you do at the site? Describe each task (e.g., pinned live seedlings, brushed, removed ingress, replaced centre stakes, measured, downloaded, etc.) and number of person-days spent on each task. | Brushed hardwood and conifer ingress. Downloaded and serviced weather station. 4 pd.
PLAN? For each task (replace centre stakes, pin live test seedlings, remove ingress, measure, brush and download). For each task, describe when it is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Brush and DL in 2023. 4 pd.
Comments/problems?