## Site visit
Site name | Golden
Date planted | May 2-6, 2012
Planting Crew names | Mary Fraser, Jonah Fraser, Ben Woods, MW
Report by | Mary Fraser
site coordinates NW | see site map
site coordinates NE
site coordinates SE
site coordinates SW
Site history | logged in 2010 (cable yarded).
Native tree species (% composition) | Fdi> Sx>>Pli, Pw, Cw, Aspen, Birch
Native non-tree species (% cover) | maple, raspberry, boxwood
Soil type (clayey silt, sandy loam, etc) | sandy loam
Slope (%), Slope position (crest, upper, mid, lower) | 35%
Aspect (e.g., NW) | SW
Coarse fragment content (%) | 3%
Stock condition | good Ycc dry
Soil moisture | good perfect
Weather | 8°- 16° C
Soil condition (e.g., compacted, fluffy) | Fluffy
Labels | Good
Slash | very little 20%
Vegetation control req'd? | perhaps at year 5 after harvest (2015)
Deer/elk/cattle control req'd? | no
Surrounds planted? | no, operational plant up to site. Be sure not to brush surrounds closest to trial as they will act as a buffer.
Weather station installed? | Yes
Wildlings need pulling? | A few - perhaps at year 5
Comments/problems | Steeply sloping but uniform site. Rectangular cutblock. Perimeter flagged. Bears in the area. 2 1/2 hour drive from Golden to site, road washed out with lots of ruts, 1/2 dozen slides, one bad slide in front of the site.
Site | Golden
Date | Sept 7 2013
Visitor(s) | R. White Woods - J. Pelttari / J. Hepting
Notes by | J. Pelttari
Purpose of Visit | HOBO download & maintenance, site inspection
Road Condition/access | 2 wd access but very long drive, rough road, lake level issues
Fence Condition/needed | N/A
Veg Control Needed? | Yes, lots of large hardwoods
Animal/Pest Damage | No
Other damage (frost/human/fire | Some frost
Label and stake condition | Good
Tree Condition | Good survival, some trees suppressed under hardwood clumps
Wildlings need pulling? | Some.
Comments/problems | About 40% of the site is covered with Birch, Alder, and Maple
clumps up to 3 meters tall. Smaller competing hardwoods are
present throughout the rest of the site. The establishment
notes however say "veg control not required until 2015".
We estimate brushing will take 6 - 8 person days. Because of
the size of the hardwoods to be removed, the slope, and the
chances that snow this winter will move cut brush over test
trees, we decided to leave brushing until spring 2014.
Site Name | Golden
Date of visit | October 25th, 2014
Visitor(s) | D. Evans & M. Brown
Notes by | Mike Brown
Purpose of visit | HOBO download & brushing
Road condition/access | good
Fence condition. Fence needed? | no
Veg control needed? Describe | Totally brushed--- lots of hardwoods, all cedar ingress removed
Animal or pest damage | none
Other damage (frost, human, fire) | nil
Label and stake condition | Good.
Tree condition | good
Wildlings need pulling? | Done ---Maybe spraying next year to rid site of hardwoods. Work completed 2014—6 days 2015---if spray 3 days
Comments/problems | none
HOBO working? Repairs? | All good.
Site Visit Report ver5
Site Name | Golden
Date of visit | September 20-28, 2016
Visitor(s) | R White Woods - Jeff Cooney and John Hepting
Notes by | Jeff Cooney
Road condition? Access notes updated? | road in good condition, access unchanged, very long drive to site
Fence condition. | N/A
Vegetation - type, amount and height? Affecting seedlings? | very heavy resprouting of maple and also much new small maple
Animal or pest damage? | minimal Sx weevil and adelgid
Other damage (frost, human, fire) | winter kill
Label and stake condition | Good, installed PVC, moved labels to new PVC
Tree height? Survival? | Approx. 75% survival; most survivors near 1 m tall
Wildlings - amount, height, species? | heavy willow, maple, alder, aspen
HOBO - Downloaded? Batteries changed? OK button flashing? | Yes to all.
What did you do at the site? Describe each task (e.g., pinned live seedlings, brushed, removed ingress, replaced centre stakes, measured, downloaded, etc.) and number of person-days spent on each task. | Measured test trees + pinned/painted (6 pd), Brush & remove primarily hardwoods around test trees (9 pd), Travel (2 pd), installed new PVC and moved tags (1.5 pd)
PLAN? For each task (replace centre stakes, pin live test seedlings, remove ingress, measure, brush and download). For each task, describe when it is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | This is a very brushy site and we concentrated our brushing efforts in insuring that each tree was brushed around. It is also a steep and awkward site and movement is slow. This site will need annual cleaning around trees for a few years (6-8 pd). We recommend the site be fully brushed in 2017 or 2018.
Comments/problems? | difficult site to walk; 2.5 hr to site with heavy logging traffic
Site Visit Report ver5
Site Name | Golden
Date of visit | Nov2016
Visitor(s) | Scott King
Notes by | Scott King
Road condition? Access notes updated?
Fence condition.
Vegetation - type, amount and height? Affecting seedlings?
Animal or pest damage?
Other damage (frost, human, fire)
Label and stake condition
Tree height? Survival?
Wildlings - amount, height, species?
HOBO - Downloaded? Batteries changed? OK button flashing?
What did you do at the site? Describe each task (e.g., pinned live seedlings, brushed, removed ingress, replaced centre stakes, measured, downloaded, etc.) and number of person-days spent on each task. | inspection
PLAN? For each task (replace centre stakes, pin live test seedlings, remove ingress, measure, brush and download). For each task, describe when it is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Brushing not required until 2018. Brush dogwood and douglas maple to 1.0 m from each tree. Ensure falsebox is well-brushed as it is a strong moisture competitor.
Comments/problems? | Brushing done better in 2016 than in 2014.
Site Visit Report ver5
Site Name | Golden
Date of visit | Aug 8-11 2018
Visitor(s) | Jeff Cooney, Darren Gustafson
Notes by | Jeff Cooney
Road condition? Access notes updated? | Good
Fence condition. | N/A
Vegetation - type, amount and height? Affecting seedlings? | clumps of Birch, Maple. and Aspen through out block.
Animal or pest damage? | no
Other damage (frost, human, fire) | no
Label and stake condition? 5' PVC centre stakes in place? | good
Tree height? Survival? | 30cm-250cm. Good
Wildlings - amount, height, species? | few Fd 30 cm
HOBO - Downloaded? Batteries changed? OK light flashing? | yes
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | Hobo not logging on arrival. Download,change batteries, Hobo logging. Brush site clearing around smaller trees and cutting clumps of hardwoods back to open up trees. Brush trail into site. New research sign installed
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | it is a productive site and will need regular maintenance. Resprouting of maple very heavy. Many of the trees are well above the competition.
Comments/problems? | very long drive to site with heavy logging traffic.
Site Visit Report ver5
Site Name | Golden
Date of visit | Aug 8-11 2018
Visitor(s) | Jeff Cooney, Darren Gustafson
Notes by | Jeff Cooney
Road condition? Access notes updated? | Good
Fence condition. | N/A
Vegetation - type, amount and height? Affecting seedlings? | clumps of Birch, Maple. and Aspen through out block.
Animal or pest damage? | no
Other damage (frost, human, fire) | no
Label and stake condition? 5' PVC centre stakes in place? | good
Tree height? Survival? | 30cm-250cm. Good
Wildlings - amount, height, species? | few Fd 30 cm
HOBO - Downloaded? Batteries changed? OK light flashing? | yes
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | Hobo not logging on arrival. Download,change batteries, Hobo logging. Brush site clearing around smaller trees and cutting clumps of hardwoods back to open up trees. Brush trail into site. New research sign installed
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | it is a productive site and will need regular maintenance. Resprouting of maple very heavy. Many of the trees are well above the competition.
Comments/problems? | very long drive to site with heavy logging traffic.
Site Visit Report ver6
Site Name | Golden
Date of visit | September 10-15, 2020
Visitor(s) | Jeff Cooney and Michel Bergeron - R. White Woods Inc.
Notes by | Jeff Cooney
Road condition? Access notes updated? | long drive, very busy industrial road, good shape
Fence condition. | no fence
Vegetation - type, amount and height? Affecting seedlings? | large amount of maple/birch/alder resprouts - all cutdown with brushsaws
Animal or pest damage? | none observed
Other damage (frost, human, fire) | none observed
broken PVC | much showpress with bent rebar and broken PVC. Suggest redo next year
Tree height? Survival? | fairly good overall
Wildlings - amount, height, species? | all conifer and hardwoods cutdown this visit
HOBO - what did you OBSERVE on arrival? Which light was flashing? Any damage? Faceplate leaking? Precip bucket screen clean? Are the sensors working? | OK light flashing. No damage. No leaks. Bucket cleaned, sensors working
HOBO - what did you DO? Was the data successfully downloaded? Is there data in both the temp and precip columns? Sensors or faceplate replaced? Batteries changed? Vaseline applied to faceplate? OK button pushed after changing batteries? OK light flashing on departure? | Inspection, servicing, download, change batteries and dessicant. OK light flashing.
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | Used brushsaws to cut thick hardwood re-sprouts and new sprouts.
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Brushing was much more than forecast in 2018. Actual time was 12pd. It is anticipated that 10 pd will be required in 2022 or at the next measurement.
Comments/problems? | will need posts replaced with short ones to avoid snowpress - 2 pd
Site Visit Report ver5
Site Name | Golden
Date of visit | Aug 3-7 2021
Visitor(s) | J. Pelttari/J. Hepting - R. White Woods Inc
Notes by | J. Pelttari
Road condition? Access notes updated? | Long drive - 2:30-2:45 hr drive on dusty very active logging road
Fence condition. | N/A
Vegetation - type, amount and height? Affecting seedlings? | Heavy resprout of birch, aspen and willow plus buckbrush and other shrubs.
Animal or pest damage? | Some browse and adelgid.
Other damage (frost, human, fire) | Some snow,frost, and drought .
Label and stake condition | Most posts leaning a few broken. Labels are attached with zap straps, some sliding down the post.
Tree height? Survival? | Good survival in most plots. Some Pl & Lw over 5m, Fdi to 4m, Sx to 2,5m, Cw to 2m. Good survival of Yc, >1.5. Good survival of Ep but leaves browned by heat wave.
Wildlings - amount, height, species? | Some Fd ingress.
HOBO - Downloaded? Batteries changed? OK button flashing? | HOBO was running. Downloaded, data looked good. Replaced batteries and dessicants, relaunched. OK light was flashing.
What did you do at the site? Describe each task (e.g., pinned live seedlings, brushed, removed ingress, replaced centre stakes, measured, downloaded, etc.) and number of person-days spent on each task. | DL and Measurement. (6.5pd)
PLAN? For each task (replace centre stakes, pin live test seedlings, remove ingress, measure, brush and download). For each task, describe when it is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Site will need brushing in 2022 (Est 8-10 pd)
Comments/problems?