## Site visit
Site name | Haines Alaska
Date planted | June 15-19, 2012
Planting Crew names | Jonah Fraser, Ben Woods, MW 2 Alaska Planters
Report by | Jonah Fraser
site coordinates | 59° 25' 18" 136°15' 16"
Site history
Native tree species (% composition) | Sx Hw, Ct
Native non-tree species (% cover) | dogwood, maple ash, devils club
Soil type (clayey silt, sandy loam, etc) | sandy loam
Slope (%), Slope position (crest, upper, mid, lower) | flat
Aspect (e.g., NW) | flat
Coarse fragment content (%) | while site was ROCK
Stock condition | good
Soil moisture | perfect
Weather | mild
Soil condition (e.g., compacted, fluffy) | fluffy but rocky
Labels | good
Slash | mild
Vegetation control req'd? | Need to pin flag all sites but this one will come back thick
Deer/elk/cattle control req'd? | No deer but moose and vole damage. No tree cones to install
Surrounds planted? | yes
Weather station installed? | yes
Wildlings need pulling? | no, rich site vergetation will come back quick and thick
Comments/problems | Site, wild, coastal and wet, very rich site. Glacial till, some woody debris. Woody debris (cottonwood) to be removed by Alaska Forest Service (Greg Palmeri) and put to one side. No grass, logged summer 2011 Good access Moose, bear in area. Undulating site, lots of rock. Some skid trails on site
Site | Haines
Date | July 25th, 2013
Visitor(s) | Roy of Alaska Dept of Natural Resources
Notes by | Vicky
Purpose of visit
Road condition/access
Fence condition. Fence needed?
Veg control needed? Describe. | Phoned Roy and asked if he thought the site needed brushing this year. He said he was by it yesterday and it would NOT require any maintenance in 2013.
Animal or pest damage
Other damage (frost, human, fire)
Label and stake condition
Tree condition
Wildlings need pulling?
Comments/problems
Site | Haines Alaska
Date | 2015-08-10
Visitor(s) | Vicky Berger, David Hickman, Greg Palmeri
Notes by | Vicky Berger
What did you do at the site? | Assessed the site for brushing and maintenance requirements before measuring in 2016
Road condition/access | Excellent
Fence condition. Fence needed? | N/A
Veg control needed? Describe | YES!! There was a lot of cottonwood ingress as well as other herbaceous. No maintenance has been done on the site to date. The surviving crop trees should be pinned with PVC stakes next spring, then the site brushed and then measured. Greg will look into finding a contractor that would be willing to do the work for us... Perhaps retired Roy Josephson
Animal or pest damage | nothing of significance
Other damage (frost, human, fire) | Good
Label and stake condition | nothing of significance
Tree condition/Survival | Good survival in many species, Coastal Douglas fir dead, interior hemlock dead. Spruce and pine 1.5-2 meters tall
Wildlings need pulling? | Yes, there was quite a bit of spruce ingress that can be removed at the time of brushing.
Comments/problems? PLAN? (Be specific- when and how many person days for each task) | See Veg control above. Greg Palmeri will work with us to get the work done next spring-fall. It will take 2 person days to place pvc stakes at each tree as there is good survival and tall vegetation. The brushing will take 4 person days and the measurements 2.5 person days.
HOBO working? Repairs? | Yes. Greg will download data logger again this fall.
Site | Haines
Date | Sept 15-20 2016
Visitor(s) | J. Pelttari, D. Gustafson - R. White Woods Inc.
Notes by | J. Pelttari
Road condition? Access notes updated? | Good 2wd access, notes updated.
Fence condition. | N/A
Vegetation - type, amount and height? Affecting seedlings? | Very heavy red-osier dogwood + high-bush cranberry, elderberry, willow, alder & cottonwood up to 4m tall, strongly affecting seedlings.
Animal or pest damage? | No
Other damage (frost, human, fire) | No
Label and stake condition | 4' schedule 20 PVC posts hard to see and many broken. Due to logistics 5' PVC was not installed on this trip. This can be done on the next northern trip tying in with Ft St John & Ft Nelson or Terrace/Kitimat.
Tree height? Survival? | Fdc are all dead, Fdi about 50% survival, up to 1.4m. Pl up to 2m. Best looking Sx in all of AMAT, up to 1.6m. Only a few Hw still alive. Ba, Cw, Yc, Ep hanging in.
Wildlings - amount, height, species? | Scatterd small Hw and Ss.
HOBO - Downloaded? Batteries changed? OK button flashing? | Weather station was severly damaged, attacked by moose or bear, all cables torn out, rain bucket crushed. Note: (This is strange - there were no batteries in the Hobo, only dessicants. Batteries were found on the ground AND the face plate was still on the Hobo and undamaged...) Replaced the entire weather station and launched Hobo.
What did you do at the site? Describe each task (e.g., pinned live seedlings, brushed, removed ingress, replaced centre stakes, measured, downloaded, etc.) and number of person-days spent on each task. | Measured + pinned/painted test trees (5 pd), brushed dogwood, elderberry and cranberry from around test trees, removed all cottonwood alder & willow, removed wildlings (5 pd), replaced weather station (.25 pd)
PLAN? For each task (replace centre stakes, pin live test seedlings, remove ingress, measure, brush and download). For each task, describe when it is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Site will need brushing of shrubs, hardwoods and conifers in 2018, at next Hobo download (5-6 pd + 4 pd travel)
Comments/problems?
Site Visit Report ver5
Site Name | Haines
Date of visit | Aug 6-9 2018
Visitor(s) | J. Pelttari / W. Gordon
Notes by | J. Pelttari / W. Gordon
Road condition? Access notes updated? | Good, 2wd access directly to site
Fence condition. | N/A
Vegetation - type, amount and height? Affecting seedlings? | Large patches of red osier dogwood up to 1.5 m tall, willow clumps resprouted from previous brushing, cottonwood resprout. Dogwood has affected seedling causing mortality in early years.
Animal or pest damage? | Yes, heavy damage to Pl by Moose, most Pl plots have all trees killed or badly damaged, only a few Pl plots in slashier areas are intact.
Other damage (frost, human, fire)
Label and stake condition? 5' PVC centre stakes in place? | Good. 5' PVC installed and new labels attached.
Tree height? Survival? | Pl were doing the best in terms of height growth but most have been killed by Moose. Sx are doing very well
Wildlings - amount, height, species? | Numerous Ss and Hw up to 40 cm - removed.
HOBO - Downloaded? Batteries changed? OK light flashing? | Weather station had been completely destroyed by Moose or Bear in 2016. After straightening the pole and replacing all of the components, I neglected to hit the Button Start so no data recorded Sept 2016-Aug 2018. My apologies. Batteries changed and HOBO restarted.
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | Installed 5' PVC center posts and attached new labels, 1 pd. Brushed hardwoods, cut paths through dogwood and cleared around test trees, removed conifer ingress, replaced HOBO batteries and re-started, 6.5 pd
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | This site is not due for measurement until 2021. It will need brushing and a HOBO download before then, possibly in 2020 when the Mackezie and Ft St John sites are due for measurement. Brushing and download, 6 pd.
Comments/problems?
Site Visit Report ver6
Site Name | Haines
Date of visit | 2020-10-22
Visitor(s) | GPalmieri
Notes by | GPalmieri
Road condition? Access notes updated? | good - none
Fence condition. | NA
Vegetation - type, amount and height? Affecting seedlings? | cut brush sprouting(1 - 1.5m Ht.) impacting some smaller seedlings
Animal or pest damage? | some new animal damage, broken tops noticed in Spruce seedlings
Other damage (frost, human, fire) | none
Label and stake condition? 5' PVC centre stakes in place? | some center stakes broken, most are good
Tree height? Survival? | many seedlings now 2-3m tall, consistently overtoping brush.
Wildlings - amount, height, species? | natural regen typical with majority <30cm tall
HOBO - what did you OBSERVE on arrival? Which light was flashing? Any damage? Faceplate leaking? Precip bucket screen clean? Are the sensors working? What type of microstation is in place? | Temp/RH sensor damaged, appeared to be "chewed" through at cable ends. No lights flashing. Precip bucket functioning. 1 sensor was found when connected to device and data downloaded and Hobo relaunched, but no data points in collected data.
HOBO - what did you DO? Was the data successfully downloaded? Is there data in both the temp and precip columns? Sensors or faceplate replaced? Batteries changed? Vaseline applied to faceplate? OK button pushed after changing batteries? OK light flashing on departure? | 10/28-returned to repair sensor by splicing in old Temp/RH sensor from previously replaced weather station, installed new batteries, sealed face plate, found three sensor when connected to device and relaunched data collector. OK light flashing on departure.
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | No. Just a walk through on 10/22.
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Replace weather station, adding a section of pipe. Some brush cutting and center stake replacement.
Comments/problems?
Site Visit Report ver6
Site Name | Haines
Date of visit | 2021-06-14
Visitor(s) | GPalmieri
Notes by | GPalmieri
Road condition? Access notes updated?
Fence condition.
Vegetation - type, amount and height? Affecting seedlings?
Animal or pest damage?
Other damage (frost, human, fire)
Label and stake condition? 5' PVC centre stakes in place?
Tree height? Survival?
Wildlings - amount, height, species?
HOBO - what did you OBSERVE on arrival? Which light was flashing? Any damage? Faceplate leaking? Precip bucket screen clean? Are the sensors working? What type of microstation is in place?
HOBO - what did you DO? Was the data successfully downloaded? Is there data in both the temp and precip columns? Sensors or faceplate replaced? Batteries changed? Vaseline applied to faceplate? OK button pushed after changing batteries? OK light flashing on departure?
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task.
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd)
Comments/problems? | Hobo thrashed by bear