## Recon_Establishment
AMAT test site recon/establishment report
Site name | Kitsumkalum NW of Terrace
Date planted | June 19-21, 2011
Planting Crew names | Future Forests, Mary Fraser Jonah, Ben, Kenton Hannah
Report by | Recon report by Michael Carlson Fall 2010
Establishment Report by Mary Fraser Future Forests
Site history | harvested Fall 2009 Site prepped Fall 2010
Native tree species (% composition) | Hw 28% Bl 71% Sx <1% Ac <1%
Native non-tree species (% cover) | blueberry, elderberry, salmonberry, mountain ash
Soil type (clayey silt, sandy loam, etc) | clay with lots fo organic and duff
Slope (%), Slope position (crest, upper, mid, lower) | gentle 10% crest, 60% mid, 30 % lower
Aspect (e.g., NW) | SE
Coarse fragment content (%) | 25% rock, 25% buried logs, 40% heavy organic duff
Stock condition | frozen had to thaw for a day
Soil moisture | 35 % dry 20% soggy 55% moist
Weather | cloudy 16° C
Soil condition (e.g., compacted, fluffy) | 10% compacted, the rest good
Labels | good
Slash | 15%
Vegetation control req'd? | lots of Hw coming in, maybe brush in 2013
Deer/elk/cattle control req'd? | No problems expected with deer browse, maybe a little moose browse. Should watch for vole damage.
Surrounds planted? | Yes, except in burn piles and swamp area
Weather station installed? | Yes
Wildlings need pulling? | No, but Hw will need controlling
Comments/problems | Tad short on space-- only 2/3 of surrounds had room for planting. Varying degrees of soil conditions re: swamps to dry areas. Mega bugs!
Only 3 reps of LC SS Label 208 Rep 4 had no SS LC

## Site visit
Site visit report
Site | Kitsumkalum
Date | Oct. 4, 2012
Visitor(s) | J. Cooney & D. Gustafson of R. White Woods
Notes by | J. Cooney
Purpose of visit | Download HOBO / site maintenance
Road condition/access | Good
Fence condition. Fence needed? | N/A
Veg control needed? Describe. | fireweed
Animal or pest damage | N/A
Other damage (frost, human, fire) | no
Label and stake condition | Good
Tree condition | Good
Wildlings need pulling? | N/A
Comments/problems | 2 person days should be scheduled next viist to ensure trees are free to grow
HOBO working? Repaired? | OK
Site | Kitsukalum Lake
Date | 09/29/2013
Visitor(s) | R. White Woods (J. Pelttari, J. Hepting)
Notes by | J. Pelttari
Purpose of Visit | HOBO download, site inspection, brushing.
Road Condition/access | Good, 2wd.
Fence Condition/needed | N/A
Veg Control Needed? | Hardwoods removed, competing Raspberry cut back - 2013
Animal/Pest Damage | No
Other damage (frost/human/fire | No
Label and stake condition | Good
Tree Condition | Good survival & growth
Wildlings need pulling? | Conifer ingress (Hw, Ba) removed - 2013
Comments/problems
Site Name | Kitsumkalum Lake
Date of visit | June 20th, 2014
Visitor(s) | J. King, E. van Eeden, Jesse, T. Jeppesen & M. Brown
Notes by | Mike Brown
Purpose of visit | HOBO download & brushing
Road condition/access | good
Fence condition. Fence needed? | n/a
Veg control needed? Describe | Brushing completed. .
Animal or pest damage | nil
Other damage (frost, human, fire) | nil
Label and stake condition | Good. Suggest use tall white pvc pipe over existing aluminum centre posts in future.
Tree condition | Good survival and growth.
Wildlings need pulling? | done
Comments/problems | Site clean of naturals, trees are free to grow Work completed 2014—3 days 2015--0
HOBO working? Repairs? | All good.
Site Name | Kitsumkalum Lake
Date of visit | 2015-09-01
Visitor(s) | Jim Peltari
Notes by | Vicky from conversation with Jim in the office
Purpose of visit | 5 year measurements and put pvc pipe over centre stakes
Road condition/access | good
Fence condition. Fence needed? | n/a
Veg control needed? Describe | no brushing as this was a measure only year
Animal or pest damage | nil
Other damage (frost, human, fire) | nil
Label and stake condition | Good.
Tree condition | Good survival and growth. No need to pin trees anymore
Wildlings need pulling? | Yes,
Comments/problems | Site requires removing ingress and brushing 2.0 person days
HOBO working? Repairs? | All good.
AMAT SITE VISIT REPORT 2015
Site | Kitsukalum Lake
Date | Sept 15 2015
Visitor(s) | R. White Woods - J. Pelttari / J. Hepting
Notes by | J. Pelttari
Purpose of Visit | Hobo download, remove ingress, install PVC on center posts.
Road Condition/access | Good, 2wd
Fence Condition/needed | N/A
Veg Control Needed? | Yes, alder and willow re-sprouting.
Animal/Pest Damage | Occasional weevil on Sx, Ss
Other damage (frost/human/fire | No
Label and stake condition | Good
Tree Condition | Good survival and growth, especially Pl and Ep
Wildlings need pulling? | Yes, some Hw, Cw & Ba
Comments/problems
Brushing & ingress control - 2016 | 2 person days
Brushing & ingress control - 2017 | 2 person days or 3-4 if not done in 2016
Site Visit Report ver5
Site Name | Kitsumkalum
Date of visit | 2016-08-30
Visitor(s) | Greg ONeill, Marie Vance
Notes by | Greg
Road condition? Access notes updated? | good. Yes.
Fence condition. | NA
Vegetation - type, amount and height? Affecting seedlings? | Lots of fireweed. Up to 1.5 m. some grass, raspberry
Animal or pest damage? | Cwr brosed; lots of weevil damage on Ss
Other damage (frost, human, fire) | no
Label and stake condition? 5' PVC centre stakes in place? | PVC stakes in place with labels screwed to PVC
Tree height? Survival? | Ep 5m; Pl 3.5 m; overall 80% surv
Wildlings - amount, height, species? | LOTS of Hw and Ba; bit of Ss and Dr 3-8 y.o.
HOBO - Downloaded? Batteries changed? OK button flashing? | yes, yes, yes
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | download 0.05 pd; manually removed ingress with clippers in 2 eastern-most columns of plots - 1.5 pd.
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Finish removing ingress in 2017 - 3 pd with brushsaws; 2-3 pd for flagging BEFORE any further brushing or measurements.
Comments/problems? | Need step stool to download hobo.
Comments/problems? | Large stumps resulted in a few crooked rows. Need to be careful when removing ingress and flagging trees.
Comments/problems? | Ingress has not been removed for at least 5 y
Comments/problems? | better access maps needed.
AMAT Kitsum Kalum, Terrace BC
Date of visit | Spring 2017
Visitor(s) | Future Forest Services Ltd.
Notes by | J. Fraser
Road condition? Access notes updated? | Good road conditions, notes updated
Fence condition. | n/a
Vegetation - type, amount and height? Affecting seedlings? | lush area with good growth of vegetation but not affecting test trees
Animal or pest damage? | none
Other damage (frost, human, fire) | none
Label and stake condition? 5' PVC centre stakes in place? | good condition, all present
Tree height? Survival? | great survival, 1.5m - 5m
Wildlings - amount, height, species? | Thick ingress in some areas with low, sparse vegetation in others
HOBO - Downloaded? Batteries changed? OK button flashing? | n/a
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | Site was completely brushed, all competing ingress and shrubs removed All test trees flagged with Winter weight Arctic Blue flagging 1m lenth
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd)
Comments/problems? | Perimeter of site needs to be brushed
Site Visit Report ver5
Site Name | kitsum
Date of visit | 19 and 23 Aug 2019
Visitor(s) | Rachel, lindsay, kyle greg
Notes by | greg
Road condition? Access notes updated? | Notes had us start 4 km west of the bridge at the west end of Terrace, however, it's much easier to start 40 m west of the bridge. Notes updated. Road full of potholes. Slow - about 25 km/h.
Fence condition. | na
Vegetation - type, amount and height? Affecting seedlings? | Hw, salmonberry, swordfern, Cw
Animal or pest damage? | nothing remarkable, some weevil in Spruce
Other damage (frost, human, fire) | some frost damage in Fdi and Cw.
Label and stake condition? 5' PVC centre stakes in place? | good. PVC in place w labels
Tree height? Survival? | tallest trees about 6 m. Overall survival about 80%.
Wildlings - amount, height, species? | lots!! Mostly hemlock, many 1-2m tall
HOBO - what did you OBSERVE on arrival? Which light was flashing? Any damage? Faceplate leaking? Precip bucket screen clean? Are the sensors working? | no light flashing on arrival, but after replacing batteries, and launching, everything good. Faceplate good. Top of rain gauge found on ground. Data appeared good, but stopped collecting in Nov 2017.
HOBO - what did you DO? Was the data successfully downloaded? Is there data in both the temp and precip columns? Sensors or faceplate replaced? Batteries changed? Vaseline applied to faceplate? OK button pushed after changing batteries? OK light flashing on departure? | No parts replaced. Old data downloaded, but no new data available. Replaced batteries and tested. yes yes yes.
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | Flagged and brushed trail into site. Manually brushed reps 1, 2, and 4 (2.5pd), removing much ingress. Downloaded and maintained weather station (0.5pd). Pickle trees are removed, except for rep 3.
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | This site will be measured in fall 2020 (4 pd). Should download (0.5 pd) and brush rep 3 in 2020 (1 pd). Except for rep 3, this site should not need brushing/ingress removal for 3 years.
Comments/problems? | Fix access notes. Use first exit to the R after the bridge leaving Terrace. Weather station data missing from November 6, 2017 to Aug 19, 2019. Recommend using loppers to remove ingress in Rep3.
Site Visit Report ver5
Site Name | Kitsumkalem
Date of visit | 2020-06-12
Visitor(s) | Rachel Reed, IA wildfire crew (Keelo, Del, Nigel)
Notes by | Rachel
Road condition? Access notes updated? | 2 ways to site - Zymagortz or Erlandsen mainline. Zymagortz is VERY rutted and slow, access notes updated to encourage use of Erlandsen.
Fence condition. | NA
Vegetation - type, amount and height? Affecting seedlings? | Lower brush and fern, not much affecting seedlings. Salmonberry, swordfern, Cw.
Animal or pest damage? | Some sx weevil
Other damage (frost, human, fire) | Some frost damage in Fdi and Cw
Label and stake condition? 5' PVC centre stakes in place? | Good.
Tree height? Survival? | tallest trees about 6 m. Overall survival about 80%.
Wildlings - amount, height, species? | LOTS of hemlock, some of them 2m tall or more.
HOBO - what did you OBSERVE on arrival? Which light was flashing? Any damage? Faceplate leaking? Precip bucket screen clean? Are the sensors working? | OK light was not flashing on arrival. No damage or leakage. Bucket clean.
HOBO - what did you DO? Was the data successfully downloaded? Is there data in both the temp and precip columns? Sensors or faceplate replaced? Batteries changed? Vaseline applied to faceplate? OK button pushed after changing batteries? OK light flashing on departure? | Downloaded data, replaced batteries and desiccant, vaselined faceplate, relaunched station. OK light flashing on departure - all sensors active.
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | Finished brushing Rep 3.
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Should not need attention for another 2-3 years, at which time it should be brushed.
Comments/problems? | There were "pickle" trees at this site (additional Sx planted in between trest tree rows). We think we got the rest of them, but next visitor for brushing should be careful.
Site Visit Report ver5
Site Name | Kitsumkalem
Date of visit | 2020-10-12
Visitor(s) | Future Forest Services Ltd. - J. Fraser, T. Fraser
Notes by | J Fraser
Road condition? Access notes updated? | Good road access
Fence condition. | n/a
Vegetation - type, amount and height? Affecting seedlings? | Fireweed, thimbleberry, swordfern, salmonberry, etc. Abundant throughout site. Approx. 1-2 m tall
Animal or pest damage? | minor amounts of weevil
Other damage (frost, human, fire) | Frost in Cedar and some Fir, evidence of some snow press
Label and stake condition? 5' PVC centre stakes in place? | Good PVC in place with labels
Tree height? Survival? | Overall good survival and height with tallest trees Ep up to 12m (See Data)
Wildlings - amount, height, species? | Very prolific site with lots of ingress Hw, Cw, Balsam, Willow. Approx 1m or less
HOBO - what did you OBSERVE on arrival? Which light was flashing? Any damage? Faceplate leaking? Precip bucket screen clean? Are the sensors working? | OK light was flashing. No damage. Faceplate not leaking but there was no dessicant. Rain bucket screen clean. Only two of the three sensors were operating.
HOBO - what did you DO? Was the data successfully downloaded? Is there data in both the temp and precip columns? Sensors or faceplate replaced? Batteries changed? Vaseline applied to faceplate? OK button pushed after changing batteries? OK light flashing on departure? | Downloaded Data successfully - data showed recording stopped October 27, 2019. Replaced with new rain bucket and sensor. New batteries. New Dessicant. Vaseline applied to faceplate. Yes pushed OK button after battery change. Relaunched with all sensors working. Yes, OK light flashing upon departure.
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | Measure Heights, Inspect and replace centre stakes if needed; Download Data from Hobo, inspected and replaced rain bucket
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Suggest Brushing 2021/2022 as site is lush, 3pd
Comments/problems?