## recon and establishment
AMAT test site recon/establishment report
Site name | Lynx Creek
Date planted | 23-25 June 2009
Planting Crew names | MF, JF, MC, VB, NU, GO
Report by | Greg
Site history | Harvested Jan 2007; commercially planted in 2008
Native tree species (% composition) | Pli and Bl
Native non-tree species (% cover)
Soil type (clayey silt, sandy loam, etc) | sandy loam
Slope (%), Slope position (crest, upper, mid, lower) | 2-10%; mid slope
Aspect (e.g., NW) | Southeast
Coarse fragment content
Stock condition | good
Soil moisture | very good
Weather | cold, wet
Soil condition (e.g., compacted, fluffy)
Labels | good
Slash | very little; some alder and aspen sprouts may need brushing;
Vegetation control req'd?
Deer/elk/cattle control req'd?
Surrounds planted? | yes
Weather station installed? | no
Wildlings need pulling? | YES!!!
Comments/problems | Will need to remove planted stock and abundant ingress; CBC documentary made same day as planting

## Site visit
Site visit report
Site | Lynx Creek
Date | October 2009
Visitor(s) | VB, MC, NU, GO
Notes by | Greg
Purpose of visit | survival survey; establish met station
Road condition/access | good
Fence condition. Fence needed? | none
Veg control needed? Describe. | no
Animal or pest damage | no
Other damage (frost, human, fire) | no
Label and stake condition | good
Tree condition | good
Wildlings need pulling? | YES!!!
Comments
Site | Lynx Creek
Date | Sept. 30, 2010
Visitor(s) | Tim, Ryan Mike
Notes by | Mike Brown
Purpose of visit | download HOBO weatherstation and relaunch
Road condition/access | good
Fence condition. Fence needed? | no
Veg control needed? Describe. | Brush 2011. Some ingress of Pli and Bl. Remove commerciallly planted spruce. Pin flag all living trees
Animal or pest damage? Type of control needed. | no
Other damage (frost, human, fire)
Label and stake condition
Tree condition | Dieback on Sx, Pli. Cy, Cw wiped out. Fdi.. Poor conditon
Wildlings need pulling? | Some commercially planted Sx need removing.
Comments
Site | Lynx Creek
Date | 2011-10-03
Visitor(s) | J. Cooney, D. Gustafson R. White Woods
Notes by | D. Gustafson
Purpose of visit | Hobo download, relaunch and brushing
Road condition/access | good/solid
Fence condition. Fence needed? | n/a
Veg control needed? Describe. | Lots of Pli ingress. Salix clumps
Animal or pest damage? Type of control needed. | none
Other damage (frost, human, fire) | frost
Label and stake condition | good stakes 6 tags missing
Tree condition | approx. 50% of trees survived
Wildlings need pulling? | wildlings pulled away from surviving trees
Comments | Lots of Pli ingress. Brushsaws 2013-2014
Site | Lynx Creek
Date | Oct. 5, 2012
Visitor(s) | J. Peltarri, J. Hepting of R. WhiteWoods
Notes by | J. Peltarri
Purpose of visit | HOBO download, maintenance and site inspection
Road condition/access | Good 2 WD
Fence condition. Fence needed? | N/A
Veg control needed? Describe. | scattered willow clumps, brush in 2013
Animal or pest damage? Type of control needed. | some browse
Other damage (frost, human, fire) | Frost damage
Label and stake condition | good, found/replaced missing labels
Tree condition | Approx 50% survival
Wildlings need pulling? | pulled around trees in 2011, brush in 2013 2 person days
Comments
HOBO working?Repair? | Yes
Site | Lynx Creek
Date | Aug 21 2013
Visitor(s) | R. White Woods
Notes by | Jim Pelttari
Purpose of Visit | Hobo download, measurement & brushing.
Road Condition/access | Good, 2wd
Fence Condition/needed | N/A
Veg Control Needed? | No
Animal/Pest Damage | Some adelgid on Sx
Other damage (frost/human/fire | Some frost
Label and stake condition | Good, a few missing tags replaced.
Tree Condition | Fdc, Hwc, Hwi, Cw, Cy - gone, Pw & Lw poor, most Pl & Sx ok
Wildlings need pulling? | Done
Comments/problems | Pl, B & Sx ingress, planted seedlings & hardwoods removed
Es removed
HOBO working?Repair?
Site Name | Lynx Creek
Date of visit | September 29th, 2014
Visitor(s) | E. van Eeden & M. Brown
Notes by | Mike Brown
Purpose of visit | HOBO download & brushing
Road condition/access | Good
Fence condition. Fence needed? | no
Veg control needed? Describe | Totally rebrushed with brushsaws tried to keep blades low to maximize as much setback as possible
Animal or pest damage | no
Other damage (frost, human, fire) | nil
Label and stake condition | Good.
Tree condition | Good in surviviors---Pli and sx slow growth
Wildlings need pulling? | Always be wildlings —constant problem also quite abit of hardwoods. Work completed 2014---3 days 2015---0
Comments/problems | Also did Charlies BL at top of hill
HOBO working? Repairs? | All good.
Site Name | Lynx Creek
Date of visit | July 8-10 2016
Visitor(s) | R. White Woods - Pelttari/Hepting
Notes by | J. Pelttari
Road condition? Access notes updated? | Good, 2wd access to site, no changes.
Fence condition. | N/A
Vegetation - type, amount and height? Affecting seedlings? | Mostly Willow clumps and some Alder, up to 1.3m. Affecting some seedlings. Removed in 2016.
Animal or pest damage? | Some adelgid
Other damage (frost, human, fire) | Some frost
Label and stake condition | Good, PVC center posts installed
Tree height? Survival? | Coastal & wetbelt SL's gone, some Pw & Lw doing ok , most Sx and Pli doing well, some Pli >1.5m
Wildlings - amount, height, species? | Pli up to 80 cm, thick in places, also Bl and Sx. Removed in 2016.
HOBO - Downloaded? Batteries changed? OK button flashing? | Yes, all good.
What did you do at the site? Describe each task (e.g., pinned live seedlings, brushed, removed ingress, replaced centre stakes, measured, downloaded, etc.) and number of person-days spent on each task. | Installed PVC center posts (.8 pd), pinned/painted test trees (1.5 pd), Brushed/removed ingress (2.5 pd), download (.2 pd)
PLAN? For each task (replace centre stakes, pin live test seedlings, remove ingress, measure, brush and download). For each task, describe when it is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Site should not require a visit until it is due for measurement in 2018. Batteries should last until then. Measurement in 2018 (4-5 pd), brushing & ingress removal (4 pd)
Comments/problems? | Logging of adjacent block created more wind, many tags off, most were found, the rest replaced with write-ons.
Site Name | Lynx Creek
Date of visit | July 9 2017
Visitor(s) | J. Pelttari - R. White Woods Inc.
Notes by | J. Pelttari
Road condition? Access notes updated? | Good, 2wd access to the site.
Fence condition. | N/A
Vegetation - type, amount and height? Affecting seedlings? | Willow and alder clumps re-sprouting, shrubs also.
Animal or pest damage? | Some adelgid
Other damage (frost, human, fire) | Some frost
Label and stake condition | Good.
Tree height? Survival? | Coastal & wetbelt SL's gone, some Pw & Lw doing ok , most Sx and Pli doing well, some Pli >2.0m
Wildlings - amount, height, species? | Pl, Sx and Bl coming back in <50 cm
HOBO - Downloaded? Batteries changed? OK button flashing? | Yes, all good.
What did you do at the site? Describe each task (e.g., pinned live seedlings, brushed, removed ingress, replaced centre stakes, measured, downloaded, etc.) and number of person-days spent on each task. | Hobo download and site inspection, .5 pd.
PLAN? For each task (replace centre stakes, pin live test seedlings, remove ingress, measure, brush and download). For each task, describe when it is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Due for measurement in 2018, 4 pds. brush hardwoods/shrubs and remove conifer ingress, 4-5 pds. Download .1 pd.
Site Visit Report ver5
Site Name | Lynx Creek
Date of visit | 2018-06-26
Visitor(s) | Trenna, Amy and Greg
Notes by | Greg
Road condition? Access notes updated? | excellent
Fence condition. | n/a
Vegetation - type, amount and height? Affecting seedlings? | bit of grass
Animal or pest damage? | n/a
Other damage (frost, human, fire) | drought evidence from 2017
Label and stake condition? 5' PVC centre stakes in place? | few stakes bent and heaved; label crushed
Tree height? Survival? | Sx ± 1.0 m
Wildlings - amount, height, species? | +++ Pl, ++ Sx, +Ba
HOBO - Downloaded? Data examined? Batteries changed? OK button flashing? | y,y,y
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | recon; download, assess veg comp
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | brushing, ingress 4 days 2018, replace labels
Comments/problems?
Site Visit Report ver5
Site Name | Lynx Creek
Date of visit | Sept 18-19 2018
Visitor(s) | J. Pelttari / J. Hepting - R. White Woods Inc
Notes by | J. Pelttari
Road condition? Access notes updated? | Good - 2wd access directly to site.
Fence condition. | N/A
Vegetation - type, amount and height? Affecting seedlings? | Numerous small willow clumps re-sprouting.
Animal or pest damage? | Some adelgid on Sx.
Other damage (frost, human, fire) | Some frost on Sx, lots of new mortality
Label and stake condition? 5' PVC centre stakes in place? | Good.
Tree height? Survival? | Good survival of Pl - some over 3m. Some Sx SLs doing well, Some Lw doing well, some Pw doing ok, a few Fdi surviving, 1 Cwi survives.
Wildlings - amount, height, species? | Numerous small Pl, Sx and Bl naturals, most under 40cm - removed.
HOBO - Downloaded? Batteries changed? OK light flashing? | Downloaded HOBO and saw that G.O had serviced HOBO in June 2018, added fresh dessicant packs, did not change batteries or re-launch HOBO.
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | Measured test trees, 2.4 pd. Brushed site, 1.6 pd.
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | This site will not require a visit until 2020 for HOBO download.
Comments/problems?
Site Visit Report ver5
Site Name | Lynx Creek
Date of visit | 2020-09-23
Visitor(s) | Sarina Meggait and Mikayla Stirling
Notes by | Sarina Meggait
Road condition? Access notes updated? | Very Good - Access Notes Updated Slightly
Fence condition. | N/A
Vegetation - type, amount and height? Affecting seedlings? | Grass - 30cm, Kinnikinnick, False Orange? (See Photos) - 40 - 60cm, Williow - max 1m. Grass, False Orange and Willow affecting seedlings slightly.
Animal or pest damage? | None noticed
Other damage (frost, human, fire) | None noticed
Label and stake condition? 5' PVC centre stakes in place? | Good. 5'PVC with rebar center in place. Aluminum labels on wire loops all attached.
Tree height? Survival? | Good survival of all pines, spruce and larch. Tree height from 30cm - 4m (lodgepole pine)
Wildlings - amount, height, species? | Lots of Lodgepole Pine - 20 to 40cm and a few 15cm or so Sx
HOBO - Downloaded? Batteries changed? OK light flashing? | Yes, yes, yes.
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | Download and maintain Wx station. Built a log stand at the base of the Wx station. Checked condition of aluminum tags and PVC stakes.
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | *Brush Lodgepole ingress - 1.5pd or so. I suggest trying to pull vs. using a brush saw in Spring 2021. *Transfer aluminum tags to the side of 5' PVC stakes from wire loops. .5pd
Comments/problems? | * Lots of Lodgepole ingress - 20+ per plot?. Should brush soon especially those near smaller test seedlings. *Wx station microstation is looking weathered. Small crack in bottom left corner not affecting seal. Whole station could be replaced in 1-2 years. * Roughly 90% of the test seedlings have pins at the base. 10% of pins either missing or lying down - if someone is up to brush send with pins to replace these as well. * Two 4m or so Sx on site older than 11 years at the NE? corner of the site - should be removed.
Site Visit Report ver5
Site Name | Lynx Creek
Date of visit | June 10-11 2021
Visitor(s) | J. Pelttari / J. Hepting - R. White Woods Inc.
Notes by | J. Pelttari
Road condition? Access notes updated? | Good, 2 wd access directly to site.
Fence condition. | N/A
Vegetation - type, amount and height? Affecting seedlings? | Willow and alder clumps < 1.3m, some asped and cottonwood < 80cm.
Animal or pest damage? | Some adelgid and gall rust.
Other damage (frost, human, fire) | Some frost. Drought.
Label and stake condition | Good, new labels attached with screws.
Tree height? Survival? | Pl & Lw doing best, some over 4.5m. Some Sx and Fdi SLs doing ok.
Wildlings - amount, height, species? | Pl, Bl and Sx ingress, mostly resprout, heavy in patches. Most < 50cm,
HOBO - Downloaded? Batteries changed? OK button flashing? | HOBO was running, data looks good. Replaced batteries and dessicants, relaunched. OK light blinking.
What did you do at the site? Describe each task (e.g., pinned live seedlings, brushed, removed ingress, replaced centre stakes, measured, downloaded, etc.) and number of person-days spent on each task. | Brushed hardwood and conifer ingress, attached new labels, downloaded and serviced weather station, 4 pd.
PLAN? For each task (replace centre stakes, pin live test seedlings, remove ingress, measure, brush and download). For each task, describe when it is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Brush and DL in 2023, 4 pd.
Comments/problems?