## Recon_establishment
AMAT test site recon/establishment report
Site name | McLeese Lake (formerly Skelton)
Date planted | 28 April 2010
Planting Crew names | Mary Fraser, Jonah Fraser, MC, GO
Report by | Greg
Site history | harvested 2007
Native tree species (% composition) | Pli 70; Sx 20, Bl 10, Dfi trace
Native non-tree species (% cover) | shrub alder
Soil type (clayey silt, sandy loam, etc) | Silty clay, good organic layer
Slope (%), Slope position (crest, upper, mid, lower) | flat
Aspect (e.g., NW) | flat
Coarse fragment content
Stock condition | good
Soil moisture | very good
Weather | overcast, 5 °C
Soil condition (e.g., compacted, fluffy) | compacted in some areas due to slash removal
Labels | applied
Slash | very little
Vegetation control req'd? | yes - chem spray req'd to control alder in 2011
Deer/elk/cattle control req'd? | possibly. Deed, moose and cattle scat observed.
Surrounds planted? | yes
Weather station installed? | yes
Wildlings need pulling? | yes. Lots of very small wildlings that will need pulling, esp in Pli plots
Comments/problems | Many plots were established in burn piles which had been burned the year before; 2 new planters; 1 row of Py (or Pw?) missing in Rep 1; Jonah brushed much of the alder and removed much ingress at layout, however will need to spray alder and continue to remove ingress

## Site visit
Site visit report
Site | McLeese Lake
Date | 2010-09-24
Visitor(s) | Michael Carlson
Notes by | Michael Carlson
Purpose of visit | Survival assessment brief (30 plot sample)
Road condition/access | good hard surface
Fence condition. Fence needed?
Veg control needed? Describe. | Some aspen/willow sprouting across ~50% of block-brush 2012.
Animal or pest damage
Other damage (frost, human, fire)
Label and stake condition
Tree condition | Entries dead or high % of damage(frost or drought): Fdc,(2), Hwc, (2), Cwc, Lw NE low, Lw IETIC, Fdc Weyco CB (8/32 plots) All other entries with little or no damage at this time.
Wildlings need pulling? | Much Pli ingress- give it another growing season and pull in 2012.
Comments/problems
Site | McLeese Lake
Date | Sept. 13, 2011
Visitor(s) | J. Peltarri, J. Hepting R. Whitewoods Inc
Notes by | J. Peltarri
Purpose of visit | HOBO download, site inspection and maintenance
Road condition/access | good
Fence condition. Fence needed? | n/a
Veg control needed? Describe. | No, aspen and willow removed
Animal or pest damage | some browse
Other damage (frost, human, fire) | some frost
Label and stake condition | good
Tree condition | Fdc, Hwc, Cwc, Bg dead or poor
Wildlings need pulling? | removed Pli ingress around test trees
Comments/problems | will require 1 man day to remove remaining ingress
Site | McLeese Lake
Date | Sept. 25, 2012
Visitor(s) | J. Pelttari/J Hepting
Notes by | J. Pelttari
Purpose of visit | HOBO download/site inspection
Road condition/access | Good, 2 WD
Fence condition. Fence needed? | N/A
Veg control needed? Describe. | No, aspen and willow removed in 201
Animal or pest damage | some browse
Other damage (frost, human, fire) | some frost
Label and stake condition | Good, 2 WD
Tree condition | Fdc, Hwc, Cwc, Bg -- dead or very poor
Wildlings need pulling? | No
HOBO working? Repairs? | Working fine
Comments/problems | Cleared around trees in 2011, remainder 2012
Site | McLeese Lake Skeleton
Date | July 31 2013
Visitor(s) | R. White Woods
Notes by | Jim Pelttari
Purpose of Visit | Hobo download & brushing.
Road Condition/access | Good, 2wd
Fence Condition/needed | N/A
Veg Control Needed? | No
Animal/Pest Damage | Some browse
Other damage (frost/human/fire | Some frost
Label and stake condition | Good, 2wd
Tree Condition | Coastal species gone, Some Bg, Pw, Fdi remain. Pli, Sx, Lw mostly ok
Wildlings need pulling? | Done
Comments/problems | Pl & Sx ingress, At, Ds & Salix removed
Comments/problems
Site Name | Mcleese
Date of visit | Sept 6th, 2014
Visitor(s) | D> Davis, E. van Eeden & M. Brown
Notes by | Mike Brown
Purpose of visit | HOBO download, measurements & brushing
Road condition/access | Good
Fence condition. Fence needed? | none
Veg control needed? Describe | Totally brushed, wildings pulled
Animal or pest damage | none
Other damage (frost, human, fire) | none
Label and stake condition | Good.
Tree condition | Most species except coastal looking good
Wildlings need pulling? | future
Comments/problems | Brush hardwoods again in 2015. Work completed 2014—2.5 days 2015—if spray 2 days
HOBO working? Repairs? | All good.
Site | McLeese Lake
Date | 2014-09-12
Visitor(s) | Greg
Notes by | Greg
Purpose of Visit | check on contractor work
Road Condition/access | very good
Fence Condition/needed | none. Not needed
Veg Control Needed? | good brushing done 2013(?). May be needed again (1 person day) in 2017?
Animal/Pest Damage | none
Other damage (frost/human/fire
Label and stake condition | good
Tree Condition | Pl>Sx>Fdi = Lw >>Yc
Wildlings need pulling? | About 70% of the wildlings appear to have been removed about 1 week ago. Will need to remove remaining wildlings in 2015, but first MUST insert plastic white pin beside each live seedling to avoid accidentally removing experimental trees.
Comments/problems
HOBO OK?
Site Visit Report ver5
Site Name | McLeese Lake
Date of visit | Aug 23-24 2016
Visitor(s) | R White Woods - J. Pelttari/J.Hepting
Notes by | J. Pelttari
Road condition? Access notes updated? | Good, 2wd, drive right to site. No
Fence condition. | N/A
Vegetation - type, amount and height? Affecting seedlings? | Willow, aspen and some alder, conifer ingress.
Animal or pest damage? | Some adelgid and browse
Other damage (frost, human, fire) | Some frost
Label and stake condition | Good.
Tree height? Survival? | Mostly Pl, Sx, Lw doing well. Some Fdi, Pw, Bg. A few Cy remain
Wildlings - amount, height, species? | Pl ingress, patchy, mostly under 80 cm
HOBO - Downloaded? Batteries changed? OK button flashing? | No, done earlier by Vanessa.
What did you do at the site? Describe each task (e.g., pinned live seedlings, brushed, removed ingress, replaced centre stakes, measured, downloaded, etc.) and number of person-days spent on each task. | Re-measured to 2014 height (4 pd). Also painted and pinned as we went.
PLAN? For each task (replace centre stakes, pin live test seedlings, remove ingress, measure, brush and download). For each task, describe when it is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Site is scheduled in 2017 for PVC center posts (.8 pd) and brushing, suggest ingress removal also. (3 pd)
Comments/problems? | Note: Someone stole one of the Pw - can see shovel marks around the planting spot. Weird.
Site Name | McLeese
Date of visit | Sept.26 2017
Visitor(s) | J.Cooney/D.Gustafson
Notes by | J. Cooney
Road condition? Access notes updated? | Good
Fence condition. | N/A
Vegetation - type, amount and height? Affecting seedlings? | Pl ingress majority of site. small amount of willow/alder
Animal or pest damage? | No
Other damage (frost, human, fire) | No
Label and stake condition | tags screwed to new PVC
Tree height? Survival? | Pl and Sx doing well. poor survival for most other species
Wildlings - amount, height, species?
HOBO - Downloaded? Batteries changed? OK button flashing? | Yes
What did you do at the site? Describe each task (e.g., pinned live seedlings, brushed, removed ingress, replaced centre stakes, measured, downloaded, etc.) and number of person-days spent on each task. | PVC added, download Hobo. Blinking OK. Brush site completely. total knock down
PLAN? For each task (replace centre stakes, pin live test seedlings, remove ingress, measure, brush and download). For each task, describe when it is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | 2 man/days in 2019 to remove small Pl ingress
Comments/problems? | spent 8 pds brushing
Site Visit Report ver5
Site Name | McLeese Lake (skeleton)
Date of visit | July 17 2018
Visitor(s) | Amy Vallarino and Paul Lichtblau
Notes by | Amy Vallarino
Road condition? Access notes updated? | good, new logging occuring 1km away
Fence condition. | n/a
Vegetation - type, amount and height? Affecting seedlings? | Pl and Al both <50cm, minimal
Animal or pest damage? | none
Other damage (frost, human, fire) | some drought dieback from 2017
Label and stake condition? 5' PVC centre stakes in place? | good
Tree height? Survival? | Pl (100%) 2-3m>Sx (80%) 1-1.5m> Fd (60%) 1m> Lw (40%) 0.5-1m
Wildlings - amount, height, species? | Pl ~ 50cm 5% coverage
HOBO - Downloaded? Data examined? Batteries changed? OK button flashing? | yes, yes,yes,yes
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | download logger, reposition smart sensor adaptor to horizontal position. Relaunch logger to button start from delayed start and switich to wrap memory. Renamed microstation to McLeese from Skeleton.
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | 1 person day removal of ingress
Comments/problems? | hot and sunny
Site Visit Report ver5
Site Name | McLeese Lake
Date of visit | July 13-15, 22-23 2019
Visitor(s) | J. Pelttari / J. Hepting - R. White Woods
Notes by | J. Pelttari
Road condition? Access notes updated? | Good, 2wd access directly to site, no change.
Fence condition. | N/A
Vegetation - type, amount and height? Affecting seedlings? | Moderate willow, alder and aspen, twinberry, crowding some small trees.
Animal or pest damage? | Stem disease on some Pl, likely Commandra blister rust.
Other damage (frost, human, fire) | Some frost.
Label and stake condition | Good
Tree height? Survival? | Pl doing best, some over 4m. Some Sx over 2 m. A few Lw pushing 3m. Py, Pw, Bg, At doing ok but small
Wildlings - amount, height, species? | Pl, Sx and Bl ingress, 30-80 cm.
HOBO - Downloaded? Batteries changed? OK button flashing? | Hobo was not running. Replaced batteries and downloaded - data looked ok. Replaced dessicants and relaunched. Ok light flashing when we left.
What did you do at the site? Describe each task (e.g., pinned live seedlings, brushed, removed ingress, replaced centre stakes, measured, downloaded, etc.) and number of person-days spent on each task. | Measured site, 3 pd. Brushed and downloaded, 4 pd
PLAN? For each task (replace centre stakes, pin live test seedlings, remove ingress, measure, brush and download). For each task, describe when it is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Download and brush in 2021.
Comments/problems?
Site Visit Report ver5
Site Name | McLeese Lake
Date of visit | June 5-6 2021
Visitor(s) | J. Pelttari/J. Hepting - R. White Woods Inc
Notes by | J. Pelttari
Road condition? Access notes updated? | Good - 2wd access directly to site.
Fence condition. | N/A
Vegetation - type, amount and height? Affecting seedlings? | Scattered small willow, cottonwood and alder. Not affecting trees.
Animal or pest damage? | Adelgid on Sx
Other damage (frost, human, fire) | Some frost on Bg & Pw.
Label and stake condition | Good.
Tree height? Survival? | Pl & Lw doing best, some Pl up to 5m. Some Sx SLs doing ok. Bg and Pw hangin in but small. At surviving but poor. Some Cy snd Cw surviving.
Wildlings - amount, height, species? | Scattered small Pl, Sx & Fd ingress
HOBO - Downloaded? Batteries changed? OK button flashing? | HOBO had stopped in Nov 2020. Changed batteries & downloaded, data looks good up to when it stopped. No damage to station components.
What did you do at the site? Describe each task (e.g., pinned live seedlings, brushed, removed ingress, replaced centre stakes, measured, downloaded, etc.) and number of person-days spent on each task. | Removed conifer & hardwood ingress, serviced HOBO (2 pd)
PLAN? For each task (replace centre stakes, pin live test seedlings, remove ingress, measure, brush and download). For each task, describe when it is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Site will not need any maintenance for a few years, just a DL in 2022/23.
Comments/problems?
Site Visit Report ver5
Site Name | McLeese Lake
Date of visit | May 16 2021
Visitor(s) | Greg, Marie
Notes by | Greg
Road condition? Access notes updated? | Good - 2wd access directly to site.
Fence condition. | N/A
Vegetation - type, amount and height? Affecting seedlings? | rose, grass, not affecting seedlings. Mossy and wet. Some standing water.
Animal or pest damage? | Cow sign; Sx weevil; Sx adelgid; WGR, commandra
Other damage (frost, human, fire) | frost on Pw
Label and stake condition | 5' PVC; aluminum labels in good condition.
Tree height? Survival? | tallest tree - Pl about 6 m
Wildlings - amount, height, species? | 5 Sx and 5 Fd / plot up to 30 cm tall
HOBO - Downloaded? Batteries changed? OK button flashing? | yes yes yes
What did you do at the site? Describe each task (e.g., pinned live seedlings, brushed, removed ingress, replaced centre stakes, measured, downloaded, etc.) and number of person-days spent on each task. | download, inspect
PLAN? For each task (replace centre stakes, pin live test seedlings, remove ingress, measure, brush and download). For each task, describe when it is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | attach tree tags next measurement
Comments/problems? | none