## Site visit report
Site | McLure
Date | Aug 15 2013
Visitor(s) | R. White Woods
Notes by | Jim Pelttari
Purpose of Visit | Hobo download & Site inspection
Road Condition/access | Good, 2wd
Fence Condition/needed | N/A
Veg Control Needed? | No
Animal/Pest Damage | No
Other damage (frost/human/fire | No
Label and stake condition | Good
Tree Condition | Good survival and growth, all species.
Wildlings need pulling? | No, re-assess in 2014
Comments/problems
Site Name | McLure
Date of visit | October 15th, 2014
Visitor(s) | J. Pincomb, M. Brown
Notes by | Mike Brown
Purpose of visit | HOBO download & brushing
Road condition/access | Good
Fence condition. Fence needed? | n/a
Veg control needed? Describe | Clean
Animal or pest damage | nil
Other damage (frost, human, fire) | nil
Label and stake condition | Good.
Tree condition | Good, healthy and growth
Wildlings need pulling? | done
Comments/problems | Check and PULL wildings in future visits. Work completed 2014--.5 day 2015--0
HOBO working? Repairs? | All good.
Site Visit Report
Site Name | McLure AMAT
Date of visit | 2015-10-26
Visitor(s) | Greg O and Jim Tearoe
Notes by | Greg
Road condition? Access notes updated? | very muddy and slippery last kilometer. Consider walking last km if visiting in early spring or after a rain.
Fence condition. | n/a
Vegetation - type, amount and height? Affecting seedlings? | Site was stumped prior to planting. Very little herbaceous vegetation.
Animal or pest damage? | Fresh sign of cows, but no trampling observed. Bit of deer(?) browse on Cw.
Other damage (frost, human, fire) | none
Label and stake condition | 3' PVC center stakes in place. Labels good.
Tree condition | Good survival, but slow growth. Even some Fdc, HW, Cw and Ba still alive.
Wildlings - amount, height, species? | Occaissional small pockets of residual Fd.
HOBO - Downloaded? Batteries changed? OK button flashing? | Downloaded. Changed batteries. OK button flashing.
What did you do at the site? Describe each task (e.g., pinned live seedlings, brushed, removed ingress, replaced centre stakes, measured, downloaded, etc.) and number of person-days spent on each task. | Downloaded. Inspected.
PLAN? For each task (e.g., pin live seedlings, brush, remove ingress, replace centre stakes, measure, download, etc.) describe when it should be done and how many person-days req'd for each task. | Insert PVC pins next to all short (> 40 cm) or sick test trees (1.0 pd). Brush residual Fd and herbaceous veg in 2016 (0.5-1.0 person- day). Ensure measurement sequence follows the contours on datasheet as the site is steep.
Comments/problems? | There are pink pinflags next to most test trees, but they are quickly disappearing.
Site Visit Report ver5
Site Name | McLure
Date of visit | August 7-11, 2016
Visitor(s) | R White Woods - Jeff Cooney and John Hepting
Notes by | Jeff Cooney
Road condition? Access notes updated? | road in good condition, access unchanged
Fence condition. | N/A
Vegetation - type, amount and height? Affecting seedlings? | brush, hardwood and conifer ingress, clumpy in places, ongoing
Animal or pest damage? | approx. 65 Sx and Ss with adelgid galls, three Sx with weevil
Other damage (frost, human, fire) | winter kill
Label and stake condition | Good
Tree height? Survival? | 53% survival, some Pl and Lw close to 3m tall
Wildlings - amount, height, species? | substantial snowberry; hardwood clumps and scattered conifers
HOBO - Downloaded? Batteries changed? OK button flashing? | problem with download
What did you do? | Installed PVC center posts (0.8 pd). The old, 3' PVC was very TIGHT over the majority of the posts. Attempts to bust off were slow, and messy and original metal posts would have to be removed and re-installed. RWWI decided to strap the new, 5' tall PVC to the old posts with 2 straps holding the two posts firmly together. This should last several years. We pinned/painted test trees (1 pd), measured site (5 pd), brushed & removed ingress (5 pd) attempted download
PLAN? For each task (replace centre stakes, pin live test seedlings, remove ingress, measure, brush and download). For each task, describe when it is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | This site will need brushing & download in 2018 - estimate 4 pd at that time.
Comments/problems? | could not download - two visits - two different shuttles
Site Visit Report
Site Name | McLure AMAT
Date of visit | 2016-10-13
Visitor(s) | Greg and Sarah
Notes by | Greg
Road condition? Access notes updated? | Very greasy last 2 km. Consider walking last 2 km if wet as there are few opportunities to turn around, except right at the site. Access notes updated.
Fence condition. | NA
Vegetation - type, amount and height? Affecting seedlings? | Not affecting test trees. (maybe more competition in summer than in Oct) Grasses, strawberry, rose, mullein. Saw evidence of small amount of brushing.
Animal or pest damage? | cow damage on a few trees
Other damage (frost, human, fire) | frost or sun scald on a few Fd
Label and stake condition | New Sched 40 5' PVC in place with labels zapped to stake
Tree condition | tallest Lw 190 cm; about 25% of Fdc 13 (Weyco ) alive!!
Wildlings - amount, height, species? | None seen!!!
HOBO - Downloaded? Batteries changed? OK button flashing? | hobo flashing ok. Downloaded by RWW 2 weeks ago.
What did you do at the site? Describe each task (e.g., pinned live seedlings, brushed, removed ingress, replaced centre stakes, measured, downloaded, etc.) and number of person-days spent on each task. | inspected stakes, brushing, ingress. Checked test tree heights. inspect hobo.
PLAN? For each task (e.g., pin live seedlings, brush, remove ingress, replace centre stakes, measure, download, etc.) describe when it should be done and how many person-days req'd for each task. | confirm measurements are ok; Download in 2018, brush and ingress removal in 2018 (1-2 d); measure in 2021 (3 pd).
Comments/problems? | excellent site. Easy to find; no ingress seen in 2016; very little veg comp. (in Oct).
Site Visit Report
Site Name | McLure
Date of visit | June 13th 2017
Visitor(s) | Charlotte Ballantyne and Greg O'Neill
Notes by | Greg
Road condition? Access notes updated? | Dry but rough last 2km. Too wet to turn around past the site
Fence condition. | N/A
Vegetation - type, amount and height? Affecting seedlings? | Lots of grass, rose; 20-80cm; not affecting seedlings.
Animal or pest damage? | A bit of wolley gall adelgid
Other damage (frost, human, fire) | None
Label and stake condition? 5' PVC centre stakes in place? | Excellent
Tree height? Survival? | Wide range; even some Weyco Fd alive; avg. 65% survival
Wildlings - amount, height, species? | Very small amount of Fd ingress
HOBO - Downloaded? Batteries changed? OK button flashing? | Batteries not in place on arrival. Device not found after new batteries inserted. Could not get restarted. Need to replace or re-program
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | Orientated Allan Parellson & Albert Newsbaum to the site. Attempted download. Located seedlots for CFLT tour on July 6
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Return to site to replace or reprogram logger. Approx. 4 pd brushing required in 2018 or 2019
Comments/problems? | Excellent site. Do not attempt to drive last 1.5km if it has rained in the last week
Site Visit Report
Site Name | McLure
Date of visit | June 13th 2017
Visitor(s) | Charlotte Ballantyne and Greg O'Neill
Notes by | Charlotte
Road condition? Access notes updated? | Dry but rough
Fence condition. | N/A
Vegetation - type, amount and height? Affecting seedlings? | Lots of grass, rose; 20-80cm; not affecting seedlings.
Animal or pest damage? | None seen
Other damage (frost, human, fire) | None
Label and stake condition? 5' PVC centre stakes in place? | Excellent
Tree height? Survival? | Wide range; even some Weyco Fd alive; avg. 65% survival
Wildlings - amount, height, species? | Very small amount of Fd ingress
HOBO - Downloaded? Batteries changed? OK button flashing? | Microstation reprogrammed and batteries replaced. Discovered that someone had shot the tipping bucket, so it was replaced as well.
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | Gave presentation to chief foresters. Fixed weather station.
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Bring spray paint on the next site visit to camouflage tipping bucket.
Comments/problems?
Site Name | McLure
Date of visit | Sept 12 2018
Visitor(s) | Greg O'Neill and Amy Vallarino
Notes by | Amy V
Road condition? Access notes updated? | good. On badger. 5215 road very rutted, and greasy. Drove with caution, and were ok
Fence condition. | N/a
Vegetation - type, amount and height? Affecting seedlings? | grass covered. Brush~ 40cm, rose, snowbush etc. Not affecting seedlings
Animal or pest damage? | none noted
Other damage (frost, human, fire) | none noted
Label and stake condition? 5' PVC centre stakes in place? | excellent
Tree height? Survival? | varied, 0.8-3m avg 60% survival
Wildlings - amount, height, species? | <10% fdi @ 0.4m
HOBO - Downloaded? Data examined? Batteries changed? Did you push the OK button after changing batteries? | yes, yes, yes, yes
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | downloaded weather station. Some brushing of site.
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | download weather station 1pd
Comments/problems? | weather station battery dead, so last recorded data gathered July 4th 2018
Site Name | McLure
Date of visit | May 22 2019
Visitor(s) | Marie V and Amy V
Notes by | Amy vallarino
Road condition? Access notes updated? | Good -a bit rutted. Drove right to site.
Fence condition. | NA
Vegetation - type, amount and height? Affecting seedlings? | Rose .5m
Animal or pest damage? | NA
Other damage (frost, human, fire) | NA
Label and stake condition? 5' PVC centre stakes in place? | Good
Tree height? Survival? | Pl>Py>Lw>Sx>fd ( 2m to .4m) survival @ 50%
Wildlings - amount, height, species? | minimal
HOBO - what did you OBSERVE on arrival? Which light was flashing? Any damage? Faceplate leaking? Precip bucket screen clean? Are the sensors working? | no. Possible batteries dead, questionable rain gauge.
HOBO - what did you DO? Was the data successfully downloaded? Is there data in both the temp and precip columns? Sensors or faceplate replaced? Batteries changed? Vaseline applied to faceplate? OK button pushed after changing batteries? OK light flashing on departure? | data was downloaded. Only gathered from sept to nov. The rain guage and station was replaced. - forgot cable to setup new station. - fail. Going back next week to start station.
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | download and fix station
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | go back start weather station ( 0.1pd), light brushing of site ( 0.5pd)
Comments/problems? | plan to head back the following week.
Site Name | McLure
Date of visit | May 30 2019
Visitor(s) | Amy V and Sarama K
Notes by | AmyV
Road condition? Access notes updated? | rutted
Fence condition. | NA
Vegetation - type, amount and height? Affecting seedlings? | rep 1 and 2 minor veg, Rep 3 and 4 vegetation in areas 1m tall - Saskatoom berries, willows. -yes affecting seedlings
Animal or pest damage? | n/a
Other damage (frost, human, fire) | n/a
Label and stake condition? 5' PVC centre stakes in place? | good
Tree height? Survival? | ~50%
Wildlings - amount, height, species? | none visible seen
HOBO - what did you OBSERVE on arrival? Which light was flashing? Any damage? Faceplate leaking? Precip bucket screen clean? Are the sensors working? | started new hobo logger- USB version.
HOBO - what did you DO? Was the data successfully downloaded? Is there data in both the temp and precip columns? Sensors or faceplate replaced? Batteries changed? Vaseline applied to faceplate? OK button pushed after changing batteries? OK light flashing on departure? | launched HOBO . Data was already downlaoded. Light was flashing ok, vaslined the seal.
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | launched HOBO (.1pd), brushed rep 4 (1pd)
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | I would recommend going back in 2019, if people are available, do a full clean up of reps 3 and 4. - (2.5pd)
Comments/problems? | brushing should be done by experienced personel, as the stumping has made for uneven ground.
Site Visit Report ver5
Site Name | McLure
Date of visit | October 1 2019
Visitor(s) | Rachel Reed and Mark Griffin
Notes by | Rachel
Road condition? Access notes updated? | Good, last 2km rough and slow. Even though it hadn't rained in a week or so, there was still some water pooling in areas.
Fence condition. | NA
Vegetation - type, amount and height? Affecting seedlings? | Mostly snowberry and saskatoon, some 1m tall or above
Animal or pest damage? | Evidence of western gall in Pli
Other damage (frost, human, fire) | Frost damage to Cwc
Label and stake condition? 5' PVC centre stakes in place? | Some stakes down that could be replaced.
Tree height? Survival? | Survival at around 50 percent. Pl, Py, and Lw the tallest - up to 3m
Wildlings - amount, height, species?
HOBO - what did you OBSERVE on arrival? Which light was flashing? Any damage? Faceplate leaking? Precip bucket screen clean? Are the sensors working? | Checked on HOBO - Ok light was flashing. Everything appeared in good condition and rain gauge was clean. :)
HOBO - what did you DO? Was the data successfully downloaded? Is there data in both the temp and precip columns? Sensors or faceplate replaced? Batteries changed? Vaseline applied to faceplate? OK button pushed after changing batteries? OK light flashing on departure?
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | Brushed reps 3 and 4 (2pd)
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Since there is so much brush ~0.5m tall, it would be nice to do a cleanup inbetween rows before measurement in 2021 (3.5pd)
Comments/problems?
Site Visit Report ver5
Site Name | McLure
Date of visit | September 2 2020
Visitor(s) | Sarina Meggait and Tanisha Hett
Notes by | Sarina Meggait
Road condition? Access notes updated? | Good when dry, Access notes updated
Fence condition. | NA
Vegetation - type, amount and height? Affecting seedlings? | Blackberry, snowberry, rosehip, saskatoon berry. Affecting small cedars and fdc. Blackberry max 1.5m wide by 2m tall.
Animal or pest damage? | Pest damage on one grand fir and one pine.
Other damage (frost, human, fire) | None noticed
Label and stake condition? 5' PVC centre stakes in place? | Good
Tree height? Survival? | Pine and Lard survival 85%. Grand fir 70%. Coastal species almost all dead.
Wildlings - amount, height, species? | A few Doug fir under 30cm. A few maple bushes around 2.5m wide and 2m high.
HOBO - what did you OBSERVE on arrival? Which light was flashing? Any damage? Faceplate leaking? Precip bucket screen clean? Are the sensors working? | All sensors working. Batteries were dead on arrival - only a few weeks of data from 2019 were recorded.
HOBO - what did you DO? Was the data successfully downloaded? Is there data in both the temp and precip columns? Sensors or faceplate replaced? Batteries changed? Vaseline applied to faceplate? OK button pushed after changing batteries? OK light flashing on departure? | Downloaded, changed batteries, OK button floashing when we left. Microstation is the new style.
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | 1.Downloaded & maintained weather station - 1 hr. 2.Brushed about 1/2 of the site, specifically clearing vegitation around very small seedlings - 1 person day.
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Ideally one further person day would be spent brushing around small seedlings and removing the large blackberry bushes.
Comments/problems? | 1. Blackberry bushes and rosehip make it very difficult to walk the site. 2.The vegitation on the site makes it difficult to see stumps and holes under or around stumps (there are many). The footing is tretcherous and I would suggest brush saws not be used to clear the site. 3. It is unclear if the batteries at this microstation were used up particularly quickly or if they were replaced with dead batteries by accident in 2019 or if they were not changed at all.
Site Visit Report ver5
Site Name | McLure
Date of visit | July 23-25 2021
Visitor(s) | J. Pelttari/J. Hepting - R. White Woods Inc
Notes by | J. Pelttari
Road condition? Access notes updated? | Good, 2wd access directly to site.
Fence condition. | N/A
Vegetation - type, amount and height? Affecting seedlings? | Very little hardwood ingress, lots of snowberry and prickly rose sometimes crowding smaller test trees.
Animal or pest damage? | Some hare damage and antler rub.
Other damage (frost, human, fire) | Drought on Fd and Sx
Label and stake condition | Good.
Tree height? Survival? | Pl doing best, up to 6m. Lw up to 5m, Fdi to 3.5. Bg doing well, some up to 2m. Some Cw, Cy and Ep remain.
Wildlings - amount, height, species? | Scattered small Fd ingress, a few larger ones flagged with orange.
HOBO - Downloaded? Batteries changed? OK button flashing? | New-style HOBO was not running, stopped in Sept 2020. Changed batteries and downloaded, replaced dessicants and relaunched. OK light was blinking.
What did you do at the site? Describe each task (e.g., pinned live seedlings, brushed, removed ingress, replaced centre stakes, measured, downloaded, etc.) and number of person-days spent on each task. | Measured and downloaded, 5pd
PLAN? For each task (replace centre stakes, pin live test seedlings, remove ingress, measure, brush and download). For each task, describe when it is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Site is due for brushing in 2021 but due to extremem fire hazard this will be done in the Fall.
Comments/problems? | This site is very difficult to get around in, there are large pulled up stumps and deep holes throughout.