## Site visit
Site name | Nitinat
Date planted | April 11, 12 2012
Planting Crew names | Mary Fraser, Jonah Fraser, Ben Woods, MW
Report by | Mary Fraser, Jonah Fraser, Ben Woods, MW
site coordinates NW | site perimeter was flagged by Charlie and Greg. Corners shown on cutblock map
site coordinates NE | N 48° 51’ 35.1” W 124° 45’ 14.1
Site history | logged 2010 or early 2011+B32
Native tree species (% composition) | Fdc> Hw>BA>Dr
Native non-tree species (% cover) | Rubus spectabilis, elderberry, sambuca, deerfern, swordfern, blackberry
Soil type (clayey silt, sandy loam, etc) | clayey silt deep soil about 70 cm.
Slope (%), Slope position (crest, upper, mid, lower) | 0.2
Aspect (e.g., NW) | N
Coarse fragment content (%) | 30
Stock condition | Good
Soil moisture | wet-perfect
Weather | 9-11° C
Soil condition (e.g., compacted, fluffy) | fluffy
Labels | Good
Slash | not a lot, little vegetation on site in fall of 2011
Vegetation control req'd? | Probably Spring 2013 rich site
Deer/elk/cattle control req'd? | deer and elk scat observed. This site is fenced with 2 gates.
Surrounds planted? | Yes, hemlock all the way around
Weather station installed? | Yes
Wildlings need pulling? | a few Hw
Comments/problems | uniform site; at bottom of valley, very rick. No cold air ponding. Soil slightly disturbed. The corners and perimeter were flagged and there is a draft of the site layout. Should be easy planting. There are a few hemlock to remove.
Site | Nitinat
Date | July 23 2013
Visitor(s) | R. White Woods - J. Pelttari
Notes by | J. Pelttari
Purpose of Visit | HOBO download & maintenance, site inspection
Road Condition/access | Good, 2wd
Fence Condition/needed | Good condition.
Veg Control Needed? | Yes, alder and elderberry to remove.
Animal/Pest Damage | No
Other damage (frost/human/fire | No
Label and stake condition | Good
Tree Condition | Good survival most SL's
Wildlings need pulling? | Some Hw
Comments/problems | Site will be brushed in late Nov / early Dec 2013.
Site Name | Nitinat
Date of visit | Nov 14, 2014
Visitor(s) | J. Pincomb, M. Brown
Notes by | Mike Brown
Purpose of visit | HOBO download, brushing &site inspection
Road condition/access | Good
Fence condition. Fence needed? | Good
Veg control needed? Describe | A brushing before next measurement otherwise good shape
Animal or pest damage | nil
Other damage (frost, human, fire) | nil
Label and stake condition | Good.
Tree condition | Good, healthy and growth PLI looks great
Wildlings need pulling? | done
Comments/problems | Check and PULL wildings in future visits Work completed 2014—1 day 2015—1 day
HOBO working? Repairs? | Bottom port cap missing, hobo not working but with new batteries all seemed to be good. Gate at bottom of hill close to the weather station
Site Visit Report ver5
Site Name | Nitinat
Date of visit | 3-5 Oct 2016
Visitor(s) | Greg O, Marie V, Charlie C, Keith B, Margot S
Notes by | Greg
Road condition? Access notes updated? | Excellent, yes notes updated, but next visitor needs to figure out which of the two sets (old or new) is better and revise again.
Fence condition. | Intact, but sign of elk scat throughout and about 20 damaged trees.
Vegetation - type, amount and height? Affecting seedlings? | Dr up to 5 m tall >rose, blackberry, fireweed, bracken, swordfern, salmon berry, huckleberry. Definitely affecting growth.
Animal or pest damage? | Elk on about 20 Py and Pl
Other damage (frost, human, fire) | no
Label and stake condition? 5' PVC centre stakes in place? | 3' Sch 40 in place when we arrived; labels fine.
Tree height? Survival? | tallest Fd and Pl about 370 cm; overall survival about 85%
Wildlings - amount, height, species? | LOTS of Hw and alder. Lesser amounts of Fd, Cw, Pw. Needs to be removed soon.
HOBO - Downloaded? Batteries changed? OK button flashing? | Not flashing on arrival. Download took 30 s instead of usual 2 s; batteries replaced; flashing on departure. Next crew: Please check to make sure HOBO is working. Check that sensors are reading correctly and light is flashing. If not, change sensors.
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | 1) attached 5' PVC sched 40 onto 3' PVC using zaps on about half of the plots; the other half we replaced the 3' with 5' PVC, placing 5' over the Aluminum stakes (1.5 pd); 2) Painted and ribboned ALL test trees, except Py and Pl which received only ribbon (6 pd); 3) measured height except for rows 19 and 20, and top 12 plots 3 pd); 4) GPS fence corners; brushed a few plots in NE corner; taught Keith download (0.5 pd).
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Finish measurements (1 pd); brush (4 pd if done in 2016) - there is a lot of brush but should be relatively easy with all the trees ribboned and painted.
Comments/problems? | There is 1 PVC stake inside the gate. It needs to go on a plot near the centre of the site. Long drive from Cowichan. Consider Nitinat Motel (if it has kitchens) as it is very close, or enquire with Bamfield marine station (slightly closer than Cowichan).
Site Visit Report ver5
Site Name | Nitinat
Date of visit | March 24-26,2017 and return April 11 to power up HOBO
Visitor(s) | J. Pelttari/J. Hepting - R. White Woods Inc.
Notes by | J. Pelttari
Road condition? Access notes updated? | Good 2wd access directly to site, long drive from Port Alberni or Lake Cowichan.
Fence condition. | Fence is intact but there is evidence Elk may have jumped it.
Vegetation - type, amount and height? Affecting seedlings? | Main shrub species is Salmonberry, very thick in places, cut back when encroaching on smaller test trees. Lots of alder re-sprout from previous brushing.
Animal or pest damage? | Some Elk damage on a few Pl.
Other damage (frost, human, fire) | No
Label and stake condition | Good.
Tree height? Survival? | Fdc and Pli doing the best, some over 3m. Ss, Cw, Cy, Lw, Pw, Hw and Fdi all doing fine. Moderate survival of Bl and Ba but not doing very well.
Wildlings - amount, height, species? | Patchy, mostly Hw and some Cw. Many Hw germinants coming in in some places
HOBO - Downloaded? Batteries changed? OK button flashing? | HOBO was not running, it failed on Jan 25 2017. Replaced batteries, downloaded and restarted. Dessicant packs were damp to the touch and there was condensation inside the HOBO.
What did you do at the site? Describe each task (e.g., pinned live seedlings, brushed, removed ingress, replaced centre stakes, measured, downloaded, etc.) and number of person-days spent on each task. | Measured remaining 450 trees (1 pd). Removed Alder, cut back Salmonberry and Elderberry encroaching on smaller trees and removed conifer ingress, mostly Hw with some Cw and Fd. Restarted HOBO. Brushed trail to gate (6 pd).
PLAN? For each task (replace centre stakes, pin live test seedlings, remove ingress, measure, brush and download). For each task, describe when it is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Batteries should last until 2019 but this is a very wet site so maybe a good idea to check the HOBO in 2018. Recommend brushing and conifer ingress removal in 2019. (4-6 pd)
Comments/problems?
Site Visit Report ver5
Site Name | Nitinat AMAT
Date of visit | 2018-12-30
Visitor(s) | Jake King, Karly Oliver
Notes by | Jake King
Road condition? Access notes updated? | A very long and bumpy 1.5 hours from Port Alberni, radio frequencies needed. Access notes are fine
Fence condition. | Surprisingly good after the storm.
Vegetation - type, amount and height? Affecting seedlings? | Very thick and deep salmonberry at this site, still affecting the smaller trees.
Animal or pest damage? | A few PW affected by blister rust, a couple FD looked chlorotic.
Other damage (frost, human, fire) | None
Label and stake condition? 5' PVC centre stakes in place? | Mostly good, a few knocked over.
Tree height? Survival? | 3 metres, fair to middling
Wildlings - amount, height, species? | Lots of small Hw and some Cw coming in as well as some hardwoods resprouting.
HOBO - Downloaded? Batteries changed? OK button flashing? | Downloaded, batteries changed, Ok flashing. The HOBO was dead when we arrived?? It did fire up and sensors read normal when I tried it, so it was left as is. It had been dead since July 5 2017, so possibly bad batteries to blame.
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | Download and assessment.
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Keep an eye on the HOBO. Brushing at this site will be an ongoing and expensive indeavour.
Comments/problems?
HOBO Location | Rep 3 49 YC
Site Visit Report ver5
Site Name | Nitinat
Date of visit | Nov 11-13 2019
Visitor(s) | J. Pelttari / J. Hepting - R. White Woods
Notes by | J. Pelttari
Road condition? Access notes updated? | Good, 2wd access to site, long drive.
Fence condition. | Mostly intact,tree down across fence at back of site.
Vegetation - type, amount and height? Affecting seedlings? | Salmonberry, huckleberry and elderberry up to 2m tall encroaching on some test trees. Lots of multi-stem re-sprout from previously cut Alder.
Animal or pest damage? | Elk damage on a few Pl, some Adelgid on Sx, Ss. Some blister rust in Pw.
Other damage (frost, human, fire) | No
Label and stake condition | Good
Tree height? Survival? | Generally good survival, Fdc and Pl over 5m.
Wildlings - amount, height, species? | Lots of new Hw and some Cw coming and resprout of some previously cut ingress, mostly under 1m.
HOBO - Downloaded? Batteries changed? OK button flashing? | HOBO was not running, again. There is no damage to the station or to the faceplate, all of the sensors appear working. Replaced batteries and restarted. This is a very wet site, could possibly require download at six month intervals to get continuous data.
What did you do at the site? Describe each task (e.g., pinned live seedlings, brushed, removed ingress, replaced centre stakes, measured, downloaded, etc.) and number of person-days spent on each task. | Downloaded, removed conifer ingress, brushed hardwoods and trail from road to gate. (6 pd)
PLAN? For each task (replace centre stakes, pin live test seedlings, remove ingress, measure, brush and download). For each task, describe when it is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | The site is listed as 'maybe' for Pruning in 2021, this should be done in Pl and Fd plots and maybe some others. Est 6 pd.
Comments/problems?
Site Visit Report ver5
Site Name | Nitinat
Date of visit | Oct 17-19 2021
Visitor(s) | J. Pelttari/J. Hepting - R. White Woods Inc
Notes by | J. Pelttari
Road condition? Access notes updated? | Good, 2wd access directly to site. Long drive from Lake Cowichan.
Fence condition. | Good.
Vegetation - type, amount and height? Affecting seedlings? | Salmonberry thick in places, Elderberry, Huckleberry, Alder resprouting from last brushing.
Animal or pest damage? | Extensive damage in Pl and Py from Dothistroma. Most Pw affected by WPBR, some killed. Rhabdocline affecting many Fd but not severely. Lw needlecast present. Heavy spruce gall in Ss plots.
Other damage (frost, human, fire) | No
Label and stake condition | Good.
Tree height? Survival? | Good survival of most SLs. A few Hw over 8m, Fdc to 7m, Pl and Cw to 6m. Lw doing the worst, maybe 10% survival.
Wildlings - amount, height, species? | Hw and Cw coming in, most <1 m, a few missd Hw >3m.
HOBO - Downloaded? Batteries changed? OK button flashing? | Yes. HOBO was not running, only ran for one month after servicing in 2020. Changed batteries and dessicants, restarted, OK light flashing.
What did you do at the site? Describe each task (e.g., pinned live seedlings, brushed, removed ingress, replaced centre stakes, measured, downloaded, etc.) and number of person-days spent on each task. | Measured site and downloaded HOBO, 6 pds
PLAN? For each task (replace centre stakes, pin live test seedlings, remove ingress, measure, brush and download). For each task, describe when it is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Site should be brushed in 2023. Est. 7-8 pds
Comments/problems?
Site Visit Report ver6
Site Name | Nitinat
Date of visit | 2021-12-16
Visitor(s) | Andrew Coster, Jake King
Notes by | Jake
Road condition? Access notes updated? | Notes and road in decent condition ~2 hours from CLRS, georeferenced map built
Fence condition. | Good
Vegetation - type, amount and height? Affecting seedlings? | Thick salmonberry to 2m, not affecting trees
Animal or pest damage? | Fence holding, blister rust on Pw, cankers on Pl
Other damage (frost, human, fire) | na
Label and stake condition? 5' PVC centre stakes in place? | good
Tree height? Survival? | variable 1.5 m to 8m
Wildlings - amount, height, species? | Hw and a few hardwoods. Moderate
HOBO - what did you OBSERVE on arrival? Which light was flashing? Any damage? Faceplate leaking? Precip bucket screen clean? Are the sensors working? What type of microstation is in place? | No lights, appears out of batteries or? Older unit
HOBO - what did you DO? Was the data successfully downloaded? Is there data in both the temp and precip columns? Sensors or faceplate replaced? Batteries changed? Vaseline applied to faceplate? OK button pushed after changing batteries? OK light flashing on departure? | Just observed
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | Fence and access check
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Recommend brushing within 3 years for hw and hardwoods ~5k, fence removal in 2022-2024 ~10k
Comments/problems? | Hobo inoperable