## Recon_Establishment
AMAT test site recon/establishment report
Site name | PGTIS
Date planted | June 1-2, 2011
Planting Crew names | Future Forest Crew Mary Jonah Ben Kent Hannah
Report by | Michael Carlson
Establishment report: Mary Fraser Future Forests
Site history | Pine research plantation Removed 2008
Native tree species (% composition) | Pli Aspen
Native non-tree species (% cover) | Grass
Soil type (clayey silt, sandy loam, etc) | Sandy loam, well drained
Slope (%), Slope position (crest, upper, mid, lower) | flat
Aspect (e.g., NW) | Flat
Coarse fragment content (%) | 2%
Dimensions of Site | 100 x 200
Stock condition | Wet
Soil moisture | Damp
Weather | 19° C and buggy
Soil condition (e.g., compacted, fluffy) | Should be fluffy once it is disked. Sandy, gravel
Labels | Good
Slash | none
Vegetation control req'd? | Site needs to be herbicided in Spring 2011, double disked Spring 2011, then laid out and planted
Deer/elk/cattle control req'd?
Surrounds planted? | Yes
Weather station installed? | Yes
Wildlings need pulling? | no wildlings but will require grass competition to be held in check.
Comments/problems | Grass will likely have to be spot-sprayed again in 2012 growing season

## Site visit
Site name | PGTIS
Date planted | June 1-2, 2011
Planting Crew names | Mary Fraser, Kent, Ben, Jonah, Hanna
Report by | Michael Carlson (initial) Mary Fraser Establishment report
Site history | Pine research plantation Removed 2008
Native tree species (% composition) | Pli Aspen
Native non-tree species (% cover) | Grass
Soil type (clayey silt, sandy loam, etc) | sandy loam well drained
Slope (%), Slope position (crest, upper, mid, lower) | flat
Aspect (e.g., NW) | flat
Coarse fragment content (%) | 2%
Dimensions of Site | 100 x 200
Stock condition | wet
Soil moisture | damp
Weather | hot and buggy 19° C
Soil condition (e.g., compacted, fluffy) | MF: sandy gravel
Labels | all good
Slash | none
Vegetation control req'd? | Sitewas herbicided in Spring 2011, double disked Spring 2011, then laid out and planted
Deer/elk/cattle control req'd?
Surrounds planted? | Yes
Weather station installed? | Yes
Wildlings need pulling? | no wildlings but will require grass competition to be held in check.
Comments/problems | Grass will likely need to spot sprayed in 2012
Site | PGTIS Prince George
Date | Oct. 23, 2012
Visitor(s) | J. Cooney & D. Gustafson of R.White Woods
Notes by | J. Cooney & D. Gustafson of R.White Woods
Purpose of visit | HOBO download and site maintenance
Road condition/access | Good
Fence condition. Fence needed? | N/A
Veg control needed? Describe. | No
Animal or pest damage | No
Other damage (frost, human, fire) | No
Label and stake condition | Good
Tree condition | Poor
Wildlings need pulling? | No
Comments/problems | Grass competition killed many trees
HOBO working? Repairs
Site | Prince George Tree Improvement Station
Date | 2013-09-06
Visitor(s) | J. Cooney, D. Gustafson
Notes by | J. Cooney
Purpose of Visit | HOBO Download
Road Condition/access | good
Fence Condition/needed | N/A
Veg Control Needed? | no some veg management done by the PGTIS staff 2013
Animal/Pest Damage | no
Other damage (frost/human/fire) | no
Label and stake condition | tags showing wear from wind
Tree Condition | poor
Wildlings need pulling? | no
Comments/problems | yes, rain bucket plugged
Site Name | PGTIS
Date of visit | October 22th, 2014
Visitor(s) | D Davis, M. Brown
Notes by | Mike Brown
Purpose of visit | HOBO download & maintenance
Road condition/access | Good
Fence condition. Fence needed? | n/a
Veg control needed? Describe | Clean
Animal or pest damage | nil
Other damage (frost, human, fire) | nil
Label and stake condition | Found or replaced missing labels.----4 hrs
Tree condition | Good, healthy and growth
Wildlings need pulling? | Not needed—good job by station staff
Comments/problems | Tags could be a future problem because o wind. Work completed 2014--.5 days 2015--0
HOBO working? Repairs? | All good.
Site Visit Report ver5
Site Name | Prince George Tree Improvement Station AMAT test
Date of visit | 2017-03-01
Visitor(s) | Bonnie Hooge
Notes by | Bonnie Hooge
Road condition? Access notes updated? | Site is within PGTIS compound so is 2WDrivable
Fence condition. | No fence
Vegetation - type, amount and height? Affecting seedlings? | The vegetation is mainly grass and is not competing with the surviving seedlings/trees
Animal or pest damage? | None
Other damage (frost, human, fire) | None
Label and stake condition? 5' PVC centre stakes in place? | Site is labeled with PVC stakes
Tree height? Survival? | Height varies between 20-120 cm depending on species. Most coastal species are not alive.
Wildlings - amount, height, species? | No wildlings
HOBO - Downloaded? Batteries changed? OK button flashing? | I believe Vanessa's student downloaded it in 2016
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | Bonnie measured it in 2015. Took most of a week for one person.
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Bonnie will flag short trees and download.
Comments/problems?
Site Visit Report ver5
Site Name | PGTIS
Date of visit | June 9/10 2020
Visitor(s) | Rachel Reed, Jarrett Columbus, Tiffany Farwick
Notes by | Rachel Reed
Road condition? Access notes updated? | Excellent - 2WD access right to site
Fence condition. | Good.
Vegetation - type, amount and height? Affecting seedlings? | Negligble, a few Pl and low rose bushes. Nothing affecting seedlings.
Animal or pest damage? | Nothing major.
Other damage (frost, human, fire) | Drought and snow press damage in Sx, some weevil in Sx.
Label and stake condition? 5' PVC centre stakes in place? | Labels on hanging tabs, should be replaced next visit to screwed in labels. Some were missing or on the ground and were secured back on the post with zip ties.
Tree height? Survival? | 20-30 percent survival. Pli over 5m in areas, Py 3m, Sx 1-2m.
Wildlings - amount, height, species? | A few stray Pli
HOBO - what did you OBSERVE on arrival? Which light was flashing? Any damage? Faceplate leaking? Precip bucket screen clean? Are the sensors working? | HOBO light was flashing, all sensors intact. No leaking.
HOBO - what did you DO? Was the data successfully downloaded? Is there data in both the temp and precip columns? Sensors or faceplate replaced? Batteries changed? Vaseline applied to faceplate? OK button pushed after changing batteries? OK light flashing on departure? | Downloaded and relaunched the station. Replaced batteries and desiccants, all sensors were operational.
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | Measured tree heights (4pd), downloaded wx station (0.1pd), removed some ingress (0.5pd), replaced a few tags (0.2pd).
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | This site should not need brushing for 2-3 years, and will not require measurement for another 5 years. Should be downloaded in 2021
Comments/problems? | During our two days at PGTIS, we encountered 6 adult black bears and 5 cubs, most of which were on the site, and a few on surrounding logging roads.