## recon_establishment
AMAT test site recon_establishment report
Site name | Spillimacheen Driftwood
Date planted | May 2009
Planting Crew names | MF, JF, VB, MC, NU
Report by | Greg O
Site history | Logged 2008
Native tree species (% composition) | Pli and Dfi
Native non-tree species (% cover)
Soil type (clayey silt, sandy loam, etc)
Slope (%), Slope position (crest, upper, mid, lower) | 0%, flat
Aspect (e.g., NW) | flat
Coarse fragment content
Stock condition | good
Soil moisture
Weather
Soil condition (e.g., compacted, fluffy)
Labels
Slash
Vegetation control req'd?
Deer/elk/cattle control req'd? | fence needed
Surrounds planted? | yes
Weather station installed? | no
Wildlings need pulling?
Comments/problems

## site visit
Site visit report
Site | Spillimacheen Driftwood
Date | 2010-10-15
Visitor(s) | Mike, Ryan, LiLi, Jeremy
Notes by | Mike Brown
Purpose of visit | download Hobo weatherstation data
Road condition/access | good
Fence condition. Fence needed? | no
Veg control needed? Describe. | no
Animal or pest damage | no
Other damage (frost, human, fire) | lots of frost damage, frost pockets
Label and stake condition | good
Tree condition | poor
Wildlings need pulling? | no
Comments/problems | anything planted in a depression is now dead. Mixture of fir and spruce surviving in high areas. ~ 300 surviving seedlings mostly Fdi
Site | Spillimacheen Driftwood
Date | 2011-07-05
Visitor(s) | Vicky & Nick
Notes by | Vicky & Nick
Purpose of visit | check site for survival on way to EK Pli sites
Road condition/access | good
Fence condition. Fence needed? | No
Veg control needed? Describe. | Some aspen ingress should be removed
Animal or pest damage? Type of control needed. | No
Other damage (frost, human, fire) | Frost pockets... Same as MB's notes above
Label and stake condition | good
Tree condition | Poor
Wildlings need pulling? | Yes, Pli needs removing . Many plots with no trees.
Comments/problems | Some good plots of Sx, Fdi and Pli
>50% mortality overall
Site | Spillimacheen Driftwood
Date | October 5, 2011 J. Pelttari, J. Hepting - R. White woods
Visitor(s) | J. Pelttari, J. Hepting - R. White woods
Notes by | J. Pelttari
Purpose of visit | Hobo download, site inspection, maintenance
Road condition/access | Good
Fence condition. Fence needed? | n/a
Veg control needed? Describe. | removed extensive At ingress
Animal or pest damage? Type of control needed. | No
Other damage (frost, human, fire) | some frost
Label and stake condition | good
Tree condition | poor
Wildlings need pulling? | remove Pl ingress in treed plots
Comments/problems
Site | Spillimacheen Driftwood
Date | 2012 fall
Visitor(s) | R. WhiteWoods crew
Notes by | J. Pelttari
Purpose of visit | HOBO download, maintenance/ site inspection
Road condition/access | Good 2 WD
Fence condition. Fence needed? | N/A
Veg control needed? Describe. | Brushed in 2011, Aspen resprouting, reassess in 2013
Animal or pest damage? Type of control needed. | some browse
Other damage (frost, human, fire) | no
Label and stake condition | Good 2 WD
Tree condition | fairly good survival
Wildlings need pulling? | some Pli germinants, re-assess in 2013
Comments/problems
HOBO working? Repair? | working/ok
Site | Driftwood
Date | 2013-03-09
Visitor(s) | R. White Woods (J. Pelttari, J. Hepting)
Notes by | J. Pelttari
Purpose of Visit | HOBO download, site inspection, measurement, brushing.
Road Condition/access | Good, 2wd
Fence Condition/needed | N/A
Veg Control Needed? | Hardwoods & competing shrubs removed in 2013
Animal/Pest Damage | Some browse, some root disease in Pl
Other damage (frost/human/fire | Some frost
Label and stake condition | Good
Tree Condition | Good survival of Pl, others poor, coastal dead.
Wildlings need pulling? | All conifer ingress removed in 2013.
Comments/problems
Note: Plots with heavy Pl ingress were plots where all
test trees had died. Pl was left in those plots as per our
understanding of the requirements, taking into consideration
conversation with M. Carlson re: NSF. Those plots are now clean.
JP
Interesting to note effect of deactivated road on tree growth
where a plot straddles the road. See photos.
Site | Spillimacheen Driftwood
Date | 2013-06-14
Visitor(s) | Greg
Notes by | Greg
Purpose of visit | Assess contractor performance; site assessment
Road condition/access | Excellent 2 WD access
Fence condition. Fence needed? | not required. Few old cow turds
Veg control needed? Describe. | none
Animal or pest damage? Type of control needed. | about 15% of the Pli killed in last 12 months. 100 of needles red; tree easily pulled from ground; few white hyphae on roots; 3-5 yellow 3-cm fungal lesions on stem at base of each dead tree. Diagnosis - Armalleria? Commandra?
Other damage (frost, human, fire) | none
Label and stake condition | good
Tree condition | Estimated survival: Sx 15%; Pw 5%; Lw 5%; Aspen 10%; Fdi 5% (despite this being an IDF site!!); Pli 80%.
Wildlings need pulling? | YES!!!! Immediately! This site is full of Pli ingress which must be removed. Be careful not to remove our planted Pl. Suggest running rows of pin flags to assist with locating seedlings.
Comments/problems
Site Name | Spillimacheen Driftwood
Date of visit | October 23th, 2014
Visitor(s) | D. Evans E. van Eeden & M. Brown
Notes by | Mike Brown
Purpose of visit | HOBO download & brushing
Road condition/access | good
Fence condition. Fence needed? | n/a
Veg control needed? Describe | Hardwoods and competing brush removed.
Animal or pest damage | nil
Other damage (frost, human, fire) | nil
Label and stake condition | Good.
Tree condition | Pl and the odd sx survival ---very dry harsh site
Wildlings need pulling? | Constant problem
Comments/problems | Surviving trees painted with last measurement---good idea. Work completed 2014--.5 day 2015--.5 day
HOBO working? Repairs? | All good.
Site Visit Report ver5
Site Name | Spillimacheen/Driftwood
Date of visit | October 11-14, 2016
Visitor(s) | R White Woods - Jeff Cooney and Darren Gustafson
Notes by | Jeff Cooney
Road condition? Access notes updated? | road in good condition, access unchanged
Fence condition. | N/A
Vegetation - type, amount and height? Affecting seedlings? | conifer and hardwood ingress
Animal or pest damage? | none apparent
Other damage (frost, human, fire) | winter
Label and stake condition | Good, PVC center posts installed
Tree height? Survival? | trees 30 cm to 3 m
Wildlings - amount, height, species? | mostly Pl - all removed
HOBO - Downloaded? Batteries changed? OK button flashing? | Yes to all.
What did you do at the site? Describe each task (e.g., pinned live seedlings, brushed, removed ingress, replaced centre stakes, measured, downloaded, etc.) and number of person-days spent on each task. | Installed PVC center posts (1 pd), painted/pinned trees (1.5 pd), brushed & removed ingress + download (5 pd), travel (2 pd)
PLAN? For each task (replace centre stakes, pin live test seedlings, remove ingress, measure, brush and download). For each task, describe when it is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Scheduled for measurement in 2018 (4-6 pd). Download and battery change could be OK until then. Brush and ingress could be done again then. Estimate 2-4 pd brushing.
Comments/problems?
Site Visit Report ver5
Site Name | Spillimacheen
Date of visit | July 2 & 4 2018
Visitor(s) | J. Pelttari/J. Hepting - R. White Woods
Notes by | J. Pelttari
Road condition? Access notes updated? | Good, 2wd access to site.
Fence condition. | N/A
Vegetation - type, amount and height? Affecting seedlings? | Very little, some aspen resprout and scattered small willow.
Animal or pest damage? | Some browse.
Other damage (frost, human, fire) | Heavy new mortality of Sx, possible frost.
Label and stake condition? 5' PVC centre stakes in place? | Good
Tree height? Survival? | Poor survival lots of new mortality, mostly Sx but also Pl with root disease. Some Pl up to 4m.
Wildlings - amount, height, species? | Scattered Pl ingress, mostly resprout from previously cut trees.
HOBO - Downloaded? Batteries changed? OK light flashing? | Yes, all good.
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | Measured surviving test trees, brushed site, downloaded Hobo and changed batteries.
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | This site will not require brushing for a few years. Download in 2019 or 2020.
Comments/problems?
Site Visit Report ver5
Site Name | Spillimacheen
Date of visit | Sept 30 2020
Visitor(s) | J. Pelttari/J;Hepting - R White Woods
Notes by | J. Pelttari
Road condition? Access notes updated? | Good, 2 wd access directly to site, no changes.
Fence condition. | N/A
Vegetation - type, amount and height? Affecting seedlings? | Minimal
Animal or pest damage? | Root disease on Pl.
Other damage (frost, human, fire) | Frost damage on Sx and Lw
Label and stake condition | Good
Tree height? Survival? | Very harsh site, only Pl and a few Lw doing marginally well, only a few Pl over 4m.
Wildlings - amount, height, species? | Very few. Pl ingress and resprout greatly reduced. Aspen resprout light.
HOBO - Downloaded? Batteries changed? OK button flashing? | Yes to all. In looking at the data the Rain guage readings were -888.88 from 10/07/19 to 30/09/202. Replaced Rain bucket. Note: dtf file name Replacement_1
What did you do at the site? Describe each task (e.g., pinned live seedlings, brushed, removed ingress, replaced centre stakes, measured, downloaded, etc.) and number of person-days spent on each task. | Downloaded HOBO, replaced Rain bucket.
PLAN? For each task (replace centre stakes, pin live test seedlings, remove ingress, measure, brush and download). For each task, describe when it is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Site will not require maintenance until 2022 - download and light brushing.
Comments/problems?