## Harrison
DATE | NOTES | AUTHOR
Spring 2005 | Site planted by Practical Tree Improvement Research Services Ltd. | Val Ashley
2007-07-13 | Site visit by Greg O’Neill. Access 4wd, could use 2wd, but need to walk last 1.5 km. Brushsaw damage to ~1% of trees. No other damage or disease noted. Stakes & labels in good condition. Site looks very good. | Notes by Greg O’Neill
Entered by Val Ashley
DATE | NOTES | AUTHOR
Nov. 20, 2012 2011 | HOBO download, re-launch and site inspection. Access road good but the last kilometer is rough. No damage, animal or climate related. Site was brushed in summer 2012. Stakes and labels in good condition. Very good survival and growth. | Notes taken by J. Pelttari of R. WhiteWoods Inc.
2013-10-10 | Hobo download & maintenance, site inspection. Road condition good 2wd access, but hike in last 400 m. No brushing needed. Stakes & labels OK, some pvc stakes seem out of place? Very good survival and growth. | Notes by J. Pelttari of R. White Woods Inc.
Date | Oct 10 2013
Visitor(s) | R. White Woods - J. Pelttari / J. Hepting
Notes by | J. Pelttari
Purpose of Visit | HOBO download & maintenance, site inspection.
Road Condition/access | Good 2wd access but hike in last 400 meters.
Fence Condition/needed | N/A
Veg Control Needed? | No, brushed in 2012.
Animal/Pest Damage | No
Other damage (frost/human/fire | No
Label and stake condition | OK, some pvc stakes seem to be out of place.
Tree Condition | Very good survival and growth.
Wildlings need pulling? | No
Comments/problems
Site Visit Report ver5
Site Name | Harrison Sx
Date of visit | 2017-11-03
Visitor(s) | Greg ONeill and Dave Kolotelo
Notes by | Greg
Road condition? Access notes updated? | FSR excellent until spur road which is overgrown w alder
Fence condition. | NA
Vegetation - type, amount and height? Affecting seedlings? | bracken up to 3 m! but not affecting trees
Animal or pest damage? | none seen. About 3% of trees affected by weevil
Other damage (frost, human, fire) | 1 dead 12 y-o tree. Uncertain agent
Label and stake condition? 5' PVC centre stakes in place? | 20% of stakes have fallen over. Stakes appear to be new: 5' PVC on rebar. Labels well screwed to stakes
Tree height? Survival? | range 1-6 m; mean = 4 m. Survival about 95%
Wildlings - amount, height, species? | Hw and Mb - rare
HOBO - Downloaded? Data examined? Batteries changed? Did you push the OK button after changing batteries? | not flashing on arrival. Changed batteries and downloaded OK, but temp sensor upside down. Changed faceplate. Pellet gun holes on shield and tipping bucket. :(
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | Inspected thinning and brushing. Both good. All cut stems were on the ground. Easy walking. Downloaded.
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | 1. Repair or replace weather station, as needed. 2) Remove 5 m tall Cy near Weather Station.
Comments/problems? | Bring ladder for weather station. Weather station is at Rep 4, Block 13
Site Name | Harrison Sx
Date of visit | Sept 7 2018
Visitor(s) | jarrett Columbus and amy Vallarino
Notes by | Amy Vallarino
Road condition? Access notes updated? | good, Aldered in road for last 1km
Fence condition. | n/a
Vegetation - type, amount and height? Affecting seedlings? | Salmon and thimble berry, 2m tall, bracket fern 3 m tall (see pic)
Animal or pest damage? | n/a, minor weaval
Other damage (frost, human, fire) | Human damage to labels close to road, minor.
Label and stake condition? 5' PVC centre stakes in place? | poor near road side. (consider replacing the first row near road) PVC yes.
Tree height? Survival? | 5 to 7m, 95%survival
Wildlings - amount, height, species? | none noted.
HOBO - Downloaded? Data examined? Batteries changed? Did you push the OK button after changing batteries? | No, Yes, yes
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | replaced weather station
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | download weather station (1pd) measure trees 2019- 4pd?
Comments/problems? | n/a
Site Name | Harrison Sx
Date of visit | August 9-14, 2020
Visitor(s) | Sarina Meggait, Greg O'Neill, Rachel Reed, 4 UBC students
Notes by | Greg and Sarina
Road condition? Access notes updated? | Good. Last 300m deactivated - must walk in.
Fence condition. | n/a
Vegetation - type, amount and height? Affecting seedlings? | 4m bracken fern, raspberry, salal. Very dense. Yes affecting shortest 5% of the test trees.
Animal or pest damage? | Weevil in roughly 15% of the trees.
Other damage (frost, human, fire) | A few of the test trees inadvertently thinned.
Label and stake condition? 5' PVC centre stakes in place? | Yes the 5' PVC stakes were in place. About half of the stakes were found fallen over and their correct position was uncertain.
Tree height? Survival? | 50 - 900 cm; average 550 cm
Wildlings - amount, height, species? | 1 wildling per 2 test trees. Dr, Hw, Mv, Ep, Hw - Average 200 cm
HOBO - Downloaded? Data examined? Batteries changed? Did you push the OK button after changing batteries? | Microstation is the old style. Yes, Yes, Yes. Batteries dead on arrival. Precipitation gauge was not recording data for the past two years.
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | Brushed - 20pd. Ribboned every 8th row and column - 6pd. Downloaded. Measured - 2pd.
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | Finish measuring ASAP - 12pd. Check the map (see comments below). Label trees - 2pd as current labels are too few.
Comments/problems? | 1. Confirm that the map matches the datasheet by comparing the layout map with tree label seedlot #s. Also check the location of Ss, Fort Simpson, and AZ/NM SLs on site match the layout map. In future contracts request limbing of thinned trees. 2. Aluminum tree labels with row and column and SL were very helpful and 99% appear to be correct. 3. Column 43 is 9999 except for the Northern most few plots, however column 42 and 44 converge toward the south so there are 58 columns at the south end and 59 at the north end. 4. Mapping error in rows 40 and 38 between columns 4 and 7. See updated map. Data sheets are correct - NOTE a map was found that appears to have this problem fixed. 5. Consider herbicide. 6. Add more row and column tree labels. 7. Inquire about landscape genomics to confirm mapping ID. 8. PVC stake locations are questionable. 9. Weeds will continue to be an issue for trees under 3m.
Site Name | Harrison Sx
Date of visit | August 24-26 2020
Visitor(s) | Sarina Meggait, Lindsay Bellingham, Theresa Coles, Taylor Holt
Notes by | Sarina Meggait
Road condition? Access notes updated? | Good until last 300m. No new access notes.
Fence condition. | n/a
Vegetation - type, amount and height? Affecting seedlings? | Recently brushed.
Animal or pest damage? | Weevil - see previous report.
Other damage (frost, human, fire) | See last report.
Label and stake condition? 5' PVC centre stakes in place? | See last report.
Tree height? Survival? | See last report.
Wildlings - amount, height, species? | See last report.
HOBO - Downloaded? Data examined? Batteries changed? Did you push the OK button after changing batteries? | See last report.
What did you do at the site? Describe each task (e.g., replaced centre stakes, pinned live seedlings, brushed, removed ingress, measured, downloaded) and number of person-days spent on each task. | Measured height with hypsometers, DBH with DBH tape, and weevil attack presence in the last 5 years for each tree (1 or 0). 10pd
PLAN? Describe when each task is needed and number of person-days req'd. (e.g., Brush 2019, 3 pd) | I suggest all or some of the remaining trees be tagged with tags including column, row, seedlot and position number. Roughly 8pd.
Comments/problems? | * Some thinning mistakes found. It would be difficult to navigate if not ribboned off and column ends flagged (see previous report).