## MR24
Release 26 OFM Implementation Checklist
Row | Target Date | Area | Task | Owner | Status | Date | Comments
0 | March-1-13 | Action | Create Release Implementation Checklist | Troy R | Done | 2015-06-01 | Troy to update List
1 | March-1-13 | Action | New Data Model change document received from BPM? | Al P | N/A |  | N/A Code only
2 | March-15-13 | IMB | Verify that data conversion/code table update scripts are ready for submission | Al P | N/A
3 | 2015-06-01 | Communication | Send to BPM, BBS a draft of Release 26 Summary of Functionality for approval | Troy | N/A |  | Infrastructure Update
4 | 2015-06-01 | Action | Release 26 Summary of Functionality approved and received? | Rick / Troy | N/A |  | Infrastructure Update
5 | 2015-06-01 | Communication | Send Summary of Functionality to APPHELP, HBS users | Tim/Crystal | N/A |  | Infrastructure Update
6 | 2015-06-01 | Action | Confirm production environment dependencies | Al P/Troy | Done | 2015-06-03 | Prod Candidate
7 | 2015-06-01 | Action | Release 26 Go-No-Go decision meeting at HMAC; confirm readiness and identify date for migration | Al P/Troy/Anne |  |  | Prod Candidate
8 | 2015-06-01 | Communication | Send proposed migration date to CGI | Al P |  |  | Prod Candidate
9 | 2015-06-01 | Communication | First HBS tentative unavailability notification to users with preliminary dates/times and summary | Tim/Crystal | Done |  | Prod Candidate
10 | 2015-06-01 | Testing | Begin Regression Testing of Prod candidate Last Release of Test SW | UAT Team / Billing Team | Done | 2015-05-01 | Prod Candidate
11 | 2015-06-01 | Communication | Apply for Change Management and secure a CM# | Al P | N/A
12 | 2015-06-01 | Communication | Send Change Management number to Sierra | Al P | N/A
13 | 2015-06-01 | Sierra | Submit Migration Request to IMB |  | N/A |  | IMB will drive migration dates
14 | 2015-06-01 | Action | Approval of Migration Request from Change Management | Al P | N/A
15 | 2015-06-01 | Documentation | CGI to provide test deliverables (i.e., test plan, results, scripts, screen shots, etc.) | CGI | Done | 2015-06-01 | CGI sent their high level test plan and reggression log results
16 | 2015-06-01 | Action | Send Approval of Migration Request from Application Custodian to IMB NOTE: Include notice to leave Listener off until further notice | Troy / Anne | N/A |  | no longer do you need to ‘approve’ the migrations.
17 | 2015-06-09 | Action | Final Release Implementation Go-No-Go decision meeting at HMAC; confirm readiness and identify last minute issues for migration | AL/Troy/Tim/Crystal |  |  | Prod Candidate
18 | 2015-06-09 | Communication | Second HBS unavailability notification to users with finalized dates/times and summary - After the Go/No Go meeting | Tim/Crystal |  |  | Prod Candidate
19 | 2015-06-09 | Action | Add 1 line Text Banner to HBS Prod page advising of service outage | Tim/Crystal | Done | 2015-06-01 | Prod Candidate
20 | 2015-06-01 | Testing | Regression Testing Maintenance Release is completed | Kevin/Ray | Done | 2015-06-01 | Prod Candidate
| 2015-06-01 | Action | Inform Ray Waldron of Production Migration dates | Troy |  | 2015-06-10 | Infrastructure Update
21 | 2015-06-01 | Action | Finalize Release Summary of Functionality | Troy | N/A |  | Infrastructure Update
22 | 2015-06-01 | IMB | Send data conversion/code table update scripts to DA/DBA | Al P | N/A |  | Infrastructure Update
24 | 2015-06-01 | Communication | Production Control to Disable Automate Tasks | Tim/Crystal
24 | 2015-06-01 | Information | Production Environment taken down for migration | IMB
25 | 2015-06-01 | Documentation | Document new / revised Error Codes > tester to give updates to Helpdesk to review and forward to branch web analyst to post. Robo Help being updated. | Tim/Crystal
26 | 2015-06-01 | Documentation | Review Application Bulletins to assure postings / information are still correct regarding new release | Tim/Crystal
28 | 2015-06-01 | Documentation | Migrate HBS User Manual from Test to Production, after editing | Tim/Crystal | N/A |  | Infrastructure Update
29 | 2015-06-01 | IMB | Send Post-migration data conversion scripts to DBAs. | N/A | N/A |  | N/A Code only
30 | 2015-06-01 | IMB | Verify Post-migration data conversion script results, after they are done. | N/A | N/A |  | N/A Code only
31 | 2015-06-01 | IMB | Check data conversion/code table update scripts done | N/A | N/A |  | N/A Code only
32 | 2015-06-01 | IMB | Insure grants and permissions to new tables and views are in place. | IMB | N/A |  | N/A Code only
33 | 2015-06-01 | IMB | Verify data model changes in Prod | Ray/Kevin | Done | 2015-06-01 | Prod Candidate
34 | 2015-06-01 | IMB | Verify DA changes in Prod (in Toad) | Ray/Kevin | Done | 2015-06-01 | Prod Candidate
35 | 2015-06-01 | Documentation | Amend BridgeTrak ticket statuses to Prod Untested | UAT Team / Billing Team | N/A |  | Infrastructure Update
36 | 2015-06-01 | Documentation | Add the Repair Release # with description in BridgeTrak | UAT Team / Billing Team | N/A |  | Infrastructure Update
37 | 2015-06-12 | Testing | Test that the ENABLED_IND is N (user with no HBS_DISABLED_BYPASS role to attempt access). | Troy / Tim
38 | 2015-06-12 | Communication | Advise users with the HBS_DISABLED_BYPASS role that HBS is available for Prod Testing | Troy / Tim
39 | 2015-06-12 | Testing | Run daily performance tests | TPB Members
40 | 2015-06-12 | Testing | Begin post production Regression Testing | UAT Team
| 2015-06-12 | Testing | Check URL for registered and unregistered users |  |  |  | Al to send URL
| 2015-06-12 | Testing | Check for FTPS site
| 2015-06-12 | Testing | Check Both production servers
41 | 2015-06-12 | Testing | Run comprehensive performance tests if applicable (are there performance enhancements?) | Ray / Troy
42 | 2015-06-12 | Communication | Stability and performance of Production test completed | Ray / Kevin/Tim/Crystal
43 | 2015-06-12 | Communication | Advise Production Control to run XML batch processes System is up and notify Production | Troy / Tim
44 | 2015-06-12 | Testing | Confirm that no 'show stoppers' have been revealed in Production regression testing | Ray/Kevin / Tim
45 | 2015-06-12 | Testing | Run and Confirm from Prod Support that HBS Release 26 Batch Implementation Processing Plan has run (are running) successfully | Tim/Crystal
46 | 2015-06-12 | Communication | Send email to Websuppport requesting ENABLED_IND be set to Y | Troy / Tim
47 | 2015-06-12 | Communication | Receive confirmation from WebSupport that Enabled Indicator is turned on | Troy / Tim
48 | 2015-06-12 | Documentation | Publish Summary of Functionality on FTP folder: \\mitten.dmz\HVA\external\!publish\HBS Help Desk, include link in Application Bulletin | Rick | N/A |  | Infrastructure Update
49 | 2015-06-18 | Communication | Notify users of system’s availability on bulletin board | Tim/Crystal
50 | 2015-06-18 | Communication | Request Production Control to remove Text Banner in HBS Prod | Troy
51 | 2015-06-18 | Communication | Advise Production Control to continue batch jobs per their checklist. | Troy
52 | 2015-06-18 | Communication | Advise Production Control to Enable batch jobs in AutoMate, per their checklist | Troy
68 | 2015-06-18 | Documentation | Remove bulletins made obsolete by this Release from HBS Application Bulletin Board | Tim/Crystal
69 | 2015-06-18 | Documentation | Ensure any FINAL amendments to HBS User Manual are also reflected in online manual | Troy | N/A |  | Infrastructure Update
70 | 2015-06-18 | Documentation | Update the Role-Page Matrix spreadsheet | Al P | N/A |  | Infrastructure Update
71 | 2015-06-18 | Documentation | List all new/changed error codes, complete the Error Code Template and forward the consolidated list Web Analyst. Ensure these changes are reflected in the HBS User Manual (electronic and on-line). | Troy | N/A |  | Infrastructure Update
72 | 2015-06-18 | Documentation | Ensure that information on the HBS Project page: http://www.for.gov.bc.ca/hva/hbs/ are updated to reflect updated information. | Troy
73 | 2015-06-18 | Documentation | Ensure that information on the Business Information Centre homepage: http://gww.for.gov.bc.ca/his/bic/business/billing/ is updated. Check Billing Business Process: Step Details. Send a note to IMB to with a list of requested changes. CC to Al. | Troy
74 | 2015-06-18 | Communication | Email Al P about issues with checklist after release of Release to Production (for PIR) | Troy
75 | 2015-06-18 | Documentation | File all important Release communication in TRIM | Ashley / Troy
76 | 2015-06-18 | Documentation | Archive Release Documentation (Ticket List; Release Summary; Implementation Checklist; Test Documentation) | Troy
77 |  | Review | Post Implementation Review meeting | Al P
Action
Documentation
Communication
Testing
IMB/Vendor

## Notes
NOTES
1
2
3

## BT PROD TEST
Migration Testing for BridgeTrak Tickets
Tcikets | Issue | Status | Tesing in Prod with HBS Down | QA Tester | Comments
BT11393 | Modify the bulk change function (P601) so that it handles saving a PSY. | Passed UAT |  | E.T.
BT17981 | Entry_timestamp is being overwritten by Update_timestamp for Cruise Based Billing Profile. | Passed UAT |  | Troy | This ticket is on hold as per the request of the BPM it is currently to spec and will be left as is untill a further time.
BT17791 | Provincial Wood Measurement Specialist requesting a fix to the Standard Deviation for Sub-samples. | Passed UAT |  | Troy/Peter/Steve
BT18110 | Area Based return is in error with a 'CBSS02 - District of Scale Site confilicts with District of Timber Mark' error. | Passed UAT |  | Troy
BT18239 | DB Monitor - inconsistent document emails are produced and sent to the BBS mailbox when a Summary Returns is HELD and the version number is incremented. | Passed UAT |  | Troy