| Contract Numbers | Description of Works and/or Services to be Included (Contract Scope) | Tendering Method | Advertising Date | Anticipated Closing/ Opening Date | *Anticipated Works/ Services Start-up | Total Completion of Works Date |
| --- | --- | --- | --- | --- | --- | --- |
| EN1136E005 | 30 km – 38 km | Invitation to Tender | May 13, 2010 | June 10, 2010 | *June 28, 2010 | October 15, 2010 |
| EN1136E006 | 2300 Road | Invitation to Tender | May 19, 2010 | June 22, 2010 | *July 5, 2010 | September 20, 2010 |
| EN1136E008 | 7 km – 30 km | Invitation to Tender | May 28, 2010 | June 24, 2010 | *July 12, 2010 | December 15, 2010 |
| EN1136E009 | 38 km – 64 km | Invitation to Tender | June 1, 2010 | June 23, 2010 | *July 9, 2010 | November 30, 2010 |
| EN1136E010 | Creek Crossing + 2 km Construction (Rainbow Rd) | Invitation to Tender | May 28, 2010 | June 22, 2010 | *July 5, 2010 | November 1, 2010 |
| EN1136E011 | Quality Assurance Testing | Invitation to Tender | May 19, 2010 | June 10, 2010 | *June 28, 2010 | November 30, 2010 |

FORT ST JAMES – MACKENZIE CONNECTOR ROAD PROJECT

TENTATIVE CONTRACT SCHEDULE

(Updated June 2, 2010)

*Please note that the anticipated works dates are only tentative at this time.  The schedule will be updated as more information becomes available and/ or changes are made.