	Contract Numbers
	Description of Works and/or Services to be Included (Contract Scope)
	Tendering Method
	Advertising Date
	Anticipated Closing/
Opening Date
	*Anticipated Works/
Services Start-up
	Total Completion of Works Date

	EN1136E005
	30 km – 38 km
	Invitation to Tender
	May 13, 2010
	June 10, 2010
	*June 28, 2010
	October 15, 2010

	EN1136E006
	2300 Road
	Invitation to Tender
	May 19, 2010
	June 22, 2010

	*July 5, 2010
	September 20, 2010

	EN1136E008
	7 km – 30 km
	Invitation to Tender
	May 28, 2010
	June 24, 2010
	*July 12, 2010
	December 15, 2010

	EN1136E009
	38 km – 64 km
	Invitation to Tender
	June 1, 2010
	June 23, 2010
	*July  9, 2010
	November 30, 2010

	EN1136E010
	Creek Crossing + 2 km Construction (Rainbow Rd)
	Invitation to Tender
	May 28, 2010
	June 22, 2010

	*July 5, 2010
	November 1, 2010

	EN1136E011
	Quality Assurance Testing
	Invitation to Tender
	May 19, 2010
	June 10, 2010
	*June 28, 2010
	November 30, 2010


FORT ST JAMES – MACKENZIE CONNECTOR ROAD PROJECT
TENTATIVE CONTRACT SCHEDULE 
(Updated June 2, 2010)

*Please note that the anticipated works dates are only tentative at this time.  The schedule will be updated as more information becomes available and/ or changes are made.





