## Sheet1
Step | Function | Timing | Accountability | Planning Bucket, main tree……. | Block or License or Road level | Applicable Field | Instruction | Data Resources
1 | Create a cutblock; enter appropriate data, activities and tasks | As soon as a blob is identified | Planner; Contract coordinator. | Planning Bucket | Block | Create cutblock |  | BWF04
BA Naming Convention. [FILE LOCATION UNKNOWN]
Planning and Block Creation
[6 empty] | Spatial | Digitize/Copy cutblock/Link | GBWF07
[6 empty] | RCDR | Planned | Managing Licence & Block Activities
BWF19
[6 empty] | 5yr Plan date | Planned | QR_PlanningBlob_Road_5YRplanProcess
[6 empty] | Activity PP Proposed | "Planned" - NOT "Information". | Corporate Mandatory Data Fields
[6 empty] | Volume estimate |  | BWF05-Create
[6 empty] | Block State | PP | Corporate Mandatory Data Fields
[6 empty] | Recce activity | Planned | Managing Licence & Block Activities
BWF19
[6 empty] | Tasks | As needed | BWF04
QR_Entering_and_Printing_Tasks
1A | Create a non-FSR or FSR road, enter appropriate data and activities | As soon as a blob is identified | Planner; Contract coordinator. | Roads | Road | Enter road; Link spatial; Planned const'n date; Planned Cost; Road state - PP. | Leave 'steward' blank until know what tenure will be used. | RWF01
GBWF04
GBWF05
RoadsSOP
[6 empty] | Planned cost |  | RWF08
Corporate Mandatory Data Fields
2 | Block Recce | Field verify | Contract coordinator; Planner. | Planning Bucket | Block | Update Volume as needed. |  | BWF05-Create
[6 empty] | Recce activity | Done | Managing Licence & Block Activities
[6 empty] | RCDR | Update if applicable | Managing Licence & Block Activities
BWF19
[6 empty] | consultation activities Referrals sent; FN2PFR; FN4Complete. | Planned.
[6 empty] | 5Yr Plan date. Make same as auction date | Update if applicable
[6 empty] | Auction date. | Make same as 5yr Plan date.
2A | Road Recce | Along with block recce | Contract coordinator. | Roads | Road | Upadates if applicable |  | RoadsSOP
RWF08
See also resources in step 1A.
AA | Defer the block if it can't proceed at this time. | Could occur any time from recce through to just prior to advertising a sale. | Planner; Contract coordinator. | Planning Bucket or Main tree | Block | Adjust 5yr plan date and auction date. Same dates. | Do relevant road updates as well. | Corporate Mandatory Data Fields
QR_PlanningBlob_Road_5YRplanProcess
Managing Licence & Block Activities
BWF19
[6 empty] | Plan Status | Deferred (pick one of two reasons) | Corporate Mandatory Data Fields
Deferred activity
Deferring Process
[5 empty] | Road | road updates |  | RoadsSOP
See also sources in step 1A.
3 | referrals; consultation; status update; | After field verified. | Planner; Contract coordinator. | Planning Bucket | Block | Activity PP Proposed | Done | Corporate Mandatory Data Fields
[6 empty] | consultation activities Referrals sent; FN2PFR; FN4Complete; Assesments. | Enter recce report. | Managing Licence & Block Activities
BWF19
[6 empty] | Tasks | As needed. | BWF04
QR_Entering_and_Printing_Tasks
[6 empty] | RCDR | Done. | QR_PlanningBlob_Road_5YRplanProcess
[6 empty] | 5Yr Plan and Auction dates | Update if applicable | QR_PlanningBlob_Road_5YRplanProcess
Managing Licence & Block Activities
BWF19
3A | Rds Consultation | Done separately for FSR, or along with block conultation | Planner; Contract coordinator. | Roads | Road |  |  | RoadsSOP
See also sources in step 1A.
4 | Block Layout | When first dollar spent on UBI; referrals are completed, and FN at least able to be risk managed. | Contract coordinator; GIS. | Main tree once UBI generated. | Block | Generate UBI |  | BA Naming Convention. [FILE LOCATION UNKNOWN]
UBI Generator
[6 empty] | Change Block name. |  | BA Naming Convention. [FILE LOCATION UNKNOWN]
[6 empty] | Block State | DIP | Corporate Mandatory Data Fields
[6 empty] | TSL #; Assign blks to license. |  | Timber Sale Licence Assignment
BWF18
QR_MovingBlocksToNewLicence
[6 empty] | Update blk and rd spatial as required. Edit non-managed data. |  | GBWF04
GBWF05
GBWF06
GBWF07
GBWF21
Planning and Block Creation
[6 empty] | Activity Development Started | Done | Managing Licence & Block Activities
BWF19
Ensure volume is allocated.
4A | Acquire License # | When referrals completed, and FN at least able to be risk managed. | Ops Techs. |  |  |  |  | Timber Sale Licence Assignment
4B | Create License | When License has been acquired. | Contract coordinator. | Main tree | License |  | Create License | BWF01
Timber Sale Licence Assignment
[6 empty] | License State | PP | License State Trigger Process
Corporate Mandatory Data Fields
[6 empty] | Estimated volume |  | BWF05-Create
[6 empty] | Activity AUC Auction | Planned | Corporate Mandatory Data Fields
4C | Road updating/changes ALL ROADS | Along with block layout. | Contract coordinator. | Roads | Road | Make any road changes | Re-refer, consult as required. | RWF04
RWF02
RWF03
GBWF05
RoadsSOP
RWF01
[6 empty] | Planned Construction Date; Road class; Road length; Road steward. |  | RoadsSOP
Corporate Mandatory Data Fields
RWF08
RWF03
4D | Road Permit roads ONLY | Along with block layout. | Contract coordinator. | Roads | Road | Road site plan |  | RWF25
Road Site Plan Report
[6 empty] | Create and submit xml to FTA |  | RWF06
[5 empty] | Road; Block | URI; Cutblock-UBI/URI link. |  | Road - Block Link Tool
RoadsSOP
UBI/URI Linkage
GBWF05
4E | Road Permit AND Schedule 'C' Roads | Along with block layout. | Contract coordinator. | Roads | Road | Road appriaisal data |  | RWF04 interior
[6 empty] | Planned deactivation date |  | RoadsSOP
Corporate Mandatory Data Fields
[5 empty] | Road; Block | Cutblock-UBI/URI link. |  | RoadsSOP
UBI/URI Linkage
GBWF05
BB. | Write-Off the block, if it will never be viable. | Could occur any time from blk layout through to just prior to advertising a sale. | Contract coordinator. | Planning Bucket or Main tree | Block | Block State to WO, and other applicable fields. | Do full process of Write-of and Delete. Do relevant road updates as well. | Block Deletion Process
Corporate Mandatory Data Fields
Managing Licence & Block Activities
[5 empty] | Road | Road updates |  | RoadsSOP
5 | Cruise Compilation | After block layout. | Ops Techs. | N/A | N/A |  | Not performed in LRM
5A | FSR Roads | After block layout. | Engineering Tech | Main tree | Road | Create and submit xml to FTA; | Main rd linked to 1st block. | RWF06
RWF02
[6 empty] | Road Site Plan |  | Road Site Plan Report
RWF25
[6 empty] | FLTC |  | See step 6B.
BWF15
[6 empty] | planned const cost |  | RWF08
5A(i) | FSR Roads | After block layout. | Engineering Tech | Main tree | Road | Activity Road plan status | Complete | RoadsSOP
URI
6 | ADV and ready for advertising, Blocks and License | All activities complete | Contract coordinator; Planner; GIS. | Main tree | Block | FTA block reporting |  | BWF12
[6 empty] | Generate a Site Plan. |  | SWF01
Block Site Plan Report
[6 empty] | Blk State | ADV | Managing Licence & Block Activities
BWF19
Corporate Mandatory Data Fields
[6 empty] | Edit Non-Managed Data. |  | GBWF21
[6 empty] | Create Managed Data; HVS logging started - Planned date; Appraisal data entry CENGEA/LRM; Access; FN sign-off. |  | Managing Licence & Block Activities
BWF19
Corporate Mandatory Data Fields
[6 empty] | Activity | Development Completed - Done | Managing Licence & Block Activities
BWF19
Corporate Mandatory Data Fields
6A | Finalize License on Sales Schedule; License activities | All blks and License are ADV | Contract coordinator. | Main tree | License | License state | ADV | License State Trigger Process
Corporate Mandatory Data Fields
[6 empty] | Block reallocation as required |  | BWF18
[6 empty] | Cruise comp and import cruise data. |  | BWF05-import
Cruise Volume Updates
[6 empty] | Create/submit appraisal data. |  | BWF06 interior
Completing Appraisals and ECAS Submissions
BWF12
6B | FLTC Process for FSR's | After UBI-URI linked for FSR. | Engineering Tech | Main tree | Road | FLTC |  | RoadsSOP
BWF15
BWF12
6C | FSR Post-Construction | When construction completed | Engineering Tech; GIS. | Main tree | Road | Cost survey data. |  | RWF11 interior
Interior Cost Survey
[6 empty] | Construction completed date and cost; Length; Planned deactivation/ transfer date and cost; Risk rating; Planned inspections; Accounting type; Road State - Wilderness. |  | RoadsSOP
RWF01
7 | TSL Package is prepared. | After ADV achieved. | Timber Tech; Ops Tech; Practices Forester. | Main tree | License | AUC Auction | Planned | Corporate Mandatory Data Fields
[6 empty] | Appraisal Volume; VCU calcualtion if neded. |  | BWF06 interior
Completing Appraisals and ECAS Submissions
Corporate Mandatory Data Fields
BWF12
8 | Advertized |  | Admin staff | Main tree | License | Tender posted |  | Corporate Mandatory Data Fields
9 | Bids opened/ Auction closes. |  | Admin staff | Main tree | License | AUC Auction | Done | Corporate Mandatory Data Fields
10 | Offer made to Successful bidder |  | Admin staff | Main tree | License | HA License Awarded | Done | Corporate Mandatory Data Fields
[6 empty] | License state | HA | License State Trigger Process
Corporate Mandatory Data Fields
10A | Offer made to Successful bidder |  | Admin staff | N/A | FTA | HA License Awarded | Done
11 | License signed by both parties |  | Admin staff | Main tree | License | HI License Issued | Done | Corporate Mandatory Data Fields
[6 empty] | License state | HI | License State Trigger Process
Corporate Mandatory Data Fields
11A | License signed by both parties |  | Admin staff | N/A | FTA | HI License Issued | Done
11B | Block Sold |  | Ops Tech. | Main tree | Block | HVS Logging Started | Planned | Corporate Mandatory Data Fields
[6 empty] | 5yr Plan | Done | QR_PlanningBlob_Road_5YRplanProcess