Monitoring Inspection

EN21TFD005 – Kokanee 8500

| Inspector: Gary Shannon |  | Date: November 12, 2020 |  |
| --- | --- | --- | --- |
| Contract #: EN21TFD005 |  | Contractor Name: Bad Ventures Contracting Ltd. |  |
| Weather: -2C; light snow; 5 cm snow cover |  | Persons on site: Don Cook, Mike |  |
| Active Construction Phases |  | Active Equipment |  |
| Kokanee 8500 | Debris burning; moving wood; processing | Kokanee 8500 | Excavator Hub 105 to POT 336 hoe moving wood; 320 hoe and buckerman processing |
| 8510 | No active operations | 8510 | N/A |

SPUR 8500

R/W ( active )
- pilot trail to POT 
- pushover falling complete to POT 
- active log processing at hub 105
- no log hauling today 

GRUBBING and STRIPPING ( active)
- approximately 90% complete to POT 

DEBRIS DISPOSAL (active)
- approximately 25% of burning complete to POT 

ENDHAUL 
- designed endhaul Hub 1-8 ( 409 m3) complete, no volume adjustments required.
- designed endhaul Hub 69-72 (332 m3) complete, no volume adjustments required.
- all within 500 m haul distance to designated sites as discussed

DRILL and BLASTING 
- large boulder at Hub 14(7 m3) was rock hammered.

SUBGRADE

- approximately 90% complete from POC to Hub 92.

- some sections still require ditching.

DRAINAGE

- 3, 600 mm culverts installed to date

- 2, 450 mm culverts installed to date.

- 1200 mm culvert at Hub 30 requires re install to seal coupler as discussed prior

- 1200 mm culvert at Hub 102 installed, requires inlet armour.

- additional 450 mm to be installed at seep Hub 107.

- designed 450 mm cross drain culvert at Hub 26, approve to shift down approximately 10 m to location within same basin.

- designed 450 mm culvert at Hub 9, not required  - no place to catch on public road

- 18 m of 600 mm culvert installed at 8500 junction replacing existing undersized culvert on public road

- Kokanee M/L culverts are marked.

SPUR 8510 ( not active)

R/W

- pushover falling complete

GRUBBING and STRIPPING

- complete

DEBRIS DISPOSAL

- complete

DRILL and BLASTING

- none to date and little more anticipated

- no solid rock, but larger boulders encountered may require blasting; to be completed at end, at one time

DRAINAGE

- none installed to date

SUBGRADE

- none to date

ENDHAUL

- Top of cut as original design, but lacking rock results in road that is shifted out; this change to be formally established with as-built measurement to capture updated volume

- approximately 500 m3 hauled within 500 m for road ballast.

- approximately 1500 m3 hauled to lift road grade from Hub 30 to junction, 1 km haul.

- remaining volume designated to lift road grade from Hub 43-35.

DISCUSSIONS

- Mike,Don,Della, Gary reviewed road to POT.

- discussed options for remaining endhaul, lifting grade at Hub 43-35, Hub 70-90.

- reviewed culvert changes on 8500 and 3 new 450 mm xings on Kokanee M/L

as per TSA.

- discussed substantial completion; appears that operations could be completed near the required date;

- discussed endhaul volume adjustments that will be required on 8510 due to lack

of rock.  Load count to be used to pro-rate final volume to haul payment categories
- Estimated paycert will be proposed this week

EMS/ SAFETY

-project quality remains good – to spec.  
-Signage and communication also in compliance.
-snow plowing will likely be required on the public road for access after the anticipated winter storm; discussed that use of dozer will need to be light handed to ensure that recent surfacing is not damaged.

-reminder to ensure that turnouts are plowed in anticipation of other traffic.

PHOTOS