Monitoring Inspection
EN21TFD005 – Kokanee 8500
	Inspector:  Gary Shannon
	Date:  October 1, 2020


	Contract #: EN21TFD005
	Contractor Name: Bad Ventures Contracting Ltd.


	Weather:   +12 C; overcast
	Persons on site: Don Cook, Mike ?


	Active Construction Phases
	Active Equipment

	Kokanee 8500 
	R/W Felling
Stripping
	Kokanee 8500
	 Excavator, processor




R/W ( active processing only)
- pilot trail to Hub 53.
- pushover falling complete to Hub 53 all with R/W.
- stakes, ticks and r/w ribbons remain in place.
- self loader is hauling 1-2 loads.

GRUBBING and STRIPPING
- approximately 150 m of stripping partially complete

DEBRIS DISPOSAL
- none to date

SUBGRADE
- Hub 15-25 ( approx 100 m) to rough grade.

DRAINAGE
- temp culvert has been installed at Hub 30 to control water at 1200 mm xing.
- no other water issues.

DRILL and BLASTING
- none to date
- larger boulders encountered so far on pilot will require measuring prior to blasting.

ENDHAUL
- none to date


Discussions
- discussed removal and piling of debris along lower side of r/w.
- discussed sloping over burden along fill slope.

EMS and Safety
- Mike will be meeting with Don this weekend to complete all EMS paperwork as per
   prework requirements, training summary update etc.
-Photos below of info provided to date
- signage posted, all safety practices being implemented.
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