Monitoring Inspection

EN21TFD005 – Kokanee 8500

| Inspector: Gary Shannon |  | Date: October 1, 2020 |  |
| --- | --- | --- | --- |
| Contract #: EN21TFD005 |  | Contractor Name: Bad Ventures Contracting Ltd. |  |
| Weather: +12 C; overcast |  | Persons on site: Don Cook, Mike ? |  |
| Active Construction Phases |  | Active Equipment |  |
| Kokanee 8500 | R/W Felling Stripping | Kokanee 8500 | Excavator, processor |

R/W ( active processing only)

- pilot trail to Hub 53.

- pushover falling complete to Hub 53 all with R/W.

- stakes, ticks and r/w ribbons remain in place.

- self loader is hauling 1-2 loads.

GRUBBING and STRIPPING

- approximately 150 m of stripping partially complete

DEBRIS DISPOSAL

- none to date

SUBGRADE

- Hub 15-25 ( approx 100 m) to rough grade.

DRAINAGE

- temp culvert has been installed at Hub 30 to control water at 1200 mm xing.

- no other water issues.

DRILL and BLASTING

- none to date

- larger boulders encountered so far on pilot will require measuring prior to blasting.

ENDHAUL

- none to date

Discussions

- discussed removal and piling of debris along lower side of r/w.

- discussed sloping over burden along fill slope.

EMS and Safety

- Mike will be meeting with Don this weekend to complete all EMS paperwork as per

prework requirements, training summary update etc.

-Photos below of info provided to date

- signage posted, all safety practices being implemented.

Photos