Monitoring Inspection
EN21TFD005 – Kokanee 8500
	Inspector:  Gary Shannon
	Date:  October 15, 2020


	Contract #: EN21TFD005
	Contractor Name: Bad Ventures Contracting Ltd.


	Weather:   0C, Clear
	Persons on site: Mike 


	Active Construction Phases
	Active Equipment

	Kokanee 8500 
	Subgrade construction ; r/w
	Kokanee 8500
	 Excavator, processor




ACTIVE EQUIPMENT 
- linkbelt hoe working on switchback at Hub 65
- 320 hoe processing wood at Hub 43
- D8 parked

8500
R/W
- pilot trail to POT
- pushover falling complete to POT
- processing of R/W wood approximately 75% complete to Hub 70.
- approximately 50% of processed wood to Hub 70 hauled.
- R/W wood processing continues POC to Hub 70

GRUBBING and STRIPPING 
- substantially complete to Hub 55

DEBRIS DISPOSAL 
- none to date.
- some excess debris has been piled.
- debris along lower r/w needs to be removed, piled and burned.

ENDHAUL 
- none to date 

DRILL and BLASTING 
- none to date 
- some larger boulders encountered on pilot will require measuring and blasting.

SUBGRADE 
- approximately 75% complete to rough grade from Hub 10-60.
- construction of junction to be completed 
- linkbelt hoe started on switchback construction at Hub 70.

DRAINAGE 
- Hub 30 1200 mm reinstall has not been completed.
- temp culvert installed at 1200 mm xing at Hub 102.
- no water issues.

DISCUSSIONS 
- reviewed potential waste site with Gord and Mike, lifting road grade Hub 32-44.
- work signage posted 
- EMS binder on site.
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