Monitoring Inspection

EN21TFD005 – Kokanee 8500

| Inspector: Gary Shannon |  | Date: October 15, 2020 |  |
| --- | --- | --- | --- |
| Contract #: EN21TFD005 |  | Contractor Name: Bad Ventures Contracting Ltd. |  |
| Weather: 0C, Clear |  | Persons on site: Mike |  |
| Active Construction Phases |  | Active Equipment |  |
| Kokanee 8500 | Subgrade construction ; r/w | Kokanee 8500 | Excavator, processor |

ACTIVE EQUIPMENT 
- linkbelt hoe working on switchback at Hub 65
- 320 hoe processing wood at Hub 43
- D8 parked

8500
R/W
- pilot trail to POT
- pushover falling complete to POT
- processing of R/W wood approximately 75% complete to Hub 70.
- approximately 50% of processed wood to Hub 70 hauled.
- R/W wood processing continues POC to Hub 70

GRUBBING and STRIPPING 
- substantially complete to Hub 55

DEBRIS DISPOSAL 
- none to date.
- some excess debris has been piled.
- debris along lower r/w needs to be removed, piled and burned.

ENDHAUL 
- none to date 

DRILL and BLASTING 
- none to date 
- some larger boulders encountered on pilot will require measuring and blasting.

SUBGRADE 
- approximately 75% complete to rough grade from Hub 10-60.
- construction of junction to be completed 
- linkbelt hoe started on switchback construction at Hub 70.

DRAINAGE 
- Hub 30 1200 mm reinstall has not been completed.
- temp culvert installed at 1200 mm xing at Hub 102.
- no water issues.

DISCUSSIONS 
- reviewed potential waste site with Gord and Mike, lifting road grade Hub 32-44.
- work signage posted 
- EMS binder on site.


Photos