Monitoring Inspection
EN21TFD005 – Kokanee 8500
	Inspector:  Gary Shannon
	Date:  October 28, 2020


	Contract #: EN21TFD005
	Contractor Name: Bad Ventures Contracting Ltd.


	Weather:   -2C; light snow; 5 cm snow cover
	Persons on site: Don Cook, Mike


	Active Construction Phases
	Active Equipment

	Kokanee 8500 
	Debris burning; end haul
	Kokanee 8500
	 Excavator, rock truck

	8510
	Stripping
	8510
	Excavator



ACTIVE EQUIPMENT 
- linkbelt hoe stripping 8510 spur 
- 320 hoe debris burning at Hub 50 on 8500
- rock truck hauling debris to Hub 50 on 8500
- D8 parked.

SPUR 8500

R/W
- pilot trail to POT
- pushover falling complete to POT 
- log processing 75% complete to Hub 70

GRUBBING and STRIPPING 
- substantially complete to Hub 80, except at junction.

DEBRIS DISPOSAL 
- approximately 5% of debris burning complete to Hub 60.
- active burning at Hub 50.
- hoe loading rock truck hauling to burn pile at Hub 50.
- debris along R/W from POC to Hub 60 requires piling and burning.

ENDHAUL 
- none to date 

DRILL and BLASTING 
- none to date 

SUBGRADE 
- approximately 75% complete to rough grade from Hub 10-80.

DRAINAGE 
- reinstall of 1200 mm culvert at Hub 30 not completed.
- temp culvert installed at Hub 102.
- no water issues.

DISCUSSIONS 
- reviewed junction and road to Hub 80 with Mike.
- discussed need to out slope of strippings along fill to shed water.
- Given increasing winter conditions, and looming deadlines, some discussion regarding the need to focus on concurrent construction such as completion of debris disposal to ensure that earthworks and drainage phases can be completed; detailing with burning of debris prior to extensive snow is suggested.
- we reviewed the junction work to be completed, there is no public traffic or 
  graveling traffic.
- work signage posted 
- binder and plans on site.
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SPUR 8510

R/W
- pushover falling complete to POT 

GRUBBING and STRIPPING 
- approximately 75% complete 

DEBRIS DISPOSAL 
- none to date 

ENDHAUL 
- none to date 

DRILL and BLASTING 
- none to date 

SUBGRADE 
- none to date 

DRAINAGE 
- none to date 

DISCUSSIONS 
-  had hoe dig 2 test pits at Hubs 7 & 10 to try and intercept S/R as per x- sections 
  there was rock intercepted a bit higher than x- sections, appears minimal staking 
  adjustments required.
- discussed possibly wasting endhaul material to lift grade below the switch back 
  on 8500, to further review once the switch back is to design grade.
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