Monitoring Inspection

EN21TFD005 – Kokanee 8500

| Inspector: Gary Shannon |  | Date: October 9, 2020 |  |
| --- | --- | --- | --- |
| Contract #: EN21TFD005 |  | Contractor Name: Bad Ventures Contracting Ltd. |  |
| Weather: +12 C; overcast |  | Persons on site: Don Cook, Mike ? |  |
| Active Construction Phases |  | Active Equipment |  |
| Kokanee 8500 | R/W, pushover Felling Stripping | Kokanee 8500 | Excavator, processor |

R/W ( active)

- pilot trail to Hub 92

- active log hauling, one load per day

GRUBBING and STRIPPING ( active)

- substantially complete to Hub 55

DEBRIS DISPOSAL

- none to date

- debris along lower r/w requires removal, piling and burning.

ENDHAUL

- none to date

DRILL and BLASTING

- none to date

- some larger boulders encountered on pilot trail that will require measurement

and blasting.

SUBGRADE

- approximately 75% to rough grade to Hub 55.

- debris along fill requires pull-up,piling and burning.

DRAINAGE

- 1200 mm culvert installed at Hub 30. ( see discussions)

- 450 mm culvert installed at Hub 40.

- 600 mm culvert installed at Hub 48.

DISCUSSIONS

- reviewed the 1200 mm culvert installed at Hub 30, coupler not sealed with

poor alignment. Don agreed to have it reinstalled.

- met on site with Don and Alex and Mike and reviewed road to Hub 102 ( 1200 mm )

- discussed waste sites for 8510 endhaul, there are no TSA wastesites prescribed.

- designed wastesites #2 and #3 will not accommodate the 4600 m3 from 8510 Spur

- would like to review with SCL ( Ted) for potential waste sites.

- could waste approximately 1000-1500 m3 to lift road from Hub 35-43.