Monitoring Inspection
EN21TFD005 – Kokanee 8500
	Inspector:  Gary Shannon
	Date:  October 9, 2020


	Contract #: EN21TFD005
	Contractor Name: Bad Ventures Contracting Ltd.


	Weather:   +12 C; overcast
	Persons on site: Don Cook, Mike ?


	Active Construction Phases
	Active Equipment

	Kokanee 8500 
	R/W, pushover Felling
Stripping
	Kokanee 8500
	 Excavator, processor




R/W ( active)
- pilot trail to Hub 92
- active log hauling, one load per day

GRUBBING and STRIPPING ( active)
- substantially complete to Hub 55

DEBRIS DISPOSAL
- none to date
- debris along lower r/w requires removal, piling and burning.

ENDHAUL
- none to date

DRILL and BLASTING
- none to date
- some larger boulders encountered on pilot trail that will require measurement
   and blasting.

SUBGRADE
- approximately 75% to rough grade to Hub 55.
- debris along fill requires pull-up,piling and burning.

DRAINAGE
- 1200 mm culvert installed at Hub 30. ( see discussions)
- 450 mm culvert installed at Hub 40.
- 600 mm culvert installed at Hub 48.




DISCUSSIONS
- reviewed the 1200 mm culvert installed at Hub 30, coupler not sealed with
   poor alignment. Don agreed to have it reinstalled.
- met on site with Don and Alex and Mike and reviewed road to Hub 102 ( 1200 mm )
- discussed waste sites for 8510 endhaul, there are no TSA wastesites prescribed.
- designed wastesites #2 and #3 will not accommodate the 4600 m3 from 8510 Spur
- would like to review with SCL ( Ted) for potential waste sites.
- could waste approximately 1000-1500 m3 to lift road from Hub 35-43.
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