Monitoring Inspection
EN21TFD005 – Kokanee 8500
	Inspector:  Gary Shannon
	Date:  September 23, 2019


	Contract #: EN21TFD005
	Contractor Name: Bad Ventures Contracting Ltd.


	Weather:   +14 C
	Persons on site: Mike


	Active Construction Phases
	Active Equipment

	Kokanee 8500 
	Push – over r/w falling
	
	 Excavator



ACTIVE EQUIPMENT
- hoe pilot and pushover falling
- hoe sorting and hand bucking pushover

R/W
- pilot trail to approximately Hub 20.
- pushover falling within the R/W complete to Hub 20
- pushover trees piled along lower R/W.
- no landings constructed to date.

DEBRIS DISPOSAL
- none to date

SUBGRADE
- none to date

DRAINAGE
- no culverts installed to date

ENDHAUL
- None to date

DRILL and BLASTING
- none to date

DISCUSSIONS
EMS and Safety
Gord to complete formal EMS Inspection, however, the following are some concerns that are raised with initial review for prior consideration:
-non-spec fuel tank is being used; no decals
-contractor is camping with trailer along public road; 
-expressed concern for r/w methodology and no plans to pre-construct landings;  Anticipate congestion.  
-Emphasize that operations cannot over-flow to public road ie: equipment and timber cannot be placed within the r/w of Kokanee Glacier Road.  Encourage that pilot trail and landing be established on the new construction as soon as possible to optimize operations and to limit over-flow.
-Emphasized that SNAGS need to be addressed as part of the right of way phase; contact info for local faller provided.
-Good signage in place at the site;  EMS binder is present; Gord to complete full inspection next week.
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