Monitoring Inspection

EN21TFD005 – Kokanee 8500

| Inspector: Gary Shannon |  | Date: September 23, 2019 |  |
| --- | --- | --- | --- |
| Contract #: EN21TFD005 |  | Contractor Name: Bad Ventures Contracting Ltd. |  |
| Weather: +14 C |  | Persons on site: Mike |  |
| Active Construction Phases |  | Active Equipment |  |
| Kokanee 8500 | Push – over r/w falling |  | Excavator |

ACTIVE EQUIPMENT

- hoe pilot and pushover falling

- hoe sorting and hand bucking pushover

R/W

- pilot trail to approximately Hub 20.

- pushover falling within the R/W complete to Hub 20

- pushover trees piled along lower R/W.

- no landings constructed to date.

DEBRIS DISPOSAL

- none to date

SUBGRADE

- none to date

DRAINAGE

- no culverts installed to date

ENDHAUL

- None to date

DRILL and BLASTING

- none to date

DISCUSSIONS
EMS and Safety

Gord to complete formal EMS Inspection, however, the following are some concerns that are raised with initial review for prior consideration:
-non-spec fuel tank is being used; no decals
-contractor is camping with trailer along public road; 
-expressed concern for r/w methodology and no plans to pre-construct landings;  Anticipate congestion.

-Emphasize that operations cannot over-flow to public road ie: equipment and timber cannot be placed within the r/w of Kokanee Glacier Road.  Encourage that pilot trail and landing be established on the new construction as soon as possible to optimize operations and to limit over-flow.
-Emphasized that SNAGS need to be addressed as part of the right of way phase; contact info for local faller provided.
-Good signage in place at the site;  EMS binder is present; Gord to complete full inspection next week.

Photos